## pmr
[6 empty] | ANNEX A | [18 empty] | ANNEX B
[6 empty] | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | Bureau of Broadcast Services Procurement Monitoring Report as of December 31, 2022
Code (PAP) |  |  |  |  | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
[8 empty] | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| 1 | 2022-01-0014 | 2022-07-0077 | Roadstar Trade Sales, Corp. | 4 Pieces - Tires/Wheels | [19 empty] | Cebu |  | Small Value Procurement | [7 empty] | 2022-07-01 | [6 empty] | 21600 | 21600 |  | 21480 | 21480
| 2 | 2022-06-0286 | 2022-07-0078 | The New Laoag Auto Supply | 1 Unit - 2SM Battery Gold | [19 empty] | Laoag |  | Small Value Procurement | [7 empty] | 2022-07-07 | [6 empty] | 6047 | 6047 |  | 6047 | 6047
| 3 | 2022-06-0246 | 2022-07-0079 | CBCD Trading | 1 - Carpet 4 yards x 7 yards | [19 empty] | Tabuk |  | Small Value Procurement | [7 empty] | 2022-07-07 | [6 empty] | 26600 | 26600 |  | 9570 | 9570
| 4 | 2022-06-0269 | 2022-07-0080 | Luzon Sales Co. Inc. | 8 Pieces - LISO Plainsheet #24 4x8 FT, 10 Pieces - Elbow PVC ¾ (Blue or Orange), 1 Gallon - Baseboard Maple Gloss Latex | [19 empty] | COA |  | Small Value Procurement | [7 empty] | 2022-07-07 | [6 empty] | 8410 | 8410 |  | 6540 | 6540
| 5 | 2022-06-259 | 2022-07-0083 | Mostaco Marketing | 80 Gallons - Alcohol, 30 Cans - Lysol 510g, 270 Boxes - Face Mask | [19 empty] | General Services |  | Shopping 52.1B | [7 empty] | 2022-07-11 | [6 empty] | 88400 | 88400 |  | 54470 | 54470
| 6 | 2022-06-0258 | 2022-07-0082 | Mostaco Marketing | 1 Lot - Office Suppliea | [19 empty] | Property and Supply Section |  | Shopping 52.1B | [7 empty] | 2022-07-11 | [6 empty] | 133200 | 133200 |  | 85970 | 85970
| 7 | 2022-06-0278 | 2022-07-0081 | Cagayan Appliance Center | 2 Units - 2HP Inverter Window Type Airconditioner | [19 empty] | Tuguegarao |  | Small Value Procurement | [7 empty] | 2022-07-11 | [6 empty] | 73600 | 73600 |  | 73600 | 73600
| 8 | 2022-07-0055 | 2022-07-0013 | KGP Travel & Tours | 4 Pax - Travel to Manila-CDO-Manila (Airdare) July 22 to July 29, 2022 Inventory and Disposal of BBS Equipment 1. Emmanuel Cedric Ontong 2. Marlon Marquez 3. Hazel Usita 4. Don Kristian Baclean | [19 empty] | Administrative |  | Small Value Procurement | [7 empty] | 2022-07-12 | [6 empty] | 63032 | 63032 |  | 63032 | 63032
| 9 | 2022-04-0196 | 2022-07-0084 | Jarf Hardware Trading | 1 Lot - Construction Materials for the Repair of DYES-Borongan Perimeter Fence and Septic Tank | [19 empty] | Borongan |  | Small Value Procurement | [7 empty] | 2022-07-12 | [6 empty] | 253154.56 | 253154.56 |  | 251225.76 | 251225.76
| 10 | 2022-06-296 | 2022-07-0086 | TMDEE Enterprises | 3 Sets - Seagate Barracuda 1TB, 3 Modules - Gigabyte Solid State Drive Sata, 2 Sets - Computer Monitor 18.5", 3 Modules - DDR4 RAM 2666MHZ 86GB ADATA | [19 empty] | Virac | [9 empty] | 2022-07-12 | [6 empty] | 34600 | 34600 |  | 34600 | 34600
| 11 | 2022-05-0231B | 2022-07-0087 | Vertical Home Builders Enterprises | 1 Lot - Replacement of Floor Tiles and dilapidated G.I. Sheets at RP1-Cagayan de Oro Transmitter Site | [19 empty] | Cagayan de Oeo |  | Small Value Procurement | [7 empty] | 2022-07-12 | [6 empty] | 25204 | 25204 |  | 25204 | 25204
| 12 | 2022-07-0301 | 2022-07-0088 | Dwinar Computer Center | 2 Units - Wireless Keyboard and Mouse Combo, 2 Units - Gigabit WiFI Router, 2 Units - 5 Meters VGA Cord | [19 empty] | Cagayan de Oeo |  | Small Value Procurement | [7 empty] | 2022-07-12 | [6 empty] | 8590 | 8590 |  | 8590 | 8590
| 13 | 2022-06-0282 | 2022-07-0085 | S1 Technologies, Inc. | 1 Unit - C922 Pro HD Stream Webcam | [19 empty] | Tuguegarao |  | Small Value Procurement | [7 empty] | 2022-07-12 | [6 empty] | 6475 | 6475 |  | 6475 | 6475
| 14 | 2022-06-0276 | 2022-07-0089 | Visionet Computers | 1 Set - Closed Circuit Television (CCTV) including 2TB, Monitor 19”, UPS AVR and labor in installing the CCTV | [19 empty] | Tabuk |  | Small Value Procurement | [7 empty] | 2022-07-14 | [6 empty] | 23647 | 23647 |  | 23647 | 23647
| 15 | 2022-07-0309 | 2022-07-0090 | TMDEE Enterprises | 1 Lot - Materials for the Repair of FM Tower and Replacement of PDX Wire | [19 empty] | Virac |  | Small Value Procurement | [7 empty] | 2022-07-18 | [6 empty] | 13815 | 13815 |  | 13815 | 13815
| 16 | 2022-06-0046 | 2022-07-0012 | My Creative Panda Web Design | 1 Lot - Subscriptions to Web Services Every Month (August 2022 to December 2022) | [19 empty] | Engineering |  | Small Value Procurement | [7 empty] | 2022-07-18 | [6 empty] | 45000 | 45000 |  | 43888.88 | 43888.88
| 17 | 2022-06-0250 | 2022-07-0092 | CBCD Trading | 1 Unit - Console Audio Mixer | [19 empty] | Tawi-Tawi |  | Small Value Procurement | [7 empty] | 2022-07-18 | [6 empty] | 14500 | 14500 |  | 13800 | 13800
| 18 | 2022-06-0250 | 2022-07-0091 | Oscom Trading | 2 Pieces - Microphone | [19 empty] | Tawi-Tawi |  | Small Value Procurement | [7 empty] | 2022-07-18 | [6 empty] | 16000 | 16000 |  | 15700 | 15700
| 19 | 2022-06-0257 | 2022-07-0093 | Halden General Merchandise | 1 Roll - 9501 Belden Wire | [19 empty] | Dagupan |  | Small Value Procurement | [7 empty] | 2022-07-18 | [6 empty] | 15000 | 15000 |  | 13500 | 13500
| 20 | 2022-06-0254 | 2022-07-0094 | JCA Builders | 1 Lot - Labor and Materials for the Repair of Roofing System of DWFB-Laoag | [19 empty] | Laoag |  | Small Value Procurement | [7 empty] | 2022-07-18 | [6 empty] | 910865 | 910865 |  | 902950 | 902950
| 21 | 2022-06-0288 | 2022-07-0099 | Dataview Computer Corp. | 1 Unit - HDMI Cable, 1 Unit - Gigabit Ethernet Switch 8port, 1 Unit - UPS 1KVA | [19 empty] | Network |  | Small Value Procurement | [7 empty] | 2022-07-21 | [6 empty] | 23000 | 23000 |  | 10750 | 10750
| 22 | 2022-06-0277 | 2022-07-0098 | Dataview Computer Corp. | 1 Unit - 43" Smart TV | [19 empty] | Batanes |  | Small Value Procurement | [7 empty] | 2022-07-21 | [6 empty] | 25000 | 25000 |  | 25000 | 25000
| 23 | 2022-06-0287 | 2022-07-0097 | Dataview Computer Corp. | 1 Unit - APC Backups 1400 220 – 240V 6.1A 50/60Hz, 1400VA | [19 empty] | Engineering |  | Small Value Procurement | [7 empty] | 2022-07-21 | [6 empty] | 11500 | 11500 |  | 11495 | 11495
| 24 | 2022-06-0295 | 2022-07-0096 | Dataview Computer Corp. | 1 Unit - MAX Stream Dual Band 4x4 WiFi 5 Router EA8100 | [19 empty] | News Division |  | Small Value Procurement | [7 empty] | 2022-07-21 | [6 empty] | 8100 | 8100 |  | 8000 | 8000
| 25 | 2022-07-0321 | 2022-07-0101 | TMDEE Enterprises | 1 Set - Stavol Automatic Voltage Regulator 5KVA/500 Watts with Time on delay | [19 empty] | Virac |  | Small Value Procurement | [7 empty] | 2022-07-25 | [6 empty] | 17200 | 17200 |  | 17200 | 17200
| 26 | 2022-06-0283 | 2022-07-0100 | JFO Engineering Construction & Consultancy Services | 1 Lot - Materials for the repair of Antenna Tower | [19 empty] | Albay |  | Small Value Procurement | [7 empty] | 2022-07-25 | [6 empty] | 283080 | 283080 |  | 281300 | 281300
| 27 | 2022-07-0328 | 2022-07-0102 | Northquad Trade Empure, Inc. | 1 Unit - Epson Printer | [19 empty] | Laoag |  | Shopping 52.1B | [7 empty] | 2022-07-26 | [6 empty] | 20938 | 20938 |  | 20938 | 20938
| 28 | 2022-03-0084, 2022-03-0072, 2022-02-0048 | 2022-07-0103 | Office Warehouse, Inc. | 5 Units - Electric Typewriter | [19 empty] | Network, Finance, General Services |  | Shopping 52.1B | [7 empty] | 2022-07-26 | [6 empty] | 130000 | 130000 |  | 109500 | 109500
| 29 | 2022-07-0298 | 2022-07-0104 | Halden General Merchandise | 1 Set - Computer Monitor | [19 empty] | DZRM |  | Small Value Procurement | [7 empty] | 2022-07-27 | [6 empty] | 6800 | 6800 |  | 6700 | 6700
| 30 | 2022-07-0315 | 2022-08-0105 | Geomer Airconditioning Works & Services, Inc. | 1 Lot - 2HP Split Type Wall Mounted ACU with Installation Daikin Air-conditioner, Non-Inverter 1 Phase 220V, R410A Refrigerant with Installation & VAT | [19 empty] | Iloilo |  | Small Value Procurement | [7 empty] | 2022-08-02 | [6 empty] | 62000 | 62000 |  | 61040 | 61040
| 31 | 2022-07-0329 | 2022-08-0106 | Octagon Computer Superstore | 2 Units - SWeb Camera Logitech Model C922 Pro HD Stream, 2 Units - USB Hub A4 Tech 4 Port Hub, 2 Units - Tripod Yunteng, 15 Meters - HDMI, 2 Units - 1 Meter Trackbar, 6 Units - 12W LED Cob Track Light White | [19 empty] | Laoag |  | Small Value Procurement | [7 empty] | 2022-08-02 | [6 empty] | 24760 | 24760 |  | 24760 | 24760
| 32 | 2022-05-0031 | 2022-08-0109 | JQD Construction and General Services | 1 Lot - Labor and Materials for the Replacement of Radyo Pliipinas Soged Roofing System | [19 empty] | Sogod |  | Small Value Procurement | [7 empty] | 2022-08-05 | [6 empty] | 963265.55 | 963265.55 |  | 940000 | 940000
| 33 | 2022-03-0118, 2022-07-0300, 2022-07-0305 |  | Aukchoi Consumer Goods Trading | 6 Units - XS-1 Dynamic Wired Vocal Microphone, 3 Units - Microphone Stand, Tabletop, 1 Unit - Professional Headphone MDR 7506 | [19 empty] | Palawan, Lucena, |  | Small Value Procurement | [7 empty] | 2022-08-08 | [6 empty] | 72500 | 72500 |  | 72222 | 72222
| 34 | 2022-07-0314, 2022-07-0297 | 2022-08-0110 | DAVTECH Marketing | 1 Unit - Executive Table, 3 Units - Highback Executive Chair, 5 Units - Ergonomic Clerical Table | [19 empty] | Batanes, Research Division |  | Small Value Procurement | [7 empty] | 2022-08-05 | [6 empty] | 67000 | 67000 |  | 58500 | 58500
| 35 | 2022-06-0289 | 2022-08-0111 | CBCD Trading | 6 Pieces - Turnbuckle ¾” (US Type) Jaw and Jaw | [19 empty] | Tuguegarao |  | Small Value Procurement | [7 empty] | 2022-08-08 | [6 empty] | 12000 | 12000 |  | 9300 | 9300
| 36 | 2022-07-0304 | 2022-08-0107 | Octagon Computer Superstore | 1 Lot - For the Repair of Flooring Tiles of Clinic's Comfort Room | [19 empty] | Engineering |  | Small Value Procurement | [7 empty] | 2022-08-05 | [6 empty] | 14250 | 14250 |  | 14030 | 14030
| 37 | 2022-08-0316 | 2022-08-0113 | CBCD Trading | 1 Unit - Flange Type 7/8 RF Connector, 1 Unit - N-Type to 7/8 RF ½ Male Connector, 1 Unit - 7/16 DIN Type Manle Connector for 7/8 cable | [19 empty] | Baguio |  | Small Value Procurement | [7 empty] | 2022-08-11 | [6 empty] | 27500 | 27500 |  | 27100 | 27100
| 38 | 2022-06-0244 | 2022-08-0108 | JCQ Hardware and Construction Supply | 1 Lot - Materials for the Repair of Transmitter Building of DYMR-Cebu | [19 empty] | Cebu |  | Small Value Procurement | [7 empty] | 2022-08-05 | [6 empty] | 295744.99 | 295744.99 |  | 294388.2 | 294388.2
| 39 | 2022-07-0299 | 2022-08-0115 | Visionet Computers | 1 Unit - Computer Monitor Panel Size at least 23.8” (60cm) Panel Resolution: 1920 x 1080 (Full HD) | [19 empty] | Tabuk |  | Small Value Procurement | [7 empty] | 2022-08-26 | [6 empty] | 9500 | 9500 |  | 9500 | 9500
| 40 | 2022-08-0056 | 2022-09-0001 | Frigid Zone Auto Aircon | 1 Lot - Repair of Isuzu Crosswind ACU CN 1115 | [19 empty] | General Services |  | Small Value Procurement | [7 empty] | 2022-08-30 | [6 empty] | 8960 | 8960 |  | 8960 | 8960
| 41 | 2022-08-0334 | 2022-08-0114 | Dataview Computer Corp. | 1 Unit - Digital Single Lens Reflex Camera, Canon EOS 3000D (W) with 18-55 DC III | [19 empty] | Laoag |  | Small Value Procurement | [7 empty] | 2022-08-30 | [6 empty] | 27000 | 27000 |  | 27000 | 27000
| 42 | 2022-08-0050 | 2022-09-0015 | Composite Technology, Inc. | 1 Lot - Diagnostic Check-up and Troubleshooting of Harris DX10 Transmitter at Kalinga including Travel Expenses VAT Inclusive | [19 empty] | Tabuk |  | Direct Contracting | [7 empty] | 2022-09-05 | [6 empty] | 155680 | 155680 |  | 155680 | 155680
| 43 | 2022-08-0351 | 2022-09-0116 | Dataview Computer Corp. | 1 Unit - AVR 5KVA Digital Display Servo | [19 empty] | Network |  | Small Value Procurement | [7 empty] | 2022-09-02 | [6 empty] | 16000 | 16000 |  | 14500 | 14500
| 44 | 2022-07-0330C | 2022-09-0117 | Qualty Appliance Plaza, Inc. | 1 Unit - Airconditioner Split Type 2.5HP inverter, 1 Unit - Television Set, Smart 43" Devant | [19 empty] | Gingoog |  | Small Value Procurement | [7 empty] | 2022-09-07 | [6 empty] | 69000 | 69000 |  | 69000 | 69000
| 45 | 2022-09-0082 | 2022-09-0021 | KGP Travel & Tours | 1 Lot - Airfare Manila-Butuan-Davao-Manila 1) Judith Traballo, 2) Ma. Eileen Eligado, 3) Sharmaine Eligado, 4) Loumuel Marissa Laytan | [19 empty] | Property |  | Small Value Procurement | [7 empty] | 2022-09-06 | [6 empty] | 71184 | 71184 |  | 71184 | 71184
| 46 | 2022-02-0041 | 2022-09-0118 | The First Family Appliance Circle Corp. | 1 Unit - , 1 Unit - Airconfitioner 5-Tonner Split Type, Floor Mounted, Inverter Koppel Brand, 1 Unit - Airconfitioner, 2HP Window Type | [19 empty] | Cebu |  | Small Value Procurement | [7 empty] | 2022-09-08 | [6 empty] | 182990 | 182990 |  | 182990 | 182990
| 47 | 2022-09-0119 | 2022-06-0267 | 90 Degrees North, Inc. | 1 Lot -Supply and Delivery of Information System Strategic Plan (ISSP) Various Broadcast Equipment (6 Sets - 8 Channel Digital Audio Mixing Console)(Bid No. 002-2022) | [19 empty] | Engineering |  | Competitve Bidding | 2022-08-03 | 2022-08-08 | 2022-08-16 | 2022-08-30 | 2022-08-30 | 2022-09-05 | 2022-09-06 |  | 2022-09-21 | 2022-10-18 | 2022-10-18 |  |  | GAA | 3288000 | 3288000 |  | 3250000 | 3250000 |  | Mr. Crisanto Ftianeza, Secretary-General of Philippine Chamber of Commerce and Industry, Engr. Vitgilio S. Santos, President of Procurement Watch and Mr. Engardo L. Rivera, State Auditor III/Audit Team Leader in BBS of Commission on Audit | 2022-08-16 | 2022-08-30 | 2022-08-30 | 2022-09-05 | 2022-09-06
| 48 | 2022-06-0268 | 2022-06-0268 | 90 Degrees North, Inc. | 1 Lot - Supply and Delivery of Information System Strategic Plan (ISSP) Various Broadcast Equipment (10 Sets - IP Codec Studio Unit & 19 Sets - IP Codec Relay Site) (Bid No. 003-2022) | [19 empty] | Engineering |  | Competitve Bidding | 2022-08-03 | 2022-08-08 | 2022-08-16 | 2022-08-30 | 2022-08-30 | 2022-09-05 | 2022-09-06 |  | 2022-09-21 | 2022-10-18 | 2022-10-18 |  |  | GAA | 6830000 | 6830000 |  | 6800000 | 6800000 |  | Mr. Crisanto Ftianeza, Secretary-General of Philippine Chamber of Commerce and Industry, Engr. Vitgilio S. Santos, President of Procurement Watch and Mr. Engardo L. Rivera, State Auditor III/Audit Team Leader in BBS of Commission on Audit | 2022-08-16 | 2022-08-30 | 2022-08-30 | 2022-09-05 | 2022-09-06
| 49 | 2022-06-0261 2022-06-0233 |  | 90 Degrees North, Inc. | 1 Lot - Supply and Delivery of Information System Strategic Plan (ISSP) Various ICT Equipment and Accessories | [19 empty] | Engineering |  | Competitve Bidding | 2022-08-03 | 2022-08-08 | 2022-08-16 | 2022-08-31 | 2022-08-31 | 2022-09-05 | 2022-09-06 |  | 2022-09-21 | 2022-10-18 | 2022-10-18 |  |  | GAA | 4950100 | 4950100 |  | 4950000 | 4950000 |  | Mr. Crisanto Ftianeza, Secretary-General of Philippine Chamber of Commerce and Industry, Engr. Vitgilio S. Santos, President of Procurement Watch and Mr. Engardo L. Rivera, State Auditor III/Audit Team Leader in BBS of Commission on Audit | 2022-08-16 | 2022-08-31 | 2022-08-31 | 2022-09-05 | 2022-09-06
| 50 | 2022-06-0279 & 2022-06-0290 |  | Broadtech Corporation | 1 Lot - Supply and Delivery of Information System Strategic Plan (ISSP) Antenna Satellite System and Sateillite Phonr, both with One (1) Year Subscription | [19 empty] | Engineering |  | Competitve Bidding | 2022-08-03 | 2022-08-08 | 2022-08-17 | 2022-08-31 | 2022-08-31 | 2022-09-05 | 2022-09-14 |  | 2022-09-30 | 2022-10-20 | 20 ocr 22 |  |  | GAA | 2965000 | 2965000 |  | 2960000 | 2960000 |  | Mr. Crisanto Ftianeza, Secretary-General of Philippine Chamber of Commerce and Industry, Engr. Vitgilio S. Santos, President of Procurement Watch and Mr. Engardo L. Rivera, State Auditor III/Audit Team Leader in BBS of Commission on Audit | 2022-08-17 | 2022-08-31 | 2022-08-31 | 2022-09-05 | 2022-09-14
| 51 | 2022-05-0201 |  | Comparts Computer Sales | 1 Lot - Supply and Delivery of Information System Strategic Plan (ISSP) Biometric System with Web Based Software | [19 empty] | Administrative |  | Competitve Bidding | 2022-08-03 | 2022-08-08 | 2022-08-17 | 2022-09-01 | 2022-09-01 | 2022-09-05 | 2022-09-08 |  | 2022-09-21 | 2022-10-14 | 2022-10-14 |  |  | GAA | 800000 | 800000 |  | 574320 | 574320 |  | Mr. Crisanto Ftianeza, Secretary-General of Philippine Chamber of Commerce and Industry, Engr. Vitgilio S. Santos, President of Procurement Watch and Mr. Engardo L. Rivera, State Auditor III/Audit Team Leader in BBS of Commission on Audit | 2022-08-17 | 2022-09-01 | 2022-09-01 | 2022-09-05 | 2022-09-08
| 52 | 2022-08-0368 | 2022-09-0120 | Dataview Computer Corp. | 2 Units - APC BX1600MI-MS UPS | [19 empty] | Engineering |  | Small Value Procurement | [7 empty] | 2022-09-08 | [6 empty] | 32400 | 32400 |  | 31000 | 31000
| 53 | 2022-08-0352 | 2022-09-0126 | Dataview Computer Corp. | 1 Unit - HP Smart Tank 500 (3-in-1) | [19 empty] | Research |  | Small Value Procurement | [7 empty] | 2022-09-12 | [6 empty] | 12000 | 12000 |  | 11495 | 11495
| 54 | 2022-08-0352 | 2022-09-0125 | Halden General Merchandise | 2 Units - 55” Smart TV | [19 empty] | Research |  | Small Value Procurement | [7 empty] | 2022-09-12 | [6 empty] | 50000 | 50000 |  | 47000 | 47000
| 55 | 2022-08-0337 | 2022-09-0122 | Mostaco Marketing | 1 Lot - Various Office Supplies | [19 empty] | Property & Supply |  | Shopping 52.1B | [7 empty] | 2022-09-09 | [6 empty] | 412000 | 412000 |  | 303500 | 303500
| 56 | 2022-08-0335, 2022-08-0332 | 2022-09-0121 | DAVTECH Marketing | 2 Units - 3 Layer Lateral Filing Cabinet, 1 Unit - 2 Layer Lateral Filing Cabinet, 15 Pieces - Hiigh Back Executive Chair | [19 empty] | Finance and Director's Office |  | Small Value Procurement | [7 empty] | 2022-09-09 | [6 empty] | 161500 | 161500 |  | 101000 | 101000
| 57 | 2022-08-0371E | 2022-09-0124 | Metro Ilocos Appliance, Inc. | 1 Unit - Window Type AirconditionerWindow Type Airconditioner, 1HP LG Brand | [19 empty] | Laoag |  | Small Value Procurement | [7 empty] | 2022-09-14 | [6 empty] | 19800 | 19800 |  | 19800 | 19800
| 58 | 2022-08-0371F | 2022-09-0123 | Triple R & M Fire Extinguisher Trading | 3 Pieces - Fire Extinguisher 20lbs - Refill | [19 empty] | Gingoog |  | Small Value Procurement | [7 empty] | 2022-09-15 | [6 empty] | 10800 | 10800 |  | 10800 | 10800
| 59 | 2022-08-0363 | 2022-09-0127 | Oscom Trading | 5 Gallons - Shelby Rubberized Liquid Waterproofing | [19 empty] | Engineering |  | Small Value Procurement | [7 empty] | 2022-09-15 | [6 empty] | 10000 | 10000 |  | 8800 | 8800
| 60 | 2022-08-0349 | 2022-09-0128 | Halden General Merchandise | 10 Pieces - Logitech H349 USB Computer Headset, 2 Pieces - Sony-ICF-306 Portable AM/FM Radio, 10 Pieces - Mouse Logitech M90 | [19 empty] | News Division |  | Small Value Procurement | [7 empty] | 2022-09-15 | [6 empty] | 19000 | 19000 |  | 18140 | 18140
| 61 | 2022-06-0280 | 2022-09-0130 | Oscom Trading | 1 Unit - Split Type Airconditioning Unit 1HP | [19 empty] | Borongan |  | Small Value Procurement | [7 empty] | 2022-09-22 | [6 empty] | 25000 | 25000 |  | 24000 | 24000
| 62 | 2022-08-0347 | 2022-09-0129 | Oscom Trading | 6 Units - Renwable Fuse 400 Amperes, Brand New | [19 empty] | Marulas |  | Small Value Procurement | [7 empty] | 2022-09-27 | [6 empty] | 22200 | 22200 |  | 21000 | 21000
| 63 | 2022-08-0336 | 2022-09-0131 | Oscom Trading | 1 Unit - Microphone Boom, 1 Unit - Dynamic Microphone, 1 Unit - Headphone HD 300 Pro, 1 Unit - FOSI Audio 4 Channel Headphone Amplifier Stereo AMP PH04 Ultra Compact Portable Headphone Splitter | [19 empty] | Laoag |  | Small Value Procurement | [7 empty] | 2022-09-27 | [6 empty] | 38333 | 38333 |  | 36550 | 36550
| 64 | 2022-09-0394 | 2022-09-0135 | Mr. A All-in Marketing | 1 Unit- Precision 1000VA / 500 Watts Uninterruptible Power Supply, 1 Unit - 2SM Battery Motolite Maintenance Free | [19 empty] | Virac |  | Small Value Procurement | [7 empty] | 2022-09-27 | [6 empty] | 26100 | 26100 |  | 26100 | 26100
| 65 | 2022-03-0015E | 2022-09-0134 | Dynamic Hardware and Construction Supply | 1 Unit - Grass Cutter | [19 empty] | Butuan |  | Small Value Procurement | [7 empty] | 2022-09-27 | [6 empty] | 18500 | 18500 |  | 18500 | 18500
| 66 | 2022-09-0381 | 2022-09-0133 | Aljeann | 1 Piece - Radiator Assembly | [19 empty] | Agoo |  | Small Value Procurement | [7 empty] | 2022-09-29 | [6 empty] | 7800 | 7800 |  | 7800 | 7800
| 67 | 2022-08-0064A | 2022-09-0017 | URE Car Aircon Tire & Vul. Shop | 1 Unit - Overhauling of the Aircon Unit of the Service Vehicle of RP-Baguio | [19 empty] | Baguio |  | Small Value Procurement | [7 empty] | 2022-09-29 | [6 empty] | 12180 | 12180 |  | 12180 | 12180
| 68 | 2022-08-0371N | 2022-09-0137 | Mid-Town Computers and Services | 1 Lot - Various Computer Accessories | [19 empty] | Butuan |  | Small Value Procurement | [7 empty] | 2022-09-29 | [6 empty] | 48032 | 48032 |  | 48032 | 48032
| 69 | 2022-09-0078 | 2022-09-0018 | R. Laurenciana Industrial & Electrical | 1 Unit - Labor and Materials cost of the rewinding/repair of burned-out transformer | [19 empty] | Albay |  | Small Value Procurement | [7 empty] | 2022-09-20 | [6 empty] | 6500 | 6500 |  | 6500 | 6500
| 70 | 2022-09-0392 | 2022-09-0136 | Makotek Computer Sales, Inc. | 1 Lot - Live Video Streaming Peripherals | [19 empty] | CDO |  | Small Value Procurement | [7 empty] | 2022-09-29 | [6 empty] | 6325 | 6325 |  | 6325 | 6325
| 71 | 2022-08-0371D | 2022-09-0138 | CBCD Trading | 1 Unit - Microphone | [19 empty] | RP-Worldwide |  | Small Value Procurement | [7 empty] | 2022-09-29 | [6 empty] | 8000 | 8000 |  | 7500 | 7500
| 72 | 2022-09-0382 | 2022-09-0139 | Office Warehouse, Inc. | 1 Unit - Printer Scanner Colored | [19 empty] | Administrative |  | Shopping 52.1B | [7 empty] | 2022-09-29 | [6 empty] | 15000 | 15000 |  | 12950 | 12950
| 73 | 2022-09-0081 | 2022-09-0019 | KGP Travel & Tours | 1 Lot - September 17-22, 2022 (AIBD Conference and Associated Meetings) Dep. Dir. Joan Marie Domingo | [19 empty] | Director's Office |  | Small Value Procurement | [7 empty] | 2022-09-29 | [6 empty] | 141990 | 141990 |  | 141990 | 141990
| 74 | 2022-09-0076 |  | Pearlmont Hotel | 1 Lot - Venue for the BBS-GAD Gender Sensitivity Training and Workshop in Cagayan De Oro City on October 5-8, 2022 | [19 empty] | GAD |  | Small Value Procurement | [7 empty] | 2022-09-29 | [6 empty] | 112000 | 112000 |  | 111994 | 111994
| 75 | 2022-08-0058 | 2022-09-0020 | Philippine Global Communications, Inc. | 1 Lot - 50 Mbps Leased Line Monthly Subscription of Dedicated Enterprise Internet Plan with Unlimited Data (Period: October to December 2922) | [19 empty] | Engineering |  | Small Value Procurement | [7 empty] | 2022-09-30 | [6 empty] | 153000 | 153000 |  | 105780 | 105780
| 76 | 2022-07-0330D | 2022-09-0143 | Metro Ilocos Appliance, Inc. | 1 Unit - Window Type Airconditioner 1HP, 1 Unit - Window Type Airconditioner 2HP | [19 empty] | Laoag |  | Small Value Procurement | [7 empty] | 2022-09-30 | [6 empty] | 51600 | 51600 |  | 51600 | 51600
| 77 | 2022-08-0371C | 2022-10-0145 | Halden General Merchandise | 1 Unit - 100A, MCCB, 3 Phase 3 Pole Industrial Circuit Breaker 100AF 10KAIC 400V (Schneider) with NEMA 3 Enclosure | [19 empty] | Lucena |  | Small Value Procurement | [7 empty] | 2022-10-05 | [6 empty] | 7000 | 7000 |  | 6920 | 6920
| 78 | 2022-08-0371H | 2022-10-0146 | Timog Tirehaus Corporation | 1 Unit - 2SM Battery Maintenance Free, 1 Unit - Battery Trackmaster 4D/N150 | [19 empty] | Calbayog |  | Small Value Procurement | [7 empty] | 2022-10-06 | [6 empty] | 24000 | 24000 |  | 23000 | 23000
| 79 | 2022-09-0069 | 2022-10-0022 | Frigid Zone Auto Aircon Specialist, Co. | 1 Unit - Airconditioning Unit Repair of Toyota Avanza P5V602 | [19 empty] | General Services |  | Small Value Procurement | [7 empty] | 2022-10-05 | [6 empty] | 30240 | 30240 |  | 30240 | 30240
| 80 | 2022-09-0088B | 2022-10-0026 | KGP Travel & Tours | 4 Pax - AIRFARE Flight Details Manila-Zamboanga Zamboanga-Tawi-Tawi-Zamboanga Zamboanga-Jolo-Zamboanga Zamboanga-Manila Passenger: 1) Emmanuela Cedric Ontong 2) Marlon Marquez 3) Hazel Usita 4) Don Kristian Baclean Service Fee and VAT | [19 empty] | Property & Supply |  | Small Value Procurement | [7 empty] | 2022-10-08 | [6 empty] | 200000 | 200000 |  | 199472 | 199472
| 81 | 2022-09-0088C | 2022-10-0027 | KGP Travel & Tours | 1 Pax - AIRFARE Flight Details Manila-Zamboanga Zamboanga-Tawi-Tawi-Zamboanga Zamboanga-Manila Passenger: 1. Edgardo Rivera | [19 empty] | COA |  | Small Value Procurement | [7 empty] | 2022-10-08 | [6 empty] | 40000 | 40000 |  | 38765 | 38765
| 82 | 2022-09-0088 | 2022-10-0024 | KGP Travel & Tours | 5 Pax - AIRFARE Manila-Iloilo Iloilo-Cebu Cebu-Palawan Palawan-Manila Flight Details: 1. Josephine Juaneza 2. Carmella Castillo 3. Marlon Marquez 4. Noriel Santos 5. Leticia Reyes Service Fee and VAT | [19 empty] | Property Section |  | Small Value Procurement | [7 empty] | 2022-10-10 | [6 empty] | 165000 | 165000 |  | 163435 | 163435
| 83 | 2022-09-0086 | 2022-10-0023 | KGP Travel & Tours | 3 Pax - AIRFARE Flight Details: Manila-Iloilo-Manila Passengers: 1. Sheena Tabil 2. Edna de Leon AIRFARE Flight Details: Manila-Puerto Princesa-Manila Passenger: 1. Edgardo Rivera Leticia Reyes Service Fee and VAT | [19 empty] | COA |  | Small Value Procurement | [7 empty] | 2022-10-10 | [6 empty] | 49000 | 49000 |  | 48236 | 48236
| 84 | 2022-09-0087 | 2022-10-0025 | KGP Travel & Tours | 2 Pax - AIRFARE Flight Details: Manila-Palawan-Manila Passengers: 1. Rizal Giovanni P. Aportadera, Jr. 2. Joan Marie Domingo 3 Pax - HOTEL ACCOMMODATION 1. Rizal Giovanni P. Aportadera, Jr. 2. Joan Marie Domingo 3. Edgardo Rivera Service Fee and VAT | [19 empty] | Director's Office |  | Small Value Procurement | [7 empty] | 2022-10-10 | [6 empty] | 162000 | 162000 |  | 157848 | 157848
| 85 | 2022-09-0380 | 2022-10-0147 | Dataview Computer Corp. | 2 Units - SSD SN 770 NVME M.2, 250GB Western Digital | [19 empty] | Engineering |  | Small Value Procurement | [7 empty] | 12 ocr 22 | [6 empty] | 7000 | 7000 |  | 6990 | 6990
| 86 | 2022-09-0372 | 2022-10-0148 | Oscom Trading | 25 Pieces - Water Hose, Clear, PVC, Fiber, Polyester Thread, 1-inch in Diameter, 15 Pieces - -Hole Metal C-Clamp for 1-inch Diameter Hose | [19 empty] | General Services |  | Small Value Procurement | [7 empty] | 2022-10-12 | [6 empty] | 6650 | 6650 |  | 6350 | 6350
| 87 | 2022-08-0371J | 2022-10-0151 | DDSI, Inc. | 641 Meters - Stranded Bare Copper Wire AGW 6 7 Stranded 14mm, 55 Pieces - Copper Cable Clamp AGW 6 | [19 empty] | Davao |  | Small Value Procurement | [7 empty] | 2022-10-12 | [6 empty] | 70822 | 70822 |  | 70822 | 70822
| 88 | 2022-08-0371L, 2022-08-0371K, 2022-09-0399 & 2022-10-0404 | 2022-10-0149 | DAVTECH Marketing | 4 Units - Chair, Mid-Back Office Chair MC 412 Black, 10 Units - Chsir, Office Chair JS-555, 7 Units - Chair, High BacK Executive Chair CNH168 Black, 1 Unit - Mobile Pedestal Cabinet 3-Layer | [19 empty] | (Engineering, RP1-Manila, News, Research) |  | Small Value Procurement | [7 empty] | 2022-10-14 | [6 empty] | 119000 | 119000 |  | 85450 | 85450
| 89 | 2022-09-0403B, 2022-09-0403C 2022-09-0403D, 2022-09-0395 & 2022-09-0397 | 2022-10-0150 | Vistaaire Builders and Airconditioning Sales and Services | 1 Set - ,Multi-Spit Inverter Aircon Unit 2 HP Wall Mounted Indoor Unit. 1HP Wall Mounted Indoor Unit. 3.3HP Outdoor Unit Brand: Koppel 2 Sets - 3TR Split Type Floor Mounted Non-Inverter Aircon Unit Brand: Koppel, 1 Unit - Air conditioner 2HP, Inverter Window Type Brand: Carrier, 2 Units - Window Type Brand: Carrier | [19 empty] | (Engineering, Research) |  | Small Value Procurement | [7 empty] | 2022-10-14 | [6 empty] | 512000 | 512000 |  | 490000 | 490000
| 90 | 2022-06-0293 | 2022-10-0152 | CBCD Trading | 1 Set - 75 Feet ½ Transmitter Cable w/ end to end N-Type RF Connectors | [19 empty] | Naga |  | Small Value Procurement | [7 empty] | 2022-10-20 | [6 empty] | 21500 | 21500 |  | 21300 | 21300
| 91 | 2922-09-0085 | 2022-10-0028 | Frigid Zone Auto Aircon Specialist, Co. | 1 Unit - Repair of Airconditioning Unit of Hyundai Grandia Starex KOU 405 | [19 empty] | General Services |  | Small Value Procurement | [7 empty] | 2022-10-21 | [6 empty] | 38640 | 38640 |  | 38640 | 38640
| 92 | 2022-09-0080 |  | Broadtech Corporation | 1 Lot - To Repair the Armstrong 1kW AM Transmitter of DXRG-Gingoog | [19 empty] | Gingoog |  | Direct Contracting | [7 empty] | 2022-10-26 | [6 empty] | 70000 | 70000 |  | 70000 | 70000
| 93 | 2022-10-0436 | 2022-10-0153 | Mark Nelson Auto Supply | 1 Unit - 2SM Motolite Gold Battery | [19 empty] | Tuguegarao |  | Small Value Procurement | [7 empty] | 2022-10-28 | [6 empty] | 6000 | 6000 |  | 6000 | 6000
| 94 | 2022-10-0419 | 2022-11-0154 | CBCD Trading | 2 Units - 3SM MF Battery | [19 empty] | Marulas |  | Small Value Procurement | [7 empty] | 2022-11-02 | [6 empty] | 12000 | 12000 |  | 12000 | 12000
| 95 | 2022-10-0092 |  | EGI Albergo, Inc. | 1 Lot - Venue for the BBS-GAD Gender Sensitivity Training and Workshop in Baguio City on November 7-12, 2022 | [19 empty] | GAD |  | Small Value Procurement | [7 empty] | 2022-11-03 | [6 empty] | 260030 | 260030 |  | 255000 | 255000
| 96 | 2022-10-0414 | 2022-11-0155 | MRV Refrigeration and Airconditioning Parts | 1 CYL - Freon R-22 (22.7kgs) | [19 empty] | Engineering |  | Small Value Procurement | [7 empty] | 2022-11-03 | [6 empty] | 10500 | 10500 |  | 10500 | 10500
| 97 | 2022-10-0413 | 2022-11-0158 | Halden General Merchandise | 1 Unit - Green Fire Extinguisher HCFC-123 20lbs. Brand New, 5-years warranty, 1 Unit - Red Fire Extinguisher Dry Chemical Brand New, 1-year warranty | [19 empty] | Malolos |  | Small Value Procurement | [7 empty] | 2022-11-04 | [6 empty] | 18000 | 18000 |  | 15900 | 15900
| 98 | 2022-09-0388 | 2022-11-0157 | Willy and Sons Corporation | 1 Unit - Airconditioner Split Type 1.5HP with Installation, 2 Units - Airconditioner Window Type 2HP | [19 empty] | Borongan |  | Small Value Procurement | [7 empty] | 2022-11-04 | [6 empty] | 119308 | 119308 |  | 118308 | 118308
| 99 | 2022-10-0433 | 2022-11-0159 | Kellson Corporation | 150 Gallons - Isopropyl Alcohol 3.7 liters/gallons, 200 Boxes - Face Mask 3 ply | [19 empty] | Administrative |  | Shopping 52.1B | [7 empty] | 2022-11-07 | [6 empty] | 91500 | 91500 |  | 71500 | 71500
| 100 | 2022-10-0413 | 2022-11-0156 | Dataview Computer Corp. | 1 Unit - Brother DCP-T720DW All-in-One Printer | [19 empty] | Palawan |  | Shopping 52.1B | [7 empty] | 2022-11-04 | [6 empty] | 13995 | 13995 |  | 13995 | 13995
| 101 | 2022-10-0089 | 2022-11-0031 | Frigid Zone Auto Aircon Specialist, Co. | 1 Unit - Repair of Airconditioning Unit of Tpyota Avanza P5V564 | [19 empty] | General Services |  | Small Value Procurement | [7 empty] | 2022-11-09 | [6 empty] | 30240 | 30240 |  | 30240 | 30240
| 102 | 2022-11-0440 | 2022-11-0161 | Timog Tirehaus Corporation | 8 Pieces - Tire (185/70 R-14) | [19 empty] | General Services |  | Small Value Procurement | [7 empty] | 2022-11-23 | [6 empty] | 40000 | 40000 |  | 36000 | 36000
| 103 | 2022-11-0448 | 2022-11-0162 | Dataview Computer Corp. | 2 Units - C922 PRO Web Camera, 2 Units - 4-Port USB Hub, 2 Units - Tripod HDMI Cable, 16 Meters - 6 Units - 1 Meter Track Bar. 2 Units - 12W LED COB Track Light White | [19 empty] | Laoag |  | Small Value Procurement | [7 empty] | 2022-11-25 | [6 empty] | 24760 | 24760 |  | 23800 | 23800
| 104 | 2022-11-0458 | 2022-11-0163 | Dataview Computer Corp. | 3 Pieces - Kingston NV1 500GB M.2 2280 NVMe PCIe SSD (SNVS/500G) | [19 empty] | News Division |  | Small Value Procurement | [7 empty] | 2022-11-25 | [6 empty] | 8997 | 8997 |  | 8997 | 8997
| 105 | 2022-09-0390 | 2022-11-0164 | CBCD Trading | 1 Unit - 12 Channel Professional Mixer, BT-1200 with Bluetooth Connectivity | [19 empty] | Baguio |  | Small Value Procurement | [7 empty] | 2022-12-29 | [6 empty] | 16000 | 16000 |  | 13800 | 13800
| 106 | 2022-10-0437 |  | 168 Security, Inc. | 1 Lot - Contract for the Provision of Security Agency Services for twelve (12) months | [19 empty] | Administrative | Yes | Competitve Bidding | 2022-10-27 | 2022-11-07 | 2022-11-15 | 2022-11-28 | 2022-11-28 | 2022-11-29 | 2022-12-02 | 2022-12-02 | 2022-12-15 | 2022-12-23 | 2022-10-23 |  |  | GAA | 25775350 | 25775350 |  | 25729173.42 | 25729173.42 |  | Mr. Crisanto Ftianeza, Secretary-General of Philippine Chamber of Commerce and Industry, Engr. Vitgilio S. Santos, President of Procurement Watch and Mr. Engardo L. Rivera, State Auditor III/Audit Team Leader in BBS of Commission on Audit | 2022-11-15 | 2022-11-28 | 2022-11-28 | 2022-11-29 | 2022-12-02
| 107 | 2022-11-0441 | 2022-12-0165 | Zhujar Manufacturing, Inc. | 478 Pieces - Gender and Development (GAD) Advocacy Vest for the 18-day Campaign to End Violence Againts Women (VAW) | [19 empty] | GAD |  | Small Value Procurement | [7 empty] | 2022-12-02 | [6 empty] | 717000 | 717000 |  | 282020 | 282020
| 108 | 2022-10-0411 | 2022-12-0167 | JMS IT Consultancy | 1 Unit - Automated Payroll System | [19 empty] | Enngineering |  | Small Value Procurement | [7 empty] | 2022-12-23 | [6 empty] | 76000 | 76000 |  | 76000 | 76000
| 109 | 2022-11-0465 | 2022-12-0166 | CAC OC Cool Ref and Aircon Repair Services | 2 Units - 2.0 Window Type Air Conditioner (WCARH019EC), 2 Units - Split Type Non Inverter | [19 empty] | Lucena |  | Small Value Procurement | [7 empty] | 2022-12-23 | [6 empty] | 175800 | 175800 |  | 175800 | 175800
| 110 | 2022-12-0106 | 2022-12-0033 | Data Images Plus Automation Phils, Inc. | 1 Lot - Lease of eight (8) units Multi-Functional Photocopying Machine | [19 empty] | Finance |  | Small Value Procurement | [7 empty] | 2022-12-23 | [6 empty] | 345600 | 345600 |  | 235200 | 235200
| 111 | 2022-11-0450 | 2022-12-0168 | Clearshot Builders, OPC | 359 Pieces - Tiles 30 x 30 White, 2 Bags - Tile Grout White, 30 Bags - Finishing Sand, 5 Bags - Cement | [19 empty] | General Services |  | Small Value Procurement | [7 empty] | 2022-12-23 | [6 empty] | 85400 | 85400 |  | 46504.8 | 46504.8
| 112 |  | 2922-11-0104 | Oiny Kapangpangan | 1 Lot - Meals for the BBS-GAD Gender Equality and Women Empowerment (GEWE) and GAD Year-End Assessment on December 21, 2022 | [19 empty] | GAD |  | Small Value Procurement | [7 empty] | 2022-12-16 | [6 empty] | 180000 | 180000 |  | 180000 | 180000
Total Alloted Budget of Procurement Activities | [41 empty] | 54175184.1
Total Contract Price of Procurement Actitvites Conducted | [44 empty] | 52728004.06
Total Savings (Total Alloted Budget - Total Contract Price) | [41 empty] | 1447180.04
0N-GOING PROCUREMENT ACTIVITIES
0
0
0
0
Total Alloted Budget of On-going Procurement Activities | [41 empty] | 0
[25 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
[25 empty] | RODNEY O. VILLANUEVA | [10 empty] | JOAN MARIE S. DOMINGO | [10 empty] | RIZAL GIOVANNI P. APORTADERA, JR.
[25 empty] | BAC Secretariat Head | [10 empty] | Director III / BAC Chairperson | [10 empty] | Director IV / Head of the Procuring Entity

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement