## pmr
[6 empty] | ANNEX A | [18 empty] | ANNEX B
[6 empty] | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | Bureau of Broadcast Services Procurement Monitoring Report as of June 30, 2023
Code (PAP) |  |  |  |  | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
[8 empty] | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
1 | 1 | 2023-01-0002 | 2023-01-0002 | CFS Creative Training and Management | 1 Lot - Resource Speaker for PBS-BBS Execomm and GAD Strategic Planning on January 18-20, 2023 | [19 empty] | GAD |  | Small Value Procurement | [7 empty] | 2023-01-16 | 2023-01-16 | [5 empty] | 49000 | 49000 |  | 49000 | 49000
2 | 2 | 2023-01-0004 | 2023-01-0001 | MNL Essentials | 1 Lot - Giveaways for PBS-BBS Execomm & GAD Strategic Planning (65 Pieces - Notebook & 65 Pieces - Canvass Bags) | [19 empty] | GAD |  | Small Value Procurement | [7 empty] | 2023-01-16 | 2023-01-16 | [5 empty] | 8775 | 8775 |  | 8775 | 8775
3 | 3 | 2022-07-0330G | 2023-01-0002 | Dataview Computer Corporation | 5 Units - Crucial BX500 240GB SSD | [19 empty] | RP1-Manila |  | Small Value Procurement | [7 empty] | 2023-01-19 | 2023-01-19 | [5 empty] | 10000 | 10000 |  | 9975 | 9975
4 | 4 | 2022-10-0438D | 2023-01-0003 | Makotek Computer Sales, Inc. | 2 Pieces - 8GB DDR4 Memory, 2 Set - Keyboard & Mouse USB,. 1 Piece - Tripod | [19 empty] | RP-Cagayan de Oro |  | Small Value Procurement | [7 empty] | 2023-01-20 | 2023-01-20 | [5 empty] | 6305 | 6305 |  | 6305 | 6305
5 | 5 | 2023-01-0018 | 2023-01-0005 | Dataview Computer Corporation | 2 Rolls - Belden Cat5e UTP Cable (305m/roll), 1 Box - RJ45 Connector (1 Box/100 Pieces) | [19 empty] | Network |  | Small Value Procurement | [7 empty] | 2023-01-24 | 2023-01-24 | [5 empty] | 20400 | 20400 |  | 19500 | 19500
6 | 6 | 2022-10-0438D | 2023-01-0004 | Gameiun Technology Computer Trading | 1 Unit - 8GB DDR3 Memory. 1 Unit - Computer Monitor 24” FHD | [19 empty] | RP-Cagayan de Oro |  | Small Value Procurement | [7 empty] | 2023-01-20 | 2023-01-20 | [5 empty] | 9004 | 9004 |  | 8385 | 8385
7 | 7 | 2023-01-0027 | 2023-02-0009 | Edmyles Engine Parts & General Merchandise | 1 Piece - CG411 2 Stroke Grass Cutter | [19 empty] | RP-Agoo |  | Small Value Procurement | [7 empty] | 2023-02-02 | 2023-02-02 | [5 empty] | 5700 | 5700 |  | 5700 | 5700
8 | 8 | 2023-01-0006 | 2023-01-0003 | Torcal Motors | Ford Ranger Pick-up C1N419 1 Piece - Replacement of Brake Pads (Front), 2 Pieces - Resurface Rotor Disc, 1 Liter - Supply of Brake Fluid (1 Liter) Labor | [19 empty] | RP-Davao |  | Small Value Procurement | [7 empty] | 2023-01-30 | 2023-01-30 | [5 empty] | 9850 | 9850 |  | 9850 | 9850
9 | 9 | 2023-01-0029 | 2022-01-0008 | RBO United Auto Parts and Hardware | 1 Unit - Electric Driller, 1 Set - Electric Bit, 1 Unit - Electric Grinder | [19 empty] | RP-Tuguegarao |  | Small Value Procurement | [7 empty] | 2023-01-31 | 2023-01-31 | [5 empty] | 15500 | 15500 |  | 15500 | 15500
10 | 10 | 2023-01-0029 | 2023-01-0006 | Circuit Shock Electronics Sales and Services | 2 Units - Multi-Tester Sanwa | [19 empty] | RP-Tuguegarao |  | Small Value Procurement | [7 empty] | 2023-01-31 | 2023-01-31 | [5 empty] | 5200 | 5200 |  | 5200 | 5200
11 | 11 | 2023-01-0029 | 2023-01-0007 | TFM-AKAC Agricultural Farm Machinery | 1 Unit - Grass Cutter 4 Stroke | [19 empty] | RP-Tuguegarao |  | Small Value Procurement | [7 empty] | 2023-01-31 | 2023-01-31 | [5 empty] | 6500 | 6500 |  | 6500 | 6500
12 | 12 | 2023-02-0035 | 2023-02-0010 | Timog Tirehaus Corporation | 4 Pieces - Tire 215 (70 R-16) | [19 empty] | Director's Office |  | Small Value Procurement | [7 empty] | 2023-02-03 | 2023-02-03 | [5 empty] | 34000 | 34000 |  | 33300 | 33300
13 | 12A | 2023-01-0007 | 2023-02-0004 | Civil Service Commission-Cordillera Administrative Region (Baguio City) | 1 Lot - Seminar Venue and Accommodation of the Management Cluster Meeting 2nd Leg in Baguio City on February 06-10, 2023 | [19 empty] | GAD |  | Agency-to-Agency | [7 empty] | 2023-02-03 | 2023-02-03 | [5 empty] | 79500 | 79500 |  | 79500 | 79500
14 | 13 | 2022-11-0466C | 2023-02-0011 | Dataview Computer Corporation | 3 Units - Samsung MZ-77E500BW 500GB Evo 2.5 Series SSD | [19 empty] | Research |  | Small Value Procurement | [7 empty] | 2023-02-03 | 2023-02-03 | [5 empty] | 15900 | 15900 |  | 13650 | 13650
15 | 14 | 2023-01-0008 | 2023-02-0012 | Dataview Computer Corporation | 1 Box - Belden CAT5E UTP Cable Grey Indoor PN: 1583A 305 Meters/Box | [19 empty] | Engineering |  | Small Value Procurement | [7 empty] | 2023-02-03 | 2023-02-03 | [5 empty] | 8000 | 8000 |  | 7950 | 7950
16 | 15 | 2023-01-0014 | 2023-02-0013 | Mostaco Marketing | 1 Lot - Various Office Supplies | [19 empty] | Property and Supply Section |  | Shopping 52.1B | [7 empty] | 2023-02-06 | 2023-02-05 | [5 empty] | 310050 | 310050 |  | 230345 | 230345
17 | 16 | 2023-01-0034B | 2023-02-0015 | Dataview Computer Corporation | 2 Units - 1TB Seagate 3.5 SATA Hardware | [19 empty] | Personnel Section |  | Small Value Procurement | [7 empty] | 2023-02-09 | 2023-02-09 | [5 empty] | 5700 | 5700 |  | 5700 | 5700
18 | 17 | 2023-01-0024 | 2023-02-0014 | Dataview Computer Corporation | 2 Units 0 TP Link TL-SC1016D Port Gigabit Switch Hub, 1 Unit - TP Link Arch C64 AC1200 Wireless Router, 50 Pieces - RJ Connector CAT5E, 1 Box - Adlink UTP Cable CAT5E, 1 Piece -Crimping Tool | [19 empty] | FM2 |  | Small Value Procurement | [7 empty] | 2023-02-09 | 2023-02-09 | [5 empty] | 14400 | 14400 |  | 12295 | 12295
19 | 18 | 2023-01-0007 | 2023-02-0016 | Halden General Merchandise | 1 Lot - Various Janitorial Cleaning Supplies | [19 empty] | General Services |  | Shopping 52.1B | [7 empty] | 2023-02-09 | 2023-02-09 | [5 empty] | 11860 | 11860 |  | 9635 | 9635
20 | 19 | 2023-01-0004 | 2023-02-0005 | Best Choice Gourmet & Catering Services, Inc. | 1 Lot - Meals for the 3-day Training on Government Procurement Reform Act (R.A. 9184) and its Revised Implementing Rules and Regulations (IRR) on February 22-24, 2023 at the Training Room, Bureau of Broadcast Services. 4th Floor PIA Media Center Bldg., Visayas Avenue, Quezon City. | [19 empty] | BAC |  | Small Value Procurement | [7 empty] | 2023-02-09 | 2023-02-09 | [5 empty] | 65340 | 65340 |  | 64350 | 64350
21 | 20 | 2023-01-0013C |  | Morning Star Printing | 1 Piece - Installation of Perforated Sticker on Glass Panels, 2 Pieces - Installation of Frosted Stickers on Glass Doors of DG and DDG’s doors | [19 empty] | RP-Davao |  | Small Value Procurement | [7 empty] | 2023-02-20 | 2023-02-20 | [5 empty] | 23000 | 23000 |  | 23000 | 23000
22 | 21 | 2023-01-0021 | 2023-02-0008 | KGP Travel and Tours | Airfare 1 Pax - Rizal Giovanni P. Aportadera, Jr. Flight Details: Manila to Cebu Cebu-Davao-Manila 1 Pax - Joan Marie S. Domingo Flight Details: Manila-Davao-Manila 1 Pax - Nigel Gamalong Flight Details: Manila-Davao-Manila | [19 empty] | Director's Office |  | Small Value Procurement | [7 empty] | 2023-02-14 | 2023-02-14 | [5 empty] | 84000 | 84000 |  | 82556 | 82556
23 | 22 | 2023-02-0043 | 2023-02-0019 | Davao JSC Curtains and Window Blinds Installation | 2 Sets - Combi Blinds (Visitor’s Lounge) 1 Set - Combi Blinds (FM1 Studio) | [19 empty] | RP-Davao |  | Small Value Procurement | [7 empty] | 2023-02-21 | 2023-02-21 | [5 empty] | 26765 | 26765 |  | 26765 | 26765
24 | 23 | 2923-01-0034D | 2023-02-0018 | Dataview Computer Corporation | 4 Units - APC BVX1200LI-MS 1200VA 230V UPS | [19 empty] | RP-Tandag |  | Small Value Procurement | [7 empty] | 2023-02-21 | 2023-02-21 | [5 empty] | 36000 | 36000 |  | 34000 | 34000
25 | 24 | 2023-01-0026 | 2023-02-0017 | Broadtech Corporation | 10 Pieces - ID Printer Ribbon N800-300-360 AP Color Ribbon YMCKOK | [19 empty] | Administrative |  | Shopping 52.1B | [7 empty] | 2023-02-20 | 2023-02-20 | [5 empty] | 50000 | 50000 |  | 37500 | 37500
26 | 24A | 2023-02-0020 | 2023-02-0007 | Department of Education Ecotech Center (Cebu City) | 1 Lot - Accommodations, Meals and Venue for the Managers’ Cluster Meeting 3rd Leg (Visayas Stations) in Cebu City on February 27 to March 3, 2023 | [19 empty] | GAD |  | Agency-to-Agency | [7 empty] | 2023-02-20 | 20 feb 23 | [5 empty] | 188475 | 188475 |  | 188475 | 188475
27 | 25 | 2023-01-0034M | 2023-02-0020 | Addessa Corporation | 2 Units - 2.0HP Airconditioner Window Type (Manual Panasonic) Model # CWN1820EPH) | [19 empty] | RP-Dagupan |  | Small Value Procurement | [7 empty] | 2023-02-28 | 2023-02-28 | [5 empty] | 60620 | 60620 |  | 60620 | 60620
28 | 26 | 2023-01-0013 | 2023-02-0009 | HPE Car Care Accessories | 1 Lot - Cleaning and Replacement of Engine Parts of the Station’s Vehicle (DWRB-Naga) | [19 empty] | RP-Naga |  | Small Value Procurement | [7 empty] | 2023-02-23 | 2023-02-23 | [5 empty] | 13000 | 13000 |  | 13000 | 13000
29 | 26A | 2023-02-0077D | 2023-02-0020A-1 | Gordiel Auto Parts | 1 Piece - Battery, 5 Plates NS40 Motolite | [19 empty] | RP-Cagayan de Oro |  | Small Value Procurement | [7 empty] | 2023-02-24 | 2023-02-24 | [5 empty] | 6800 | 6800 |  | 6800 | 6800
30 | 27 | 2023-02-0062 |  | Priority Trading | 1 Lot - Various Electrical Materials for the Electrical Line Installation at the New Office and Studio Building of RP-Lucena | [19 empty] | RP-Lucena |  | Small Value Procurement | [7 empty] | 2023-02-28 | 2023-02-28 | [5 empty] | 37386 | 37386 |  | 36060 | 36060
31 | 28 | 2023-02-0041 | 2023-02-0020 | DAVTECH Marketing | 1 Unit - Filing Cabinet, 3 Layer Lateral, 1 Unit - Filing Cabinet, 4 Vertical with Vault, 3 Units - Executive Chair High Back JS120 | [19 empty] | RP-Lucena |  | Small Value Procurement | [7 empty] | 2023-03-02 | 2 mar 223 | [5 empty] | 55500 | 55500 |  | 39900 | 39900
32 | 29 | 2023-02-0025 |  | Rafaz Land Development, Inc. | 1 Lot - Room Accommodations for Managers’ Cluster Meeting 4 (Mindanao Stations) in Davao City on March 13 to 17, 2023 (VAT Inclusive) | [19 empty] | GAD |  | Small Value Procurement | [7 empty] | 2023-03-06 | 2023-03-06 | [5 empty] | 75500 | 75500 |  | 73920 | 73920
33 | 30 | 2023-02-0039 | 2023-03-0021 | CBCD Trading | 1 Unit - Broadcast Mixer with 12 Channel | [19 empty] | RP-Lucena |  | Small Value Procurement | [7 empty] | 2023-03-03 | 2023-03-03 | [5 empty] | 16000 | 16000 |  | 15800 | 15800
34 | 31 | 2023-01-0034J | 2923-03-0022 | CBCD Trading | 1 Lot - Acoustic Panels and Various Painting Materials | [19 empty] | RP-Lucena |  | Small Value Procurement | [7 empty] | 2023-03-03 | 2023-03-03 | [5 empty] | 36900 | 36900 |  | 36860 | 36860
35 | 32 | 2023-02-0026 | 2023-03-0011 | EC King Party and Catering Services | 1 Lot - Meals for Managers’ Cluster Meeting 4 (Mindanao Stations) in Davao City on March 13 to 17, 2023 (VAT Inclusive) | [19 empty] | GAD |  | Small Value Procurement | [7 empty] | 2023-03-07 | 2023-03-07 | [5 empty] | 97400 | 97400 |  | 97400 | 97400
36 | 33 | 2022-08-0341Q, 2023-01-0032, 2023-02-0042 | 2023-03-0024 | Halden General Merchandise | 3 Units- Grass Cutter 4 Stroke | [19 empty] | RP Stations Albay, Tandag, Batanes |  | Small Value Procurement | [7 empty] | 2023-03-09 | 2023-03-09 | [5 empty] | 29400 | 29400 |  | 29400 | 29400
37 | 34 | 2023-02-0044 | 2023-03-0026 | Timog Tirehaus Corporation | 2 Units - Tire 215 / 70 R 15 | [19 empty] | General Services |  | Small Value Procurement | [7 empty] | 2023-03-10 | 2023-03-10 | [5 empty] | 17000 | 17000 |  | 16500 | 16500
38 | 35 | 2023-02-0050 | 2023-03-0025 | Dataview Computer Corporation | 2 Units - Brother DCP-T720DW All-in-One Printer, 1 Unit - Brother ADS-4300N Document Scanner | [19 empty] | COA |  | Shopping 52.1B | [7 empty] | 2023-03-09 | 2023-03-09 | [5 empty] | 60000 | 60000 |  | 38990 | 38990
39 | 36 | 2023-02-0044 | 2023-03-0027 | Great Country Auto Supply | 6 Sets - Brake Pad | [19 empty] | General Services |  | Small Value Procurement | [7 empty] | 1o mar 23 | 2023-03-10 | [5 empty] | 9000 | 9000 |  | 8700 | 8700
40 | 37 | 2023-02-0054 | 2023-03-0035 | Halden General Merchandise | 100 Pieces - T8 LED Tube Light 182 4FT Industrial Daylight Double Ended, 100 Pieces - LED Bulb 12 Watts Daylight Lamp | [19 empty] | Administrative |  | Small Value Procurement | [7 empty] | 2023-03-17 | 2023-03-17 | [5 empty] | 49000 | 49000 |  | 45000 | 45000
41 | 38 | 2023-02-0065 | 2023-03-0034 | Dataview Computer Corporation | 1 Unit - TP-Link SG 108-M2 SG10-M2 8 Port 2.5GB Gigabit Switch Hub | [19 empty] | RP3-Magasin |  | Small Value Procurement | [7 empty] | 2023-03-15 | 2023-03-15 | [5 empty] | 11567.56 | 11567.56 |  | 9500 | 9500
42 | 39 | 2023-02-0063 | 2023-03-0029 | Pacific Hardware | 1 Unit - Lawn Mower 2 Stroke | [19 empty] | RP-Zamboanga |  | Small Value Procurement | [7 empty] | 2023-03-13 | 2023-03-13 | [5 empty] | 5500 | 5500 |  | 5500 | 5500
43 | 40 | 2023-02-0058 |  | MRV Refrigeration and Airconditioning Parts and Supplies | 2 CYL - Freon R-22 (22.7kgs.) | [19 empty] | Engineering |  | Small Value Procurement | [7 empty] | 2023-03-13 | 2023-03-13 | [5 empty] | 23000 | 23000 |  | 23000 | 23000
44 | 41 | 2023-02-0061 | 2023-03-0032 | Western Lamp and Electrical Supply, Inc. | 300 Meters - Guy Wire, 18 Pieces - 1/2 U-Clamp | [19 empty] | RP-Iloilo |  | Small Value Procurement | [7 empty] | 2023-03-13 | 2023-03-13 | [5 empty] | 30540 | 30540 |  | 30540 | 30540
45 | 42 | 2023-01-0006B | 2023-01-0003D | Philippine Global Communications, Inc. | 1 Lot - 100 Mbps Monthly Subscription of Dedicated Enterprise Internet Plan with Unlimited Data (Period of January to December 2023) | [19 empty] | Engineering |  | GPPB Resolution No. 41-2017 amendment | [7 empty] | 2023-01-04 | 2023-01-04 | [5 empty] | 432000 | 432000 |  | 432000 | 432000
46 | 43 | 2023-02-0064 | 2023-03-0030 | PAM APEX Ventures, Inc. | 1 Unit - Battery for Isuzu Crosswind 3SMF, 12V | [19 empty] | RP-Cebu |  | Small Value Procurement | [7 empty] | 2023-03-13 | 2023-03-13 | [5 empty] | 8670 | 8670 |  | 8670 | 8670
47 | 44 | 2023-02-0074 | 2023-03-0033 | DAD Construction and Supply | 1 Unit - Stainless Water Tank | [19 empty] | RP-Bontoc |  | Small Value Procurement | [7 empty] | 2023-03-14 | 2023-03-14 | [5 empty] | 48000 | 48000 |  | 48000 | 48000
48 | 45 | 2023-02-0017 | 2023-03-0012 | Frigid Zone Car Aircon Specialist, Co. | 1 Unit - Repair of Crosswind Vehicle Pull Down Evaporator for General Cleaning and Leak Test (Front and Rear) Add Capella Oil, Vacumn of Lines, Recharge Freon Gas R34A and Replace Cooling Coil | [19 empty] | General Services |  | Small Value Procurement | [7 empty] | 2023-03-21 | 2023-03-21 | [5 empty] | 9500 | 9500 |  | 9500 | 9500
49 | 46 | 2023-02-0048 | 2023-03-0034 | SKM Industrial Sales | 2 Pails - Merco 364 Aircon Cleaner Alkaline, 3 Pieces - Merco 048 Squeeze In Penetrating Oilm, 3 Pieces - Merco 034 Electrical Contact Cleaner | [19 empty] | Engineering |  | Small Value Procurement | [7 empty] | 2023-03-21 | 2023-03-21 | [5 empty] | 13000 | 13000 |  | 13000 | 13000
50 | 47 | 2023-02-0028B | 2023-03-0031 | HPE Car Care Accessories | 1 Unit - Repair of Station’s Vehicle Clutch, Under Chassis and Replacement of Busted Parts (RP-Naga) | [19 empty] | RP-Naga |  | Small Value Procurement | [7 empty] | 2023-03-13 | 2023-03-13 | [5 empty] | 36730 | 36730 |  | 36730 | 36730
51 | 48 | 2023-03-0031 | 2023-03-0013 | RJD Media Advertising | 1 Lot - Printing of Vinyl over Sintra Board GAD Legacy Wall with Installation (with attached design), 1 Lot - Printing of PBS-BBS Logos with Installation (Please see attached design) | [19 empty] | GAD |  | Small Value Procurement | [7 empty] | 2023-03-22 | 2023-03-22 | [5 empty] | 77828 | 77828 |  | 77570.08 | 77570.08
52 | 49 | 2023-02-0077B | 2023-03-0036 | Melda Madrid Hardware Center, Inc. | 1 Lot - Materials for the Repair of Beam and Gutter of RP-Tuguegarao Station | [19 empty] | RP-Tuguegarao |  | Small Value Procurement | [7 empty] | 2023-03-22 | 2023-03-22 | [5 empty] | 6443 | 6443 |  | 6443 | 6443
53 | 50 | 2023-03-0089 | 2023-03-0037 | MDD Industrial Sales | 2 Units - Fire Extinguisher | [19 empty] | RP-Bontoc |  | Small Value Procurement | [7 empty] | 2023-03-22 | 2023-03-22 | [5 empty] | 3600 | 3600 |  | 3600 | 3600
54 | 50A | 2023-03-0037 | 2023-04-0039C | RJD Media Advertising | 1 Lot - Printing of Ten (10) Photos from the Mobile Photo Competition 2023 (VAT Inclusive) | [19 empty] | GAD |  | Small Value Procurement | [7 empty] | 2023-03-24 | 2023-03-24 | [5 empty] | 11760 | 11760 |  | 11760 | 11760
55 | 51 | 2023-02-0028C | 2023-03-0014 | Torcal Motors | 1 Unit - Repair of Isuzu Crosswind CN 5482 (Cleaning of Aircon and Replacement of Parts) | [19 empty] | RP-Davao |  | Small Value Procurement | [7 empty] | 2023-03-24 | 2023-03-24 | [5 empty] | 9800 | 9800 |  | 9800 | 9800
56 | 52 | 2023-03-0099 | 2023-03-0038 | Timog Tirehaus Corporation | 1 Piece - Battery 3SM, 1 Piece - Battery 2SM | [19 empty] | General Services |  | Small Value Procurement | [7 empty] | 2023-03-31 | 2023-03-31 | [5 empty] | 18000 | 18000 |  | 17800 | 17800
57 | 53 | 2023-01-0034D | 2023-04-0039 | Dataview Computer Corporation | 3 Units - Kingston 250GB NVME PCIE M.2 SSD | [19 empty] | Finance |  | Small Value Procurement | [7 empty] | 2023-04-04 | 2023-04-04 | [5 empty] | 7950 | 7950 |  | 7650 | 7650
58 | 54 | 2023-03-0039 | 2023-04-0015 | Composite Technology, Inc. | 1 Unit - Additional Services of Harris DX10 Transmitter at Tabuk, Kalinga (VAT Inclusive) | [19 empty] | RP-Tabuk |  | Direct Contracting | [7 empty] | 2023-04-03 | 2023-04-03 | [5 empty] | 112000 | 112000 |  | 112000 | 112000
59 | 55 | 2023-03-0038 | 2923-04-0016 | J.A. Aradillos Refrigeration & Airconditioning Services | 2 Units - Refill of Freon, Repair and General Cleaning of 2 Units Window Type Aircon 2HP at the Transmitter Room | [19 empty] | RP-Tandag |  | Small Value Procurement | [7 empty] | 2023-04-04 | 2023-04-04 | [5 empty] | 5600 | 5600 |  | 5600 | 5600
60 | 56 | 2023-03-0085 | 2023-04-0041 | Dataview Computer Corporation | 2 Pieces - SATA Cable with High Speed Serial Sort 3.0 6GB / Solid State Hard Disk Data Cable for PC 1 Piece - Logitech C922 Pro StreamWebcam | [19 empty] | RP3-Magasin |  | Small Value Procurement | [7 empty] | 2023-04-05 | 2023-04-05 | [5 empty] | 7523.65 | 7523.65 |  | 7450 | 7450
61 | 57 | 2023-03-0076 | 2023-04-0042 | Dataview Computer Corporation | 2 Units - Seagate 1TB External Hardrive | [19 empty] | RP-Batanes |  | Shopping 52.1B | [7 empty] | 2023-04-05 | 2023-04-05 | [5 empty] | 10000 | 10000 |  | 7990 | 7990
62 | 58 | 2023-03-0080 | 2023-04-0043 | Dataview Computer Corporation | 1 Unit - Brother DCP-T720DW Printer | [19 empty] | RP-Iligan |  | Shopping 52.1B | [7 empty] | 2023-04-05 | 2023-04-05 | [5 empty] | 13995 | 13995 |  | 13995 | 13995
63 | 59 | 2023-03-0086 | 2023-04-0045 | Dataview Computer Corporation | 1 Unit - Samsung 24” inch Curved Monitor S FHD 1920 x 1080 | [19 empty] | RP2-Sports |  | Small Value Procurement | [7 empty] | 2023-04-04 | 2023-04-04 | [5 empty] | 10000 | 10000 |  | 9000 | 9000
64 | 60 | 2023-03-0098 | 2023-04-0044 | Dataview Computer Corporation | 1 Unit - Kingston 250GB NV2 PCIE NVME SSD, 2 Units - Kingston 8GB Fury DDR4 3200 MHz Long DIMM | [19 empty] | Engineering |  | Small Value Procurement | [7 empty] | 2023-04-04 | 2023-04-04 | [5 empty] | 6734 | 6734 |  | 6540 | 6540
65 | 61 | 2023-03-0066 | 2023-04-0048 | Art Johnley Enterprises | 2 Units - 1.5HP Window Type Airconditioner (WCARJO14EE) Inverter Technology | [19 empty] | RP-Bontoc |  | Small Value Procurement | [7 empty] | 2023-04-11 | 2023-04-11 | [5 empty] | 59000 | 59000 |  | 56998 | 56998
66 | 62 | 2023-03-0107 | 2023-04-0047 | Halden General Merchandise | 700 Pieces - Trash Bag XL, 15 Gallons - Liquid Hand Soap. 15 Kilos - Powder Soap 30 Pieces - Lysol Disinfectant Spray, 500ml, 36 Pieces - Albatross, Small, 3 Gallons - Toilet Bowl Cleaner, 12 Bottles - Zonrox, 1 Liter, 9 Pieces - Furniture Cleaner | [19 empty] | General Services |  | Shopping 52.1B | [7 empty] | 2023-04-11 | 2023-04-11 | [5 empty] | 38880 | 38880 |  | 32420 | 32420
67 | 63 | 2023-03-0078 | 2023-04-0046 | Dataview Computer Corporation | 1 Unit - Samsung 24” inch IPS Monitor | [19 empty] | Public Affairs |  | Small Value Procurement | [7 empty] | 2023-04-13 | 2023-04-13 | [5 empty] | 7599 | 7599 |  | 7450 | 7450
68 | 64 | 2023-01-0034N | 2023-04-0049 | DAVTECH Marketing | 6 Units - Chair Office Computer Sturdy Chair with Headrest | [19 empty] | RP3-Magasin |  | Small Value Procurement | [7 empty] | 2023-04-14 | 2023-04-14 | [5 empty] | 24000 | 24000 |  | 21600 | 21600
69 | 65 | 2023-04-0121 | 2023-04-0051 | Dataview Computer Corporation | 1 Unit - ACER XL2320W Projector | [19 empty] | Property and Supply Section |  | Small Value Procurement | [7 empty] | 2023-04-18 | 2023-04-18 | [5 empty] | 45000 | 45000 |  | 43899 | 43899
70 | 66 | 2023-04-0071 | 2023-04-0050 | Halden General Merchandise | 1 Unit - Smart TV 32" | [19 empty] | RP3-Magasin |  | Small Value Procurement | [7 empty] | 2023-04-18 | 2023-04-18 | [5 empty] | 10300 | 10300 |  | 10280 | 10280
71 | 67 | 2023-03-0110 | 2023-04-0053 | Dataview Computer Corporation | 1 Unit - Logitech MK220 Wireless Combo Keyboard Mouse, 1 Unit - 120MM Case Fan 4-PIN, 4 Pieces - SATA Cable, 1 Unit - TP-Link Archer AX23 AX1800 Dual Band Router | [19 empty] | Property and Supply Section |  | Small Value Procurement | [7 empty] | 2023-04-18 | 2023-04-18 | [5 empty] | 8450 | 8450 |  | 6145 | 6145
72 | 68 | 2023-03-0109 | 2023-04-0052 | Dataview Computer Corporation | 2 Boxes - Belden CAT5E UTP Cable (Gray) | [19 empty] | Engineering |  | Small Value Procurement | [7 empty] | 2023-04-19 | 2023-04-19 | [5 empty] | 16000 | 16000 |  | 15900 | 15900
73 | 69 | 2023-4-0130 | 2023-04-0054 | Dataview Computer Corporation | 2 Units - Samsung 500GB 870 EVO 2.5 SATA Solid State Drive | [19 empty] | Network |  | Small Value Procurement | [7 empty] | 2023-04-25 | 2023-04-25 | [5 empty] | 10600 | 10600 |  | 9100 | 9100
74 | 70 | 2023-03-0114F | 2023-04-0055 | Dataview Computer Corporation | 1 Unit - GTX 1650 StormX 4G GDDR5 128BI DVI HDMI Video Card | [19 empty] | RP-Tuguegarao |  | Small Value Procurement | [7 empty] | 2023-04-27 | 2023-04-27 | [5 empty] | 10000 | 10000 |  | 10000 | 10000
75 | 71 | 2023-03-0102 | 2023-04-0056 | Halden General Merchandise | 1 Lot - Materials for the Repainting and Vtnyl Flooring installation of RP3-Worldwide | [19 empty] | RP-Worldwide |  | Small Value Procurement | [7 empty] | 2023-04-27 | 2023-04-27 | [5 empty] | 23430 | 23430 |  | 22160 | 22160
76 | 72 | 2023-04-0143 | 2023-04-0059 | J2 Tire Center | 4 Units - Tires 185R x 14C | [19 empty] | RP-Bontoc |  | Small Value Procurement | [7 empty] | 2023-04-28 | 2023-04-28 | [5 empty] | 19600 | 19600 |  | 19600 | 19600
77 | 72A | 2023-04-0144C | 2023-04-0059A | Winterfield Marketing | 6 Gallons - Boysen QDE White, 6 Gallons - Boysen QDE Orange, 2 Pieces - Paint Thinner, 4 Pieces - Paint Brush 3” | [19 empty] | RP-Iloilo |  | Small Value Procurement | [7 empty] | 2023-04-28 | 2023-04-28 | [5 empty] | 12280 | 12280 |  | 12280 | 12280
78 | 73 | 2023-04-0136 | 2023-04-0058 | LU JLB Battery Parts & Supply | 1 Unit - Battery 2SM/12V | [19 empty] | RP-Agoo |  | Small Value Procurement | [7 empty] | 2023-04-28 | 2023-04-28 | [5 empty] | 6400 | 6400 |  | 6400 | 6400
79 | 74 | 2023-03-0108 | 2023-04-0057 | Art Johnley Enterprises | 1 Unit - 1.5HP Split Type Wall Mounted Inverter Airconditioning Unit With free installation for the first 10FT copper tubing, free circuit breaker | [19 empty] | Public Affairs |  | Small Value Procurement | [7 empty] | 2023-04-28 | 2023-04-28 | [5 empty] | 49995 | 49995 |  | 41999 | 41999
80 | 75 | 2023-03-0114C | 2023-05-0060 | Mostaco Marketing | 1 Lot - Various Office Supplies | [19 empty] | Property and Supply Section |  | Shopping 52.1B | [7 empty] | 2023-05-03 | 2023-05-03 | [5 empty] | 137100 | 137100 |  | 105451 | 105451
81 | 75A | 2023-05-0157 | 2023-05-0061 | Timog Tirehaus Corporation | 1 Piece - Battery 3SM Reverse | [19 empty] | General Services |  | Small Value Procurement | [7 empty] | 2023-05-10 | 2023-05-10 | [5 empty] | 9450 | 9450 |  | 9450 | 9450
82 | 76 | 2023-04-0043 |  | Canva, Inc., Bitly, Inc., Twitter, Inc. | 1 Lot - Annual Subscription of Twitter Blue, Bitly and Canva for use of RP1 Social Media Accounts | [19 empty] | Research |  | Direct Retail Purchase 53.14 | [7 empty] | 2023-05-04 | 2023-05-04 | [5 empty] | 28190 | 28190 |  | 28190 | 28190
83 | 77 | 2023-04-0144B | 2023-05-0062 | Shamir da Lim's Hardware, Co. | 6 Gallons - QDE White, 6 Gallons - QDE Orange, 2 Gallons - Paint Thinner, 4 Pieces - Paint Brush 3” HIPPO, 4 Pieces - Paint Scrapper 2 ½” | [19 empty] | RP-Tabuk |  | Small Value Procurement | [7 empty] | 2023-05-15 | 2023-05-15 | [5 empty] | 8690 | 8690 |  | 8690 | 8690
84 | 78 | 2023-05-0145 | 2023-05-0063 | Timog Tirehaus Corporation | 2 Units - NS60ZS Battery | [19 empty] | RP-Iloilo |  | Small Value Procurement | [7 empty] | 2023-05-19 | 2023-05-19 | [5 empty] | 17000 | 17000 |  | 16000 | 16000
85 | 81 | 2023-04-0144C |  | Winterfield Marketing | 6 Gallons - QDE White, 6 Gallons - QDE Orange, 2 Gallons - Paint Thinner, 4 Pieces - Paint Brush 3” | [19 empty] | RP-Iloilo |  | Small Value Procurement | [7 empty] | 2023-05-17 | 2023-05-17 | [5 empty] | 12280 | 12280 |  | 12280 | 12280
86 | 82 | 2023-04-0044B | 2023-06-0018 | HPE Car Care Accessories | 1 Lot - Labor and Materials for theRepair of RP-Naga Station’s Vehicle | [19 empty] | RP-Naga |  | Small Value Procurement | [7 empty] | 2023-06-05 | 2023-06-05 | [5 empty] | 22230 | 22230 |  | 22230 | 22230
87 | 83 | 2023-03-0039H | 2023-06-0017 | Torcal Motors | 1 Lot - Replacement of Caliper Assembly and Rotor Disc | [19 empty] | RP-Davao |  | Small Value Procurement | [7 empty] | 2023-06-05 | 2023-06-05 | [5 empty] | 26300 | 26300 |  | 26300 | 26300
88 | 84 | 2023-04-0044C | 2023-06-0019 | Newstar Glass and Aluminum | 1 Lot - Repair, Assembly and Installation of Swing Doors (DZEQ-Baguio) | [19 empty] | RP-Baguio |  | Small Value Procurement | [7 empty] | 2023-06-05 | 2023-06-05 | [5 empty] | 42250 | 42250 |  | 42250 | 42250
89 | 85 | 2023-05-0166 | 2023--06-0064 | Melda Madrid Hardware Center, Inc. | 1 Lot - Various Construction Materials for the Tightening of Security in Transmitter Container Van | [19 empty] | RP-Tuguegarao |  | Small Value Procurement | [7 empty] | 2023-06-05 | 2023-06-05 | [5 empty] | 7534 | 7534 |  | 7534 | 7534
90 | 86 | 2023-04-0144H | 2023-06-0065 | Triad Fire Fighting Equipment | 2 Units - Fire Extinguisher 20LBS HFC-236 | [19 empty] | RP-Tandag |  | Small Value Procurement | [7 empty] | 2023-06-05 | 2023-06-05 | [5 empty] | 39600 | 39600 |  | 39600 | 39600
91 | 87 | 2023-04-0144G | 2023-06-0066 | CtitHardware Bacolod, Inc. | 3 Units - Swivel Chair | [19 empty] | RP-Tandag |  | Small Value Procurement | [7 empty] | 2023-06-05 | 2023-06-05 | [5 empty] | 13185 | 13185 |  | 13185 | 13185
92 | 88 | 2023-04-0144M | 2023-06-0068 | Matada Hardware | 1 Lot - Various Materials for the Repainting of RP-Jolo Transmitter | [19 empty] | RP-Jolo |  | Small Value Procurement | [7 empty] | 2023-06-05 | 2023-06-05 | [5 empty] | 15697 | 15697 |  | 15697 | 15697
93 | 89 | 2023-04-0144F | 2023-06-0067 | Better Exponents, Inc. | 1 Piece - Logitech HD Webcam, 1 Piece - 3 Meters USB Extension, 2 Pieces - Camera Tripod | [19 empty] | RP-Davao |  | Small Value Procurement | [7 empty] | 2023-06-05 | 2023-06-05 | [5 empty] | 8200 | 8200 |  | 8200 | 8200
94 | 90 | 2023-03-0114J | 2023-06-0069 | Aljeann Auto Supply, Inc. | 1 Unit - Starter Assembly | [19 empty] | RP-Agoo |  | Small Value Procurement | [7 empty] | 2023-06-05 | 2023-06-05 | [5 empty] | 9500 | 9500 |  | 9500 | 9500
95 | 91 | 2023-03-0144D | 2023-06-0072 | CBCD Trading | 2 Units - MR4 Powered Studio Monitor Speaker 4” Active Near Field Monitor Speaker, 10 Pieces - XLR Male Plug, 10 Pieces - XLR Female Plug, 4 Pieces - Stereo Microphone Plug PL-55 Plug Stereo ¼ (6.35mm) | [19 empty] | RP3-Magasin |  | Small Value Procurement | [7 empty] | 2023-06-13 | 2023-06-13 | [5 empty] | 17296.2 | 17296.2 |  | 17220 | 17220
96 | 92 | 2023-04-0124 | 2023-06-0070 | Halden General Merchandise | 1 Unit - Induction Motor Pressure Washer 130 Bar, 1900Watts | [19 empty] | Engineering |  | Small Value Procurement | [7 empty] | 2023-06-13 | 2023-06-13 | [5 empty] | 11000 | 11000 |  | 11000 | 11000
97 | 93 | 2023-04-0125 | 2023-06-0073 | CBCD Trading | 1 Unit - Power Amplifier Stereo: 2 x 50/80 Ohms Damping Factor300 THD THD 0.05% Line Frequency Response 20 Hz – 20 kHz AC 220 -250V – 50 Hz | [19 empty] | Engineering |  | Small Value Procurement | [7 empty] | 2023-06-14 | 2023-06-14 | [5 empty] | 20000 | 20000 |  | 19800 | 19800
98 | 94 | 2023-03-0117 | 2023-06-0074 | Halden General Merchandise | 1 Unit - Atem Mini Pro Livestream Switcher HDMI for Video Editing Streaming, 1 Unit - 3M HDMI to HDMI Cable, 1 Unit - Micro HDMI to Standard HDMI Cable, 1 Unit - USB Audio Interface Sound Card | [19 empty] | RP3-Magasin |  | Small Value Procurement | [7 empty] | 2023-06-15 | 2023-06-15 | [5 empty] | 36700 | 36700 |  | 36700 | 36700
99 | 95 | 2023-05-0161 | 2023-06-0075 | Halden General Merchandise | 6 Gallons - Shelby Rubberized Liquid Asphalt Waterproofing | [19 empty] | Engineering |  | Small Value Procurement | [7 empty] | 2023-06-19 | 2023-06-19 | [5 empty] | 12000 | 12000 |  | 9600 | 9600
100 | 96 | 2023-03-0100 | 2023-06-0077 | CBCD Trading | 4 Units - Dynamic Cardiod Microphone | [19 empty] | Engineering |  | Small Value Procurement | [7 empty] | 2023-06-20 | 2023-06-20 | [5 empty] | 194000 | 194000 |  | 193200 | 193200
101 | 97 | 2023-05-0164 | 2023-06-0076 | AVID Sales Corporation | 5 Units - 55” Inches 4K HDR Google TV, TCL 55P635 | [19 empty] | RP Stations Davao, Cebu, CDO, Baguio, Lucena |  | Small Value Procurement | [7 empty] | 2023-06-19 | 2023-06-19 | [5 empty] | 150000 | 150000 |  | 99995 | 99995
102 | 98 | 2023-05-0172 | 2023-06-0078 | Smartzone Appliance Square | 2 Units - Airconditioner, 2HP, Window Type Inverter, Kolin Brand | [19 empty] | RP-Cebu |  | Small Value Procurement | [7 empty] | 2023-06-09 | 2023-06-09 | [5 empty] | 73990 | 73990 |  | 73990 | 73990
103 | 99 | 2023-05-0180C | 2023-06-0079 | Dwinar Computer Center | 1 Unit - 1TB Solid State Drive with SATA Cord | [19 empty] | RP-Davao |  | Small Value Procurement | [7 empty] | 2023-06-20 | 2023-06-20 | [5 empty] | 3550 | 3550 |  | 3550 | 3550
104 | 100 | 2023-05-0156 | 2023-06-0071 | Halden General Merchandise | 6 Units - Recessed Heavy Duty Troffer Lightning Fixture (2 x 40W, 24”) with 18 Watts LED Lamp Day Light | [19 empty] | Engineering |  | Small Value Procurement | [7 empty] | 2023-06-13 | 2023-06-13 | [5 empty] | 17400 | 17400 |  | 17400 | 17400
105 | 101 | 2923-04-0123 | 2023-06-0081 | Halden General Merchandise | 1 Unit - 50K Real 4K UHD Smart TV, 1 Unit - Tripod with Hybrid Head | [19 empty] | RP3-Magasin |  | Small Value Procurement | [7 empty] | 2023-06-22 | 2023-06-22 | [5 empty] | 29490 | 29490 |  | 27800 | 27800
106 | 102 | 2023-04-0138 | 2023-06-0080 | Halden General Merchandise | 1 Unit - USB Audio Interface AGS17 with 1 Line-in, 1, Instrument Input, 1, 1 Unit -Headphone Out, 2 Line-Out Tripod, 1 Unit - Lite Panel Lamp 30W, 1 Unit - HDMI Cable | [19 empty] | RP-Worldwide |  | Small Value Procurement | [7 empty] | 2023-06-22 | 2023-06-22 | [5 empty] | 26835 | 26835 |  | 26800 | 26800
107 | 103 | 2023-05-0152 | 2023-06-0082 | CBCD Trading | 1 Unit - Carpet 4 Meter x 4 Meter (Red) | [19 empty] | RP-Lucena |  | Small Value Procurement | [7 empty] | 2023-06-23 | 2023-06-23 | [5 empty] | 9000 | 9000 |  | 8900 | 8900
108 | 104 | 2023-06-0187 | 2023-06-0083 | Mostaco Marketing | 1 Lot - Various Office Supplies | [19 empty] | Property & Supply Section |  | Small Value Procurement | [7 empty] | 2023-06-26 | 2023-06-26 | [5 empty] | 118550 | 118550 |  | 89090 | 89090
109 | 105 | 2023-05-0177 | 2023-06-0084 | Great Country Auto Supply | 1 Set - Clutch Assembly (for Avanza), 1 Set - Clutch Assembly (for Starex) | [19 empty] | General Services |  | Small Value Procurement | [7 empty] | 2023-06-30 | 2023-06-30 | [5 empty] | 15550 | 15550 |  | 15100 | 15100
110 | 106 | 2022-09-0403J | 2023-06-0087 | CBCD Trading | 1 Unit - Audio Console, Yamaha, 1 Unit - Microphone Arms, Boom Type | [19 empty] | RP-Gingoog |  | Small Value Procurement | [7 empty] | 2023-06-30 | 2023-06-30 | [5 empty] | 45500 | 45500 |  | 44500 | 44500
111 | 108 | 2023-05-0160 | 2023-06-0085 | CBCD Trading | 21 Pieces - Shuckle ½, 42 Pieces - Thimble ½, 15 Pieces - US Type Jaw & Eye Turnbuckle ¾ | [19 empty] | RP-Jolo |  | Small Value Procurement | [7 empty] | 2023-06-30 | 2023-06-30 | [5 empty] | 37800 | 37800 |  | 37035 | 37035
Total Alloted Budget of Procurement Activities | [41 empty] | 4139872.41
Total Contract Price of Procurement Actitvites Conducted | [44 empty] | 3838767.08
Total Savings (Total Alloted Budget - Total Contract Price) | [41 empty] | 301105.33
0N-GOING PROCUREMENT ACTIVITIES
1 |  | 2023-05-0180B |  |  | 100 Pieces - IRF 350 Mosfet | [19 empty] | RP Stations Tandag, Zambonanga, Tabuk, Borongan |  | Small Value Procurement | [14 empty] | 250000 | 250000
2 |  | 2023-06-0199 |  |  | 1 Unit - Dry Type Induction 60KVA Transformer, 60KVA | [19 empty] | RP-Cebu | [16 empty] | 122000 | 122000
3 |  | 2023-06-0182 |  |  | 2 Units - 2HP Window Type AC | [19 empty] | RP-Tandag |  | Small Value Procurement | [14 empty] | 73990 | 73990
4 |  | 2023-03-0100 |  |  | 4 Units - Dynamic Cardiod Microphone | [19 empty] | Engineering |  | Small Value Procurement | [14 empty] | 104000 | 194000
5 |  | 2023-04-0129 |  |  | 1 Unit - Portable Power Station, 1 Unit - 220Watts Bifacial Portable Solar Panel | [19 empty] | Engineering |  | Small Value Procurement | [14 empty] | 79000 | 79000
6 |  | 2023-06-0214 |  |  | 1 Lot - Various Cleaning Supplies | [19 empty] | General Services |  | Small Value Procurement | [14 empty] | 52450 | 52450
7 |  | 2023-03-0101 |  |  | 4 Units -Announcer’s Headset (Professional Monitor), 4 Units - Production Swivel Chair, 2 Units - Announcer's Chair, 1 Unit - 32" Smart Television | [19 empty] | FM1 |  | Small Value Procurement | [14 empty] | 176000 | 176000
8 |  | 2023-05-0154 |  |  | 2 Pieces - Printer, Colored Ink Tank, 10 Pieces - Flash Drive 16GB, 1 Piece - Hard Drive 1TB, 8 Pieces - Earphones, 3 Pieces - AM/FM Radio Portable, 4 Pieces - Extension Cord Heavy Duty, 8 Pieces - Computer Speaker | [19 empty] | News |  | Small Value Procurement | [14 empty] | 50000 | 50000
Total Alloted Budget of On-going Procurement Activities | [41 empty] | 907440
[25 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
[25 empty] | RODNEY O. VILLANUEVA | [10 empty] | ALAN L. ALLANIGUE | [10 empty] | RIZAL GIOVANNI P. APORTADERA, JR.
[25 empty] | BAC Secretariat Head | [10 empty] | BAC Chairperson | [10 empty] | Director IV / Head of the Procuring Entity

## Sheet2
49000 | 49000 | 49000 | 49000
8775 | 8775 | 8775 | 8775
10000 | 10000 | 9975 | 9975
6305 | 6305 | 6305 | 6305
20400 | 20400 | 19500 | 19500
9004 | 9004 | 8385 | 8385
5700 | 5700 | 5700 | 5700
9850 | 9850 | 9850 | 9850
15500 | 15500 | 15500 | 15500
5200 | 5200 | 5200 | 5200
6500 | 6500 | 6500 | 6500
34000 | 34000 | 33300 | 33300
79500 | 79500 | 79500 | 79500
15900 | 15900 | 13650 | 13650
8000 | 8000 | 7950 | 7950
310050 | 310050 | 230345 | 230345
5700 | 5700 | 5700 | 5700
14400 | 14400 | 12295 | 12295
11860 | 11860 | 9635 | 9635
65340 | 65340 | 64350 | 64350
23000 | 23000 | 23000 | 23000
84000 | 84000 | 82556 | 82556
26765 | 26765 | 26765 | 26765
36000 | 36000 | 34000 | 34000
50000 | 50000 | 37500 | 37500
188475 | 188475 | 188475 | 188475
60620 | 60620 | 60620 | 60620
13000 | 13000 | 13000 | 13000
6800 | 6800 | 6800 | 6800
37386 | 37386 | 36060 | 36060
55500 | 55500 | 39900 | 39900
75500 | 75500 | 73920 | 73920
16000 | 16000 | 15800 | 15800
36900 | 36900 | 36860 | 36860
97400 | 97400 | 97400 | 97400
29400 | 29400 | 29400 | 29400
17000 | 17000 | 16500 | 16500
60000 | 60000 | 38990 | 38990
9000 | 9000 | 8700 | 8700
49000 | 49000 | 45000 | 45000
11567.56 | 11567.56 | 9500 | 9500
5500 | 5500 | 5500 | 5500
23000 | 23000 | 23000 | 23000
30540 | 30540 | 30540 | 30540
432000 | 432000 | 432000 | 432000
8670 | 8670 | 8670 | 8670
48000 | 48000 | 48000 | 48000
9500 | 9500 | 9500 | 9500
13000 | 13000 | 13000 | 13000
36730 | 36730 | 36730 | 36730
77828 | 77828 | 77570.08 | 77570.08
6443 | 6443 | 6443 | 6443
3600 | 3600 | 3600 | 3600
11760 | 11760 | 11760 | 11760
9800 | 9800 | 9800 | 9800
18000 | 18000 | 17800 | 17800
7950 | 7950 | 7650 | 7650
112000 | 112000 | 112000 | 112000
5600 | 5600 | 5600 | 5600
7523.65 | 7523.65 | 7450 | 7450
10000 | 10000 | 7990 | 7990
13995 | 13995 | 13995 | 13995
10000 | 10000 | 9000 | 9000
6734 | 6734 | 6540 | 6540
59000 | 59000 | 56998 | 56998
38880 | 38880 | 32420 | 32420
7599 | 7599 | 7450 | 7450
24000 | 24000 | 21600 | 21600
45000 | 45000 | 43899 | 43899
10300 | 10300 | 10280 | 10280
8450 | 8450 | 6145 | 6145
16000 | 16000 | 15900 | 15900
10600 | 10600 | 9100 | 9100
10000 | 10000 | 10000 | 10000
23430 | 23430 | 22160 | 22160
19600 | 19600 | 19600 | 19600
12280 | 12280 | 12280 | 12280
6400 | 6400 | 6400 | 6400
49995 | 49995 | 41999 | 41999
137100 | 137100 | 105451 | 105451
9450 | 9450 | 9450 | 9450
28190 | 28190 | 28190 | 28190
8690 | 8690 | 8690 | 8690
17000 | 17000 | 16000 | 16000
12280 | 12280 | 12280 | 12280
22230 | 22230 | 22230 | 22230
26300 | 26300 | 26300 | 26300
42250 | 42250 | 42250 | 42250
7534 | 7534 | 7534 | 7534
39600 | 39600 | 39600 | 39600
13185 | 13185 | 13185 | 13185
15697 | 15697 | 15697 | 15697
8200 | 8200 | 8200 | 8200
9500 | 9500 | 9500 | 9500
17296.2 | 17296.2 | 17220 | 17220
11000 | 11000 | 11000 | 11000
20000 | 20000 | 19800 | 19800
36700 | 36700 | 36700 | 36700
12000 | 12000 | 9600 | 9600
194000 | 194000 | 193200 | 193200
150000 | 150000 | 99995 | 99995
73990 | 73990 | 73990 | 73990
3550 | 3550 | 3550 | 3550
17400 | 17400 | 17400 | 17400
29490 | 29490 | 27800 | 27800
26835 | 26835 | 26800 | 26800
9000 | 9000 | 8900 | 8900
118550 | 118550 | 89090 | 89090
15550 | 15550 | 15100 | 15100 | 450 | Savings | as of June 27, 2023
45500 | 45500 | 44500 | 44500
122000 | 122000 | 85000 | 85000
37800 | 37800 | 37035 | 37035
4261872.41 | 4261872.41 | 3923767.08 | 3923767.08

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement