## pmr
ANNEX A
[6 empty] | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | Bureau of Broadcast Services Procurement Monitoring Report as of July 01, 2023 to December 31, 2023
Code (PAP) |  |  |  |  | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
[8 empty] | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
1 | 109 | 2023-07-0052 | 2023-07-0021 | LG Madrigal Motor Works | 1 Lot - \Repair of Electrical System and Power Window Passenger Side of Sportivo SHX 567 | [19 empty] | General Services | NO | Small Value Procurement | [5 empty] | 2023-07-10 |  | 2023-07-10 | [5 empty] | GAA | 32000 | 32000 |  | 24000 | 24000
2 | 110 | 2023-07-0178 | 2023-07-0088 | Halden General Merchandise | 18 Units - Recessed Heavy Duty Troffer Lighting Fixture (2” x 40W x 24” x 48”) with 18W LED Light Day Light | [19 empty] | Engineering | NO | Small Value Procurement | [5 empty] | 2023-07-11 |  | 2023-07-11 | [5 empty] | GAA | 48600 | 48600 |  | 48600 | 48600
3 | 110A | 2023-06-0051F | 2023-07-0022C | AGB Nielsen Media Research Phils, Inc. | 1 Lot - Mega Manila Radio Audience Measurement (RAM) Service for the month of July 2023 | [19 empty] | Research | NO | Scientific Scholarly | [5 empty] | 2023-07-03 |  | 2023-07-03 | [5 empty] | GAA | 804720 | 804720 |  | 804720 | 804720
4 | 111 | 2025-06-0200 | 2023-07-0089 | PCG IT Center Corporation | 2 Units - 16GB DDR4, 2 Unit - 2666/200MHZ Memory for Desktop, 1 Piece -112CM Chassis Fan. 1 Piece - 8CM Chassis Fan | [19 empty] | Personnel | NO | Small Value Procurement | [5 empty] | 2023-07-13 |  | 2023-07-13 | [5 empty] | GAA | 9700 | 9700 |  | 5730 | 5730
5 | 112 | 2023-06-0219A, 2023-06-0212 | 2023-07-0090 | Timog Tirehuas Corporation | 2 Pieces - Battery 3SM Gold Motolite | [19 empty] | General Services | NO | Small Value Procurement | [5 empty] | 2023-07-17 |  | 2023-07-17 | [5 empty] | GAA | 19000 | 19000 |  | 18900 | 18900
6 | 113 | 2023-06-0214 | 2023-07-0092 | Halden General Merchandise | 1 Lot - Various Cleaning Supplies | [19 empty] | General Services | NO | Shopping 52.1B | [5 empty] | 2023-07-17 |  | 2023-07-17 | [5 empty] | GAA | 52450 | 52450 |  | 42410 | 42410
7 | 114 | 2023-07-0223 | 2023-07-0093 | CBCD Trading | 1 Unit - Dry Type Induction 5KVA Transformer | [19 empty] | Laoag | NO | Small Value Procurement | [5 empty] | 2023-07-17 |  | 2023-07-17 | [6 empty] | 48000 | 48000 |  | 47000 | 47000
8 | 115 | 2023-06-0191 | 2023-07-0094 | CBCD Trading | 1 Unit - USB Audio Interface 2 Mic Inputs 2 Line Inputs (6.35mm PL Port) 1 Headphone Output | [19 empty] | Engineering | NO | Small Value Procurement | [5 empty] | 2023-07-20 |  | 2023-07-20 | [5 empty] | GAA | 15000 | 15000 |  | 14900 | 14900
9 | 115A | 2023-07-0064 | 2023-07-0021B | ART JOHNLEY ENTERPRISES | 1 Lot - Installation of 1.5HP Split Type ACU @ RP1 Tech Room | [19 empty] | Engineering | NO | Small Value Procurement | [5 empty] | 2023-07-21 |  | 2023-07-21 | [5 empty] | GAA | 11550 | 11550 |  | 11550 | 11550
10 | 116 | 2023-07-0232 | 2023-07-0095 | J2 Tire Center | 2 Units - Tire 85R x 14C | [19 empty] | Baguio | NO | Small Value Procurement | [5 empty] | 2023-07-25 |  | 2023-07-25 | [5 empty] | GAA | 9800 | 9800 |  | 9800 | 9800
11 | 117 | 2023-07-0230 | 2023-07-0096 | Broadtech Corporation | 2 Boxes - Zebra White PVC Cards, 30ml, 500/Box, 1 Piece - Cleaning Kit for Zebra | [19 empty] | Personnel | NO | Small Value Procurement | [5 empty] | 2023-07-26 |  | 2023-07-26 | [5 empty] | GAA | 11200 | 11200 |  | 11200 | 11200
12 | 118 | 2023-07-0229 | 2023-07-0097 | CBCD Trading | 200 Feet - 7/8 Foam Type Transmission Cable | [19 empty] | Agoo | NO | Small Value Procurement | [5 empty] | 2023-07-28 |  | 2023-07-28 | [5 empty] | GAA | 45000 | 45000 |  | 44500 | 44500
13 | 119 | 2023-07-0053 | 2023-08-0022 | Frigid Zone Auto Aircon Specialist Co. | 1 Lot - Repair of Air-Conditioner of Sportivo SHX 567 | [19 empty] | General Services | NO | Small Value Procurement | [5 empty] | 2023-08-01 |  | 2023-08-01 | [5 empty] | GAA | 27500 | 27500 |  | 27500 | 27500
14 | 120 | 2023-05-0179 | 2023-08-0099 | Halden General Merchandise | 1 Unit - Edifier MR4 Powered Studio Monitor Speaker (Pair), 1 Unit - Desktop Monitor 21.5” | [19 empty] | Zamboanga | NO | Small Value Procurement | [5 empty] | 2023-08-01 |  | 2023-08-01 | [5 empty] | GAA | 14465 | 14465 |  | 14380 | 14380
15 | 121 | 2023-05-0169 | 2023-08-0098 | Halden General Merchandise | 1 Unit - AV Matrix UC 2018 SDI & HDMI to USB 3.0 | [19 empty] | Engineering | NO | Small Value Procurement | [5 empty] | 2023-08-01 |  | 2023-08-01 | [5 empty] | GAA | 17220 | 17220 |  | 16850 | 16850
16 | 122 | 2023-04-0117 | 2023-08-0100 | Halden General Merchandise | 1 Unit - Atem Mini Pro Live Stream Switcher HDMI for Video Editing Streaming, 1 Unit - 3M HDMI to HDMI Cable, 1 Unit - Micro HDMI to Standard HDMI Cable, 1 Unit - USB Audio Interface Sound Card | [19 empty] | RP-Magasin | NO | Small Value Procurement | [5 empty] | 2023-08-03 |  | 2023-08-03 | [5 empty] | GAA | 42000 | 42000 |  | 42000 | 42000
17 | 123 | 2023-05-0174 | 2023-08-0101 | Halden General Merchandise | 2 Units - Uninterruptible Power Supply 3KVA | [19 empty] | Engineering | NO | Small Value Procurement | [5 empty] | 2023-08-16 |  | 2023-08-16 | [5 empty] | GAA | 46000 | 46000 |  | 46000 | 46000
18 | 124 | 2023-06-0189, 2023-05-0167, 2023-03-0114B | 2023-08-0102 | L. Serrano Consumer Goods Trading | 4 Units - Production Swivel Chair, 2 Units - Announcer’s Chair Heavy Duty, 4 Units - Visitor’s Chair Heavy Duty. 1 Unit - Announcer’s Chair 1 Unit Chair, Swivel | [19 empty] | FM1 & RP-Worldwide | NO | Small Value Procurement | [5 empty] | 2023-08-11 |  | 2023-08-11 | [5 empty] | GAA | 79500 | 79500 |  | 62885.7 | 62885.7
19 | 125 | 2023-08-0245 | 2023-08-0103 |  | 4 Units - Announcer’s Chair, Heavy Duty, 8 Units - Visitor’s Chair, Heavy Duty,10 Units - Master Control Chair with Back Rest | [19 empty] | RP1-Manila | NO | Small Value Procurement | [5 empty] | 2023-08-17 |  | 2023-08-17 | [5 empty] | GAA | 143000 | 143000 |  | 115771.4 | 115771.4
20 | 126 | 2023-08-0262, 2023-08-0263 | 2023-08-0104 | Timog Tirehuas Corporation | 1 Unit - Battery, NS60ZK, B24R, 1 Unit - 6SM N100 Truckmaster LM | [19 empty] | General Services, Engineering | NO | Small Value Procurement | [5 empty] | 2023-08-24 |  | 2023-08-24 | [5 empty] | GAA | 19500 | 19500 |  | 19500 | 19500
21 | 127 | 2023-06-0051E | 2023-06-0021B | Geomar Airconditioning Works and Sales, Inc. | 1 Lot - Repair of 5TR Daikin Ceiling Cassette Type Aircon at the office of Radyo Pilipinas – Iloilo (Motor Compressor, Labor and Materials and VAT) | [19 empty] | Iloilo | NO | Small Value Procurement | [5 empty] | 2023-08-24 |  | 2023-08-23 | [5 empty] | GAA | 26320 | 26320 |  | 26320 | 26320
22 | 128 | 2023-07-0241 | 2023-09-0105 | Sagittarius Hardware Trading | 3 Units - Announcer’s Headset (Professional Monitor) Shure Brand | [19 empty] | FM1 | NO | Small Value Procurement | [5 empty] | 2023-09-05 |  | 2023-09-05 | [5 empty] | GAA | 75000 | 75000 |  | 43500 | 43500
23 | 128A | 2023-07-0236 | 2023-09-0111 | Vistaaire Builders and Airconfitioning Sales and Services | 1 Unit - Copeland Scroll Compressor, 2 Pieces - Mapp Gas, 1 Piece - Mapp Torch Dual Nozzle/Dual Tip with Igniter, 10 Pieces - Siver Rod 2 Pieces - Copper Coupling 1 1/8, with labor | [19 empty] | Engineering | NO | Small Value Procurement | [5 empty] | 2023-09-06 |  | 2023-09-06 | [5 empty] | GAA | 90100 | 90100 |  | 87540 | 87540
24 | 129 | 2023-04-0129 | 2023-09-0106 | CBCD Trading | 1 Unit - Portable Power Station , 1 Unit - 220W Bifacial Portable Solar Panel | [19 empty] | Engineering | NO | Small Value Procurement | [5 empty] | 2023-09-09 |  | 2023-09-09 | [5 empty] | GAA | 79000 | 79000 |  | 77000 | 77000
25 | 130 | 2023-08-0069 | 2023-09-0074 | Frigid Zone Auto Aircon Specialist Co. | 1 Unit - Replacement of Auxilliary Motor | [19 empty] | General Services | NO | Small Value Procurement | [5 empty] | 2023-09-18 |  | 2023-09-18 | [5 empty] | GAA | 8600 | 8600 |  | 7500 | 7500
26 | 131 | 2023-08-0265 | 2023-09-0107 | Sagittarius Hardware Trading | 2 Unit - Fuji SC-N2 Magnetic Contactor 3 Pole 220V 40A 60Hz | [19 empty] | Engineering | NO | Small Value Procurement | [5 empty] | 2023-09-15 |  | 2023-09-15 | [5 empty] | GAA | 13000 | 13000 |  | 12200 | 12200
27 | 132 | 2023-08-0271 | 2023-09-0109 | Sagittarius Hardware Trading | 100 Pieces - T8 LED Tube Light 18W 4FT Industrial Day Light (Double Ended) 1 Year Warranty | [19 empty] | Engineering | NO | Small Value Procurement | [5 empty] | 2023-09-15 |  | 2023-09-15 | [5 empty] | GAA | 30000 | 30000 |  | 28800 | 28800
28 | 133 | 2023-08-0256 | 2023-09-0108 | Halden General Merchandise | 3 Units - 1500VA Uninterruptible Power Supply | [19 empty] | Engineering | NO | Small Value Procurement | [5 empty] | 2023-09-14 |  | 2023-09-14 | [5 empty] | GAA | 15960 | 15960 |  | 15960 | 15960
29 | 134 | 2023-08-0272 | 2023-09-0110 | CBCD Trading | 1 Unit - Telescopic Hot Disconnect Stick (5 Sections, 25 Feet) Brand-New, 1 Pair - 12KV High Voltage Electrical Insulating Gloves Safety Leakage Prevention Anti-Electrical Rubber Gloves, 1 Pair - High-Cut Safety Rubber Boots (Black) | [19 empty] | Engineering | NO | Small Value Procurement | [5 empty] | 2023-09-20 |  | 2023-09-20 | [5 empty] | GAA | 49500 | 49500 |  | 49500 | 49500
30 | 135 | 2023-09-0076 | 2023-09-0033 | MODERN Refrigeration & Airconditioning Services | 1 Lot Pump-down, Relocation/Reinstallation | [19 empty] | Cagayan de Oro | NO | Small Value Procurement | [5 empty] | 2023-09-20 |  | 2023-09-20 | [5 empty] | GAA | 21504 | 21504 |  | 21504 | 21504
31 | 136 | 2023-09-0274 | 2023-09-0112 | Halden General Merchandise | 2 Pieces - Automatic Door Closer, 4 Pieces - 4 x 1.5in. Door Hinge | [19 empty] | Engineering | NO | Small Value Procurement | [5 empty] | 2023-09-22 |  | 2023-09-22 | [5 empty] | GAA | 10000 | 10000 |  | 9740 | 9740
32 | 137 | 2023-09-0276 | 2023-10-0113 | ART JOHNLEY ENTERPRISES | 1 Unit - 1.5HP Split Type Wall Mounted inverter Air-Conditioning Unit | [19 empty] | FM1 | NO | Small Value Procurement | [5 empty] | 2023-10-03 |  | 2023-10-03 | [5 empty] | GAA | 49000 | 49000 |  | 36500 | 36500
33 | 138 | 2023-09-0282 | 2023-10-0114 | Sagittarius Hardware Trading | 1 Unit - Condensing Fan Motor, ½ HP Single Shaft, 825 RPM, 12mFD Capacitor 370VAC, 220 V, 60Hz | [19 empty] | Engineering | NO | Small Value Procurement | [5 empty] | 2023-10-04 |  | 2023-10-04 | [5 empty] | GAA | 8500 | 8500 |  | 8500 | 8500
34 | 139 | 2023-09-0295 | 2023-10-0115 | All Batteries and Motor Parts Sales, Inc. | 1 Piece - Battery, Motolite 2SMF 12v | [19 empty] | Cebu | NO | Small Value Procurement | [5 empty] | 2023-10-05 |  | 2023-10-05 | [5 empty] | GAA | 7672 | 7672 |  | 7672 | 7672
35 | 140 | 2023-08-0066 | 2023-10-0025 | CBCD Trading | 1 Unit - Overhauling, Re-Insulation, Rewinding of 5KVA Transformer from Delta to Wye Configuration (Secondary Side) PBS-BBS RP-Agoo | [19 empty] | Agoo | NO | Small Value Procurement | [5 empty] | 2023-10-06 |  | 2023-10-06 | [5 empty] | GAA | 14000 | 14000 |  | 13800 | 13800
36 | 141 | 2023-09-0079 | 2023-10-0024 | CBCD Trading | 1 Lot - Overhauling, Re-Insulation, Rewinding, of 120KVA Transformer, 440 Primary, 440 Secondary, Delta-Delta | [19 empty] | Engineering | NO | Small Value Procurement | [5 empty] | 2023-10-06 |  | 2023-10-06 | [5 empty] | GAA | 150000 | 150000 |  | 147600 | 147600
37 | 142 | 2023-09-0280 | 2023-10-0117 | Sagittarius Hardware Trading | 5 Units - Kingston 250GB NVME PCIE M2 SSD | [19 empty] | FM1 | NO | Small Value Procurement | [5 empty] | 2023-10-13 |  | 2023-10-13 | [5 empty] | GAA | 12500 | 12500 |  | 11000 | 11000
38 | 143 | 2023-09-0282 | 2023-10-0116 | Sagittarius Hardware Trading | 1 Unit - Condensing Fan Motor, ½ HP Single Shaft, 825 RPM, 12mFD Capacitor 370VAC, 220 V, 60Hz | [19 empty] | Engineering | NO | Small Value Procurement | [5 empty] | 2023-10-13 |  | 2023-10-13 | [5 empty] | GAA | 8500 | 8500 |  | 8500 | 8500
39 | 144 | 2023-10-0369 | 2023-10-0118 | Halden General Merchandise | 1 Lot - Various Office Supplies | [19 empty] | COA | NO | Shopping 52.1B | [5 empty] | 2023-11-03 |  | 2023-10-27 | [5 empty] | GAA | 8800 | 8800 |  | 8110 | 8110
40 | 145 | 2023-10-0311 | 2023-11-0119 | Great Country Auto Supply | 2 Sets - Clutch Assembly for Toyota Avanza | [19 empty] | General Services | NO | Small Value Procurement | [5 empty] | 2023-11-03 |  | 2023-11-03 | [5 empty] | GAA | 17500 | 17500 |  | 14400 | 14400
41 | 146 | 2023-11-0071 | 2023-11-0096 | ART JOHNLEY ENTERPRISES | 1 Lot - Installation of 1.5HP Split Type ACU @ FM2 Booth | [19 empty] | Engineering | NO | Emergency Cases | [5 empty] | 2023-11-14 |  | 2023-11-14 | [5 empty] | GAA | 20000 | 20000 |  | 20000 | 20000
42 | 147 | 2023-10-0300 | 2023-11-0120 | Halden General Merchandise | 1 Lot - Various Office Cleaning Supplies | [19 empty] | General Services | NO | Shopping 52.1B | [5 empty] | 2023-11-17 |  | 2023-11-17 | [5 empty] | GAA | 72900 | 72900 |  | 54990 | 54990
43 | 148 | 2023-11-0316 | 2023-11-0121 | Vistaaire Builders and Airconfitioning Sales and Services | 1 Unit - Expansion Valve for 7.5 TR Capacity R-22 Flare Type | [19 empty] | Engineering | NO | Small Value Procurement | [5 empty] | 2023-11-22 |  | 2023-11-22 | [5 empty] | GAA | 9000 | 9000 |  | 9000 | 9000
44 | 149 | 2023-09-0297C | 2023-11-0122 | Seguro Marketing, Inc. | 1 Unit - Battery, 2SMF 12v Motolite | [19 empty] | Cebu | NO | Small Value Procurement | [5 empty] | 2023-11-23 |  | 2023-11-23 | [5 empty] | GAA | 7430 | 7430 |  | 7430 | 7430
45 | 150 | 2023-10-0311D |  | CBCD Trading | 1 Lot - Supply and Delivery of Information System Strategic Plan (ISSP) Various ICT Software | [19 empty] | Engineering | YES | Competitve Bidding | 2023-10-24 | 2023-10-26 | 2023-11-07 | 2023-11-21 | 2023-11-21 | 2023-11-24 | 2023-11-28 | 2023-11-29 | 2023-12-21 | 2023-12-29 | 2023-12-29 | on-going |  | GAA | 2050000 |  | 2050000 | 2021180 |  | 2021180 | Mr. Crisanto Frianeza,, Secretary-General of Philippine Chamber of Commerce and Industry, Mr. Amador Astudillo, President of Procurement Watch and Ms. Estrellita Aguilar, BBS of the Commission on Audit | 2023-11-07 | 2023-11-21 | 2023-11-21 | 2023-11-24 | 2023-11-28 | on-going
46 | 151 | 2023-10-0093 | 2023-11-0027 | Best Choice Gourmet & Catering Services | 300 Psx - Meals for BBS GAD Year-End Assessment on December 14, 2023 (Lunch and PM Snacks) | [19 empty] | GAD |  | Small Value Procurement | [5 empty] | 2023-11-29 |  | 2023-11-29 | [5 empty] | GAA | 180000 | 180000 |  | 180000 | 180000
47 | 152 | 2023-10-0311J |  | 168 Security, Inc. | 1 Lot - Contract for the Provision of Security Agency Services for twelve (12) months - Sixty-Three (63) Security Guards | [19 empty] | Administrative | YES | Competitve Bidding | 2023-10-11 | 2023-10-26 | 2023-11-07 | 2023-11-21 | 2023-11-21 | 2023-11-24 | 2023-11-29 | 2023-11-30 | 2023-12-21 | 2023-12-29 | 1933-12-29 | on-going |  | GAA | 27100000 | 27100000 |  | 27092989.91 | 27092989.91 |  | Mr. Crisanto Frianeza,, Secretary-General of Philippine Chamber of Commerce and Industry, Mr. Amador Astudillo, President of Procurement Watch and Ms. Estrellita Aguilar, BBS of the Commission on Audit | 2023-11-07 | 2023-11-21 | 2023-11-21 | 2023-11-24 | 2023-11-29 | on-going
48 | 153 | 2023-11-0321 | 2023-11-0124 | Metos Offshore, Inc, | 35 Pieces - N-Channel Mosfet 350A, 75V, 3-PIN TO 247AC Infineon IRFP4368PBF 7 Pieces - Eaton 30A F Melamine Cartridge Fuse 10 x 38NN | [19 empty] | Rngineering | NO | Small Value Procurement | [5 empty] | 2023-11-29 |  | 2023-11-29 | [5 empty] | GAA | 70000 | 70000 |  | 55392.05 | 55392.05
49 | 154 | 2023-10-0093B | 2023-11-0028 | CBCD Trading | 1 Lot - Supply of Labor and Parts for the Rehabilitation of 400a 3 Phase MCCB Type Automatic Transfer Switch include pull-out and delivery @ Site PNS Visayas Avenue, Quezon City | [19 empty] | Engineering | NO | Small Value Procurement | [5 empty] | 2023-11-29 |  | 2023-11-29 | [5 empty] | GAA | 45000 | 45000 |  | 44800 | 44800
50 | 155 | 2023-11-0323 | 2023-11-0125 | Imperial Appliance Plaza | 1 Unit - Television Set, 55" TCL 4k HDR | [19 empty] | Davao | NO | Small Value Procurement | [5 empty] | 2023-11-29 |  | 2023-11-29 | [5 empty] | GAA | 25488 | 25488 |  | 25488 | 25488
51 | 156 | 2023-11-0322 | 2023-12-0127 | FIL-OZ COMMZ DPC | 1 Lot - Android APPS for PBS Audio Streaming (5Streams) RP1, RP2, RP3, FM1, FM2 | [19 empty] | Engineering | NO | Small Value Procurement | [5 empty] | 2023-12-29 |  | 2023-12-29 | 2023-12-29 |  |  |  |  | GAA | 44000 | 44000 |  | 43600 | 43600
Total Alloted Budget of Procurement Activities | [41 empty] | 31815479
Total Contract Price of Procurement Actitvites Conducted | [44 empty] | 31618713.06
Total Savings (Total Alloted Budget - Total Contract Price) | [41 empty] | 196765.94
.
0N-GOING PROCUREMENT ACTIVITIES
0
0
0
0
Total Alloted Budget of On-going Procurement Activities | [41 empty] | 0
[25 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | Approved:
[25 empty] | RODNEY O. VILLANUEVA | [10 empty] | ALAN L. ALLANIGUE | [10 empty] | RIZAL GIOVANNI P. APROTADERA, JR.
[25 empty] | BAC Secretariat Head | [10 empty] | BAC Chairperson | [10 empty] | Director IV
Head of the Procuring Entity

## Sheet2
49000 | 49000 | 49000 | 49000
8775 | 8775 | 8775 | 8775
10000 | 10000 | 9975 | 9975
6305 | 6305 | 6305 | 6305
20400 | 20400 | 19500 | 19500
9004 | 9004 | 8385 | 8385
5700 | 5700 | 5700 | 5700
9850 | 9850 | 9850 | 9850
15500 | 15500 | 15500 | 15500
5200 | 5200 | 5200 | 5200
6500 | 6500 | 6500 | 6500
34000 | 34000 | 33300 | 33300
79500 | 79500 | 79500 | 79500
15900 | 15900 | 13650 | 13650
8000 | 8000 | 7950 | 7950
310050 | 310050 | 230345 | 230345
5700 | 5700 | 5700 | 5700
14400 | 14400 | 12295 | 12295
11860 | 11860 | 9635 | 9635
65340 | 65340 | 64350 | 64350
23000 | 23000 | 23000 | 23000
84000 | 84000 | 82556 | 82556
26765 | 26765 | 26765 | 26765
36000 | 36000 | 34000 | 34000
50000 | 50000 | 37500 | 37500
188475 | 188475 | 188475 | 188475
60620 | 60620 | 60620 | 60620
13000 | 13000 | 13000 | 13000
6800 | 6800 | 6800 | 6800
37386 | 37386 | 36060 | 36060
55500 | 55500 | 39900 | 39900
75500 | 75500 | 73920 | 73920
16000 | 16000 | 15800 | 15800
36900 | 36900 | 36860 | 36860
97400 | 97400 | 97400 | 97400
29400 | 29400 | 29400 | 29400
17000 | 17000 | 16500 | 16500
60000 | 60000 | 38990 | 38990
9000 | 9000 | 8700 | 8700
49000 | 49000 | 45000 | 45000
11567.56 | 11567.56 | 9500 | 9500
5500 | 5500 | 5500 | 5500
23000 | 23000 | 23000 | 23000
30540 | 30540 | 30540 | 30540
432000 | 432000 | 432000 | 432000
8670 | 8670 | 8670 | 8670
48000 | 48000 | 48000 | 48000
9500 | 9500 | 9500 | 9500
13000 | 13000 | 13000 | 13000
36730 | 36730 | 36730 | 36730
77828 | 77828 | 77570.08 | 77570.08
6443 | 6443 | 6443 | 6443
3600 | 3600 | 3600 | 3600
11760 | 11760 | 11760 | 11760
9800 | 9800 | 9800 | 9800
18000 | 18000 | 17800 | 17800
7950 | 7950 | 7650 | 7650
112000 | 112000 | 112000 | 112000
5600 | 5600 | 5600 | 5600
7523.65 | 7523.65 | 7450 | 7450
10000 | 10000 | 7990 | 7990
13995 | 13995 | 13995 | 13995
10000 | 10000 | 9000 | 9000
6734 | 6734 | 6540 | 6540
59000 | 59000 | 56998 | 56998
38880 | 38880 | 32420 | 32420
7599 | 7599 | 7450 | 7450
24000 | 24000 | 21600 | 21600
45000 | 45000 | 43899 | 43899
10300 | 10300 | 10280 | 10280
8450 | 8450 | 6145 | 6145
16000 | 16000 | 15900 | 15900
10600 | 10600 | 9100 | 9100
10000 | 10000 | 10000 | 10000
23430 | 23430 | 22160 | 22160
19600 | 19600 | 19600 | 19600
12280 | 12280 | 12280 | 12280
6400 | 6400 | 6400 | 6400
49995 | 49995 | 41999 | 41999
137100 | 137100 | 105451 | 105451
9450 | 9450 | 9450 | 9450
28190 | 28190 | 28190 | 28190
8690 | 8690 | 8690 | 8690
17000 | 17000 | 16000 | 16000
12280 | 12280 | 12280 | 12280
22230 | 22230 | 22230 | 22230
26300 | 26300 | 26300 | 26300
42250 | 42250 | 42250 | 42250
7534 | 7534 | 7534 | 7534
39600 | 39600 | 39600 | 39600
13185 | 13185 | 13185 | 13185
15697 | 15697 | 15697 | 15697
8200 | 8200 | 8200 | 8200
9500 | 9500 | 9500 | 9500
17296.2 | 17296.2 | 17220 | 17220
11000 | 11000 | 11000 | 11000
20000 | 20000 | 19800 | 19800
36700 | 36700 | 36700 | 36700
12000 | 12000 | 9600 | 9600
194000 | 194000 | 193200 | 193200
150000 | 150000 | 99995 | 99995
73990 | 73990 | 73990 | 73990
3550 | 3550 | 3550 | 3550
17400 | 17400 | 17400 | 17400
29490 | 29490 | 27800 | 27800
26835 | 26835 | 26800 | 26800
9000 | 9000 | 8900 | 8900
118550 | 118550 | 89090 | 89090
15550 | 15550 | 15100 | 15100 | 450 | Savings | as of June 27, 2023
45500 | 45500 | 44500 | 44500
122000 | 122000 | 85000 | 85000
37800 | 37800 | 37035 | 37035
4261872.41 | 4261872.41 | 3923767.08 | 3923767.08

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement