## pmr
[6 empty] | ANNEX A | [18 empty] | ANNEX B
[6 empty] | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | Bureau of Broadcast Services Procurement Monitoring Report as of June 30, 2024
Code (PAP) |  |  |  |  | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
[8 empty] | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| 1 | 2023-11-0320 |  |  | 3 Units - Solid State Drive 500GB NVME, 6 Units - Random Access Memory (RAM), 1 Unit -External Hard Drive 1TB 5400RPM | [19 empty] | News | NO | Small Value Procurement |  | 2024-01-02 | [5 empty] | 2024-01-02 | 2024-01-02 | 2024-01-03 |  |  |  | GAA | 33550 | 33550 |  | 23905 | 23905
| 2 | 2023-12-0327 | 2924-01-0003 | Timog Tirehaus Corporation | 4 Pieces - Tire 215 / 70R 16 | [19 empty] | General Services | NO | Small Value Procurement |  | 2024-01-03 | [5 empty] | 2024-01-03 | 2024-01-03 |  |  |  |  | GAA | 42000 | 42000 |  | 33000 | 33000
| 3 | 2023-12-0100 | 2024-01-0001 | Data Images Plus Automation, Phils, Inc. | 1 Lot - Lease of eight (8) units Multi-Functional Photocopying Machine (Digital Copier, Network Printer, Scanner) | [19 empty] | Finance Division | NO | Small Value Procurement |  | 2023-12-28 | [5 empty] | 2023-01-08 | 2024-01-08 |  |  |  |  | GAA | 346500 | 346500 |  | 235200 | 235200
| 4 | 2024-01-0007 | 2024-01-0004 | Timog Tirehaus Corporation | 1 Piece - Battery NS60ZS Motolite Gold, 1 Piece - Battery 3SM Reverse Motolite | [19 empty] | General Services | NO | Small Value Procurement |  | 2024-01-09 | [5 empty] | 2024-01-11 | 2024-01-11 |  |  |  |  | GAA | 18100 | 18100 |  | 17900 | 17900
| 5 | 2024-01-0026 | 2024-01-0006 | Sagittarius Hardware Trading | 3 Pieces - Alphalux Broad Beam Series LED SMD Flood Light, 50W, IP65 | [19 empty] | General Services | NO | Small Value Procurement |  | 2024-01-23 | [5 empty] | 2024-01-24 | 2024-01-24 |  |  |  |  | GAA | 7500 | 7500 |  | 7500 | 7500
| 6 | 2024-01-0019 | 2024-01-0007 | Halden General Merchandise | 2 Units - EF 16S Industrial Exhaust Fan, 16 Inches | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-01-22 | [5 empty] | 2024-01-25 | 2024-01-25 |  |  |  |  | GAA | 15000 | 15000 |  | 12000 | 12000
| 7 | 2024-01-0014 | 2024-01-0008 | Luzon Sales, Co. Inc. | 1 Lot - Various Materials for the Repainting of Walls | [19 empty] | Finance Division | NO | Small Value Procurement |  | 2024-01-23 | [5 empty] | 2024-01-25 | 2024-01-25 |  |  |  |  | GAA | 32670 | 32670 |  | 30546 | 30546
| 8 | 2024-01-0001 | 2024-01-0002 | Frigid Zone Auto Aircon Sepcialist Co. | 1 Lot - Repair of Air-conditioner of Toyota Avanza SAB 6357 | [19 empty] | General Services | NO | Small Value Procurement |  | 2024-01-23 | [5 empty] | 2024-01-26 | 2024-01-26 |  |  |  |  | GAA | 12000 | 12000 |  | 12000 | 12000
| 8A | 2024-01-0004 | 2024-01-0006 | Philippine Global Communication, Inc. | 1 Lot - 100 Mbps Monthly Subscription of Dedicated Enterprise Internet Plan with Unlimited Data (Period of January 01, 2024 to December 31, 2024) | [19 empty] | Engineering | NO | (GPPB) Resolution No. 41-2017 |  | 2024-01-15 | [5 empty] | 2024-01-15 | 2024-01-15 |  |  |  |  | GAA | 432000 | 432000 |  | 432000 | 432000
| 9 | 2024-01-0006 | 2024-01-0005 | A7 Enterprises, Inc. | 1 Lot - Various Office Cleaning Supplies | [19 empty] | General Services | NO | Shopping 52.1B |  | 2024-01-17 | [5 empty] | 2024-01-22 | 2024-01-22 |  |  |  |  | GAA | 60850 | 60850 |  | 47190 | 47190
| 10 | 2024-01-0027 | 2024-01-0009 | Varyline Corporation | 1 Lot - Various Office Supplies | [19 empty] | Supply & Property Section | NO | Shopping 52.1B | [7 empty] | 2024-01-31 | 2024-01-31 |  |  |  |  | GAA | 447400 | 447400 |  | 341320 | 341320
| 11 | 2024-02-0039 | 2024-02-0010 | Dataview Computer Corporation | 1 Box - Belden CAT5E Cable | [19 empty] | Proporty & Supply | NO | Small Value Procurement |  | 2024-01-26 | [5 empty] | 2024-02-07 | 2024-02-07 |  |  |  |  | GAA | 8500 | 8500 |  | 7500 | 7500
| 12 | 2024-01-0018 | 2024-02-0011 | New A.G. Stylist Furniture | 5 Units - Chair, Executive with Headrest, 8 Units - Table, Clerical with Mobile Cabinet | [19 empty] | Administrative | NO | Small Value Procurement |  | 2024-02-05 | [5 empty] | 2024-02-07 | 2024-02-07 |  |  |  |  | GAA | 82500 | 82500 |  | 79100 | 79100
| 13 | 2024-01-0029 | 2024-02-0012 | Bruno Glenn's Vulcanizing & Tire Supply | 4 Pieces - Tire, 195 R 14 Goodyear | [19 empty] | RP-Tabuk | NO | Small Value Procurement |  | 2024-01-31 | [5 empty] | 2024-02-08 | 2024-02-08 |  |  |  |  | GAA | 20800 | 20800 |  | 20800 | 20800
| 14 | 2024-01-0024 | 2024-02-0013 | Sagittarius Hardware Trading | 1 Unit - Condensing Fan Motor | [19 empty] | RP2-Sports | NO | Small Value Procurement |  | 2024-02-08 | [5 empty] | 2024-02-14 | 2024-02-14 |  |  |  |  | GAA | 8500 | 8500 |  | 8500 | 8500
| 15 | 2024-01-0002 | 2024-02-0003 | CBCD Trading | 1 Lot - Supply, Delivery and Installation of 12VDC, 10 Amp. Automatic Battery Charger (Tickle Type) for 225KVA Cummins Generator Set | [19 empty] | Engineering |  | Small Value Procurement |  | 2024-01-29 | [5 empty] | 2024-02-13 | 2024-02-13 |  |  |  |  | GAA | 16000 | 16000 |  | 15900 | 15900
| 16 | 2024-01-0003 | 2024-02-0004 | CBCD Trading | 1 Lot - Preventive Maintenance of 225KVA Cummins Generator Set (Central) | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-01-31 | [5 empty] | 2024-02-13 | 2024-02-13 |  |  |  |  | GAA | 45000 | 45000 |  | 44900 | 44900
| 17 | 2024-01-0020 | 2024-02-0016 | Art Johnley Enterprises | 1 Unit - 2.0 HP Window Type Aircon Non-Inverter Side Discharge, Model No. WCARJ019EE | [19 empty] | Engineering |  | Small Value Procurement |  | 2024-01-29 | [5 empty] | 2024-02-16 | 2024-02-16 |  |  |  |  | GAA | 43355 | 43355 |  | 43355 | 43355
| 18 | 2024-01-0007 | 2024-02-0005 | Ford Quezon Avenue | 1 Unit - Vehicle Repair Ford Wildtrack SAB-8174 | [19 empty] | General Services |  | Small Value Procurement |  | 2024-02-14 | [5 empty] | 2024-02-16 | 2024-02-15 |  |  |  |  | GAA | 16000 | 16000 |  | 16000 | 16000
| 19 | 2024-02-0045 | 2024-02-0015 | Great Country Auto Supply | 1 Piece - Intercooler Assembly | [19 empty] | General Services |  | Small Value Procurement |  | 2024-02-13 | [5 empty] | 2024-02-22 | 2024-02-24 |  |  |  |  | GAA | 11000 | 11000 |  | 10000 | 10000
| 20 | 2024-01-0037D | 2024-02-0016 | Better Component Incorporated | 1 Unit - AVR, 5KVA ADI SVC-5000VA | [19 empty] | RP-Davao |  | Small Value Procurement |  | 2024-01-22 | [5 empty] | 2024-02-22 | 2024-02-22 |  |  |  |  | GAA | 19000 | 19000 |  | 19000 | 19000
| 21 | 2924-02-0002 | 2024-01-0002B | Medrise International OPC | 531 Sets - Go Bag Kit with Contenet and Hard Hat | [19 empty] | GAD |  | Small Value Procurement |  | 2024-02-19 | [5 empty] | 2024-02-22 | 2024-02-22 |  |  |  |  | GAA | 531000 | 531000 |  | 371700 | 371700
| 22 | 2024-02-0056 | 2024-03-0018 | Timog Tirehaus Corporation | 1 Unit - Battery, DIN66H | [19 empty] | General Services | NO | Small Value Procurement |  | 2024-02-22 | [5 empty] | 2024-03-01 | 2024-03-01 |  |  |  |  | GAA | 12500 | 12500 |  | 12450 | 12450
| 23 | 2024-02-0054 | 2024-02-0022 | Luzon Sales, Co. Inc. | 1 Lot - Materials for the Installation of Water System at Marulas Transmitter Site | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-02-06 | [5 empty] | 2024-03-01 | 2024-03-01 |  |  |  |  | GAA | 43650 | 43650 |  | 28950 | 28950
| 24 | 2024-02-0069 | 2024-03-0021 | CBCD Trading | 1 Unit - RVR 1000PA Power Supply Interface Board | [19 empty] | RP-Tawi-Tawi | NO | Small Value Procurement |  | 2024-02-09 | [5 empty] | 2024-03-01 | 2024-03-01 |  |  |  |  | GAA | 16800 | 16800 |  | 16700 | 16700
| 25 | 2024-02-0060 | 2024-03-0020 | CBCD Trading | 2 Units - 9GV Series Axial Fan, 24 VCD 234.5m3/h, 38.4w, 1.6A Max 80 x 80 x 38mm | [19 empty] | RP-Tawi-Tawi | NO | Small Value Procurement |  | 2024-02-09 | [5 empty] | 2024-03-01 | 2024-03-01 |  |  |  |  | GAA | 9000 | 9000 |  | 8900 | 8900
| 26 | 2024-02-0014 | 2024-03-0006 | RJD Media Advertising | 1 Unit - Supply and Delivery with Installation of 2.60m width x 1.40m Height / 102.36in. W x 55.12in. H Vinyl Sticker (Matte) | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-02-21 | [5 empty] | 2024-03-04 | 2024-03-04 |  |  |  |  | GAA | 13904 | 13904 |  | 13904 | 13904
| 27 | 2024-02-0076 | 2024-03-0019 | Dataview Computer Corporation | 3 Pieces - 1TB External Hard Drive, Gen 3 | [19 empty] | Research | NO | Small Value Procurement |  | 2024-02-29 | [5 empty] | 2024-03-01 | 2024-03-01 |  |  |  |  | GAA | 12000 | 12000 |  | 10350 | 10350
| 28 | 2024-02-00083 | 2024-03-0023 | Homestyle Depot | 1 Unit - 2 Stroke, Lawn Mower | [19 empty] | RP-Zamboanga | NO | Small Value Procurement |  | 2024-02-12 | [5 empty] | 2024-03-04 | 2024-03-04 |  |  |  |  | GAA | 9494 | 9494 |  | 9494 | 9494
| 29 | 2024-03-0066 | 2024-03-0024 | Sagittarius Hardware Trading | 1 Unit - Transparent Acrylic Clear Bid Box with Awning Cover and Lock | [19 empty] | BAC | NO | Small Value Procurement |  | 2024-02-29 | [5 empty] | 2024-03-07 | 2024-03-07 |  |  |  |  | GAA | 6300 | 6300 |  | 6300 | 6300
| 30 | 2024-02-0069 | 2024-03-0025 | 16/35mm Production Supply | 1 Unit - 75-inch LED TV | [19 empty] | Engineering | NO | Small Value Procurement | [7 empty] | 2024-03-06 | 2024-03-06 |  |  |  |  | GAA | 79000 | 79000 |  | 53800 | 53800
| 31 | 2024-02-0007B | 2024-03-0007 | Modern Refrigeration and Airconditioning Services | 1 Unit - 3 Tons Koppel Inverter Floor AC for Replacement of Outdoor PCB Main Assy and Outdoor Diode for DXIM Radyo Pilipinas – Cagayan de Oro (Labor Included) | [19 empty] | RP-Cagayan de oro | NO | Small Value Procurement |  | 2024-02-04 | [5 empty] | 2024-03-11 | 2024-03-11 |  |  |  |  | GAA | 13100 | 13100 |  | 13100 | 13100
| 32 | 2024-02-0068 | 2024-03-0027 | Luzon Sales, Co. Inc. | 1 Lot - Materials for RP1 Ducting Repair and Lighting Relocation | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-02-19 | [5 empty] | 2024-03-13 | 2024-03-13 |  |  |  |  | GAA | 7850 | 7850 |  | 7195 | 7195
| 33 | 2024-03-0095 | 2024-03-0028 | Timog Tirehaus Corporation | 1 Unit - Battery N6S60ZS | [19 empty] | General Services | NO | Small Value Procurement |  | 2024-03-14 | [5 empty] | 2024-03-18 | 2024-03-18 |  |  |  |  | GAA | 8500 | 8500 |  | 8400 | 8400
| 34 | 2024-03-0099 | 2024-03-0032 | Halden General Merchandise | 1 Unit - 43” Full HD Digital Smart TV | [19 empty] | RP2-Sports | NO | Small Value Procurement |  | 2024-03-06 | [5 empty] | 2024-03-20 | 2024-03-20 |  |  |  |  | GAA | 21000 | 21000 |  | 19280 | 19280
| 35 | 2024-02-0043 | 2024-03-0033 | Luzon Sales, Co. Inc. | 1 Lot - Materials for the Installation of Finance Glass Panel and Door | [19 empty] | Finance | NO | Small Value Procurement |  | 2024-02-06 | [5 empty] | 2024-03-20 | 2024-03-20 |  |  |  |  | GAA | 5290 | 5290 |  | 5128 | 5128
| 36 | 2024-03-0094 | 2024-03-0030 | Timog Tirehaus Corporation | 4 Units - Tire, 205/65 R 16 | [19 empty] | General Services | NO | Small Value Procurement |  | 2024-03-14 | [5 empty] | 2024-03-21 | 2024-03-21 |  |  |  |  | GAA | 34000 | 34000 |  | 33000 | 33000
| 37 | 2024-02-0070 | 2024-03-0029 | CBCD Trading | 15 Meters - Exhibition Carpet 2m Width (Gray) | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-02-21 | [5 empty] | 2024-03-21 | 2024-03-21 |  |  |  |  | GAA | 7500 | 7500 |  | 7500 | 7500
| 38 | 2024-02-0079 | 2024-03-0034 | Dataview Computer Corporation | 1 Unit - 8GB RTX 3050 GDDRG 128 BIT Video Card | [19 empty] | RP-Alert | NO | Small Value Procurement |  | 2024-03-06 | [5 empty] | 2024-03-21 | 2024-03-21 |  |  |  |  | GAA | 17000 | 17000 |  | 17000 | 17000
| 39 | 2024-03-0016 | 2024-03-0008 | JACED Construction | 1 Lot - Supply, Delivery and Renovation of RP1-Studio Booth | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-03-05 | [5 empty] | 2024-03-20 | 2024-03-20 |  |  |  |  | GAA | 118242.72 | 118242.72 |  | 108950 | 108950
| 40 | 2024-02-0075 | 2024-03-0031 | CBCD Trading | 6 Cans - 3M Super 77 Classic Adhesive Spray | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-02-21 | [5 empty] | 2024-03-20 | 2024-03-20 |  |  |  |  | GAA | 7080 | 7080 |  | 7080 | 7080
| 41 | 2024-02-0083B | 2024-04-0035 | Wi-Al Construcrion Builders | 1 Lot - Materials for the Repair of Gate, Roof and Fences | [19 empty] | RP-Baguio | NO | Small Value Procurement |  | 2024-04-02 | [5 empty] | 2024-04-03 | 2024-04-03 |  |  |  |  | GAA | 36685 | 36685 |  | 36685 | 36685
| 42 | 2024-01-0037H | 2024-04-0034 | Prime Autoparts Sales and Services | 5 Pieces - Tires (185 R14 GT Radial) | [19 empty] | RP-Tuguegarao | NO | Small Value Procurement |  | 2024-01-29 | [5 empty] | 2024-04-08 | 2024-04-08 |  |  |  |  | GAA | 24200 | 24200 |  | 24200 | 24200
| 43 | 2024-01-0037G | 2024-04-0037 | Infoworx Inc. | 1 Unit - Computer LED Monitor 21.5 AOC | [19 empty] | RP-Naga | NO | Small Value Procurement |  | 2024-01-25 | [5 empty] | 2024-04-08 | 2024-04-08 |  |  |  |  | GAA | 4300 | 4300 |  | 4300 | 4300
| 44 | 2024-01-00367F | 2024-04-0038 | ABANA Computer Services & General Merchandise | 1 Unit - Epson Printer L121 | [19 empty] | RP-Tuguegarao | NO | Shopping 52.1B |  | 2024-01-29 | [5 empty] | 2024-01-08 | 2024-01-08 |  |  |  |  | GAA | 5495 | 5495 |  | 5495 | 5495
| 45 | 2024-02-0007C | 2024-04-0009 | JPX GLASS ALUMINUM AND HARDWARE | 1 Lot - Repair and Replacement of Overhead Door Closer (Studio Main Glass Door) | [19 empty] | RP-Palawan | NO | Small Value Procurement |  | 2024-02-29 | [5 empty] | 2024-04-08 | 2024-04-08 |  |  |  |  | GAA | 6400 | 6400 |  | 6400 | 6400
| 46 | 2024-01-0006D | 2024-04-0039 | Andoy's Car Aircon | 1 Lot- Repair of RP1-Naga Vehcile Airconditioner | [19 empty] | RP-Naga | NO | Small Value Procurement |  | 2024-01-25 | [5 empty] | 2024-04-08 | 2024-04-08 |  |  |  |  | GAA | 28300 | 28300 |  | 28300 | 28300
| 47 | 2024-03-0112 | 2024-04-0040 | Timog Tirehaus Corporation | 2 Pieces - Battery DIN66 Motolite Gold | [19 empty] | General Services | NO | Small Value Procurement |  | 2024-04-02 | [5 empty] | 2024-04-12 | 2024-04-12 |  |  |  |  | GAA | 25000 | 25000 |  | 24900 | 24900
| 48 | 2024-03-0110 | 2024-04-0041 | Kellsons Corporation | 300 Pieces - Archfile Binder (Blue) Legal Size | [19 empty] | Finance | NO | Shopping 52.1B |  | 2024-04-02 | [5 empty] | 2024-04-12 | 2024-04-12 |  |  |  |  | GAA | 48000 | 48000 |  | 46500 | 46500
| 49 | 2024-02-0062 | 2024-04-0042 | Art Johnley Enterprises | 1 Unit - 1.5HP Splt Type Wall Mounted Inverter Airconditioning Unit (Delivery and Installation included with One (1) Year Warranty) | [19 empty] | Director's Office | NO | Small Value Procurement |  | 2024-02-28 | [5 empty] | 2024-04-16 | 2024-04-15 |  |  |  |  | GAA | 49900 | 49900 |  | 49890 | 49890
| 52 | 2024-02-0052 | 2024-04-0043 | Luzon Sales, Co. Inc. | 1 Lot - Construction Materials for Partitioning and Painting of MIS Room | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-02-12 | [5 empty] | 2024-04-15 | 15 a[r 24 |  |  |  |  | GAA | 54194 | 54194 |  | 45164 | 45164
| 54 | 2024-02-0053 | 2024-04-0047 | Sagittarius Hardware Trading | 1 Lot - Construction Materials for Engineering Division Comfort Room | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-02-13 | [5 empty] | 2024-04-15 | 2024-04-15 |  |  |  |  | GAA | 52386 | 52386 |  | 41840 | 41840
| 55 | 2024-04-0117 | 2024-04-0048 | Halden General Merchandise | 2 Units- LED Monitor | [19 empty] | RP-Alert | NO | Small Value Procurement |  | 2024-03-21 | [5 empty] | 2024-04-16 | 2024-04-16 |  |  |  |  | GAA | 10000 | 10000 |  | 7600 | 7600
| 56 | 2024-03-0088 | 2024-04-0049 | Art Johnley Enterprises | 1 Unit - Air conditioner, Window Type, Inverter, 1HP R410a Refrigerant, Side Air Discharge, Carrier | [19 empty] | Proporty & Supply | NO | Small Value Procurement |  | 2024-03-08 | [5 empty] | 2024-04-17 | 2024-04-17 |  |  |  |  | GAA | 40000 | 40000 |  | 36995 | 36995
| 57 | 2024-03-0114B | 2024-04-0050 | Great Country Auto Supply | 1 Set - Power Steering Gear Box | [19 empty] | RP-Naga | NO | Small Value Procurement |  | 2024-04-16 | [5 empty] | 2024-04-16 | 2024-04-16 |  |  |  |  | GAA | 16370 | 16370 |  | 16000 | 16000
| 58 | 2024-03-0114D | 2024-04-0051 | FMG Trading & Construction Supply | 1 Lot - Painting Materials for Antenna Tower | [19 empty] | RP-Batanes | NO | Small Value Procurement |  | 2024-02-26 | [5 empty] | 2024-04-18 | 2024-04-18 |  |  |  |  | GAA | 26040 | 26040 |  | 19140 | 19140
| 59 | 2024-03-0114C | 2024-04-0052 | Edel's Concrete Product | 1 Lot - Painting Materials for Antenna Tower | [19 empty] | RP-Agoo | NO | Small Value Procurement |  | 2024-02-26 | [5 empty] | 2024-04-18 | 2024-04-18 |  |  |  |  | GAA | 32260 | 32260 |  | 22600 | 22600
| 60 | 2024-03-0023B | 2024-04-0011 | Gem's Car Aircon Shop | 1 Lot - Split Type Aircon General Cleaning, R410 (Freon) | [19 empty] | RP-Tabuk | NO | Small Value Procurement |  | 2024-03-14 | [5 empty] | 2024-04-18 | 2024-04-18 |  |  |  |  | GAA | 7400 | 7400 |  | 7400 | 7400
| 61 | 2024-04-0127 | 2024-04-0056 | Luzon Sales, Co. Inc. | 6 Gallons - Shelby Rubberized Liquid Aphalt Waterproofing | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-04-18 | [5 empty] | 2024-04-19 | 2024-04-19 |  |  |  |  | GAA | 12000 | 12000 |  | 6780 | 6780
| 62 | 2024-03-0093 | 2024-04-0053 | CBCD Trading | 6 Sets - Bi-Color LED Light, 6 Units - Impact Super Clamp with Ratchet Haldle | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-04-17 | [5 empty] | 2024-04-18 | 2024-04-18 |  |  |  |  | GAA | 78000 | 78000 | 77250 | 77250 | 77250
| 63 | 2024-03-0087 | 2024-04-0055 | CBCD Trading | 3 Units - Microphone Arm (Low Profile) | [19 empty] | RP-Alert | NO | Small Value Procurement |  | 2024-04-18 | [5 empty] | 2024-04-19 | 2024-04-19 |  |  |  |  | GAA | 26850 | 26850 |  | 26850 | 26850
| 64 | 2024-03-0086 | 2024-04-0054 | CBCD Trading | 3 Units - Microphone Cardioid Dynamic | [19 empty] | RP-Alert | NO | Small Value Procurement |  | 2024-04-18 | [5 empty] | 2024-04-19 | 2024-04-19 |  |  |  |  | GAA | 49050 | 49050 |  | 49050 | 49050
| 65 | 2024-03-0022 | 2024-04-0012 | Frigid Zone Auto Aircon Sepcialist Co. | 1 Unit - Repair of Airconditioner of Toyota Avanza P5V-602 | [19 empty] | General Services | NO | Small Value Procurement |  | 2024-04-19 | [5 empty] | 2024-04-22 | 2024-04-22 |  |  |  |  | GAA | 43680 | 43680 |  | 42000 | 42000
| 66 | 2024-02-0083D | 2024-04-0057 | GT Vulcanizing & Tire Center | 4 Pieces - Tire 185 x 14 Goodyear | [19 empty] | RP-Palawan | NO | Small Value Procurement |  | 2024-02-02 | [5 empty] | 2024-04-24 | 2024-04-24 |  |  |  |  | GAA | 18800 | 18800 |  | 18800 | 18800
| 67 | 2024-04-0025 | 2024-04-0013 | 88 Traders & Contracting Services Corp. | 1 Lot - Repair of Ford Ranger Plate No, SAB-8174 | [19 empty] | General Services | NO | Small Value Procurement |  | 2024-04-23 | [5 empty] | 2024-04-24 | 2024-04-24 |  |  |  |  | GAA | 136790 | 136790 |  | 129100 | 129100
| 68 | 2024-04-0142 | 2024-04-0058 | Dataview Computer Corporation | 1 Unit - CF276A HP Black Toner Cartridge | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-04-12 | [5 empty] | 2024-04-25 | 2024-04-25 |  |  |  |  | GAA | 7600 | 7600 |  | 6450 | 6450
| 69 | 2024-04-0133 | 2024-04-0060 | Sagittarius Hardware Trading | 3 Units - SC N2 Magnetic Contactor, 3 Pole, 220V, 40A, 60Hz, 1 Unit - Fuji SC N2S Magnetic Contactor 3 Pole, 220V, 50A, 60Hz | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-04-24 | [5 empty] | 2024-04-29 | 2024-04-29 |  |  |  |  | GAA | 29000 | 29000 |  | 28000 | 28000
| 70 | 2024-04-0141 | 2024-04-0059 | Luzon Sales, Co. Inc. | 5 Gallons - Bridal White Semi-Gloss Lstex, 1 Gallon - Chocolate Brown Semi-Gloss Latex | [19 empty] | Finance | NO | Small Value Procurement |  | 2024-04-24 | [5 empty] | 2024-04-26 | 2024-04-26 |  |  |  |  | GAA | 6000 | 6000 |  | 5825 | 5825
| 71 | 2024-04-0024 | 2024-04-0014 | Broadtech Corporation | 1 Unit - Repair of Transmitter, Armstrong HVPS X 1000B AM Transmitter | [19 empty] | RP-Gingoog | NO | Direcr Contracting |  | 2024-04-22 | [5 empty] | 2024-04-29 | 2024-04-29 |  |  |  |  | GAA | 72464 | 72464 |  | 72464 | 72464
| 72 | 2024-04-0140, 2024-04-0145 | 2024-04-0063 | AEQUUS Enterprise | 1 Unit- 7.5 TR Split Type Floor Mounted ACU with 1 Year Warranty, 1 Unit - 5.0 TR Split Type Floor Mounted ACU with 1 Year Warranty | [19 empty] | News & Administrative | NO | Small Value Procurement |  | 2024-04-28 | [5 empty] | 2024-04-30 | 2024-04-30 |  |  |  |  | GAA | 415000 | 415000 |  | 369333 | 369333
| 73 | 2024-04-0126 | 2024-05-0064 | CBCD Trading | 30 Packs - Acoustic Panel Sound Proof Padding Bevled Edge (12 Pieces per Pack) | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-04-16 | [5 empty] | 2024-05-02 | 2024-05-02 |  |  |  |  | GAA | 30000 | 30000 |  | 30000 | 30000
| 74 | 2024-04-0135 | 2024-04-0062 | Halden General Merchandise | 1 Unit - Laminating Machine | [19 empty] | Administrative | NO | Small Value Procurement |  | 2024-04-28 | [5 empty] | 2024-04-30 | 2024-04-30 |  |  |  |  | GAA | 8000 | 8000 |  | 7995 | 7995
| 75 | 2024-04-0139 | 2024-04-0061 | Halden General Merchandise | 1 Unit - 32" Computer Monitor | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-04-26 | [5 empty] | 2024-04-30 | 2024-04-30 |  |  |  |  | GAA | 20000 | 20000 |  | 19400 | 19400
| 76 | 2024-04-0150 | 2024-05-0067 | Luzon Sales, Co. Inc. | 20 Pieces - 2” x 4” Gypsum Board (PVC Laminated) | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-04-24 | [5 empty] | 2024-05-07 | 2024-05-07 |  |  |  |  | GAA | 6000 | 6000 |  | 5100 | 5100
| 77 | 2024-04-0123, 2024-04-0130 | 2024-05-0066 | Caresystem Technology Solution Co., Inc. | 1 Unit - 3.0TR Split Type Floor Mounted ACU, 1 Unit - 2.0 Window Type Aircon Non-Inverter Side Discharge | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-04-11 | [5 empty] | 2024-05-07 | 2024-05-07 |  |  |  |  | GAA | 135700 | 135700 |  | 135000 | 135000
| 78 | 2024-04-0157 | 2024-05-0068 | Great Country Auto Supply | 1 Set - Clutch Assembly, Release Bearing Cluch Cover, Clutch Disc | [19 empty] | General Services | NO | Small Value Procurement |  | 2024-05-07 | [5 empty] | 2024-05-08 | 2024-05-08 |  |  |  |  | GAA | 7500 | 7500 |  | 7000 | 7000
| 79 | 2024-04-0152 | 2024-05-0069 | Timog Tirehaus Corporation | 3 Pieces - Battery DIN66 Motolite Gold | [19 empty] | General Services | NO | Small Value Procurement |  | 2024-05-07 | [5 empty] | 2024-05-08 | 2024-05-08 |  |  |  |  | GAA | 37500 | 37500 |  | 37350 | 37350
| 80 | 2024-04-0163 | 2024-05-0071 | RYT Click Electronic Parts & Services | 1 Unit - Window Type Aircon 2HP | [19 empty] | RP-Tandag | NO | Small Value Procurement |  | 2024-04-01 | [5 empty] | 2024-05-06 | 2024-05-06 |  |  |  |  | GAA | 45880 | 45880 |  | 45880 | 45880
| 81 | 2024-04-0162 | 2024-05-0070 | JRM Auto Parts Trading | 5 Pieces - Tire 185-70 R14 Yokohama | [19 empty] | RP-Cagayan de oro | NO | Small Value Procurement |  | 2024-04-30 | [5 empty] | 2024-05-06 | 2024-05-06 |  |  |  |  | GAA | 25500 | 25500 |  | 25500 | 25500
| 82 | 2024-01-0035 | 2024-05-0072 | CBCD Trading | 1 Lot - IOS (iPhone Operating System) APPS for PBS Audio Streaming 6Streams RP1, RP2, RP3, RP4, FM1 and FM2 | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-04-30 | [5 empty] | 2024-05-06 | 2024-05-06 |  |  |  |  | GAA | 60000 | 60000 |  | 59650 | 59650
| 83 | 2024-02-0071 | 2024-05-0073 | CBCD Trading | 1 Unit - RV (Mobile) Satellite Internet with One (1) Year Subscription Plan, (Unlimited Mobilr Data Inland) | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-04-30 | [5 empty] | 2024-05-07 | 2024-05-07 |  |  |  |  | GAA | 85000 | 85000 |  | 84600 | 84600
| 84 | 2024-03-0102 | 2024-05-0074 | Sagittarius Hardware Trading | 6 Rolls - Guy Wire 3/8” 1000ft./roll, 18 Pieces - Turn Buckles Jaw & Jaw ¾” US Type, 100 Pieces - Thimble, ¾” US Type | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-04-30 | [5 empty] | 2024-05-07 | 2024-05-07 |  |  |  |  | GAA | 181400 | 181400 |  | 163800 | 163800
| 85 | 2024-05-0164 | 2024-05-0065 | Broadtech Corporation | 4 Pieces - Microchip Technology APT6025BVRG, Mosfet FG, Mosfet 600V, TO-247, RoHS VAT | [19 empty] | RP-Gingoog | NO | Direcr Contracting |  | 2024-05-02 | [5 empty] | 2024-05-07 | 2024-05-07 |  |  |  |  | GAA | 6272 | 6272 |  | 6272 | 6272
| 86 | 2024-04-0156 | 2024-05-0075 | Halden General Merchandise | 2 Units - Paper Shredder Machine | [19 empty] | Administrative | NO | Shopping 52.1B |  | 2024-05-13 | [5 empty] | 2024-05-15 | 2024-05-15 |  |  |  |  | GAA | 10000 | 10000 |  | 8000 | 8000
| 87 | 2024-04-0159, 2024-04-0160 | 2024-05-0176 | Timog Tirehaus Corporation | 4 Pieces - Tire 185/70 R14, 1 Piece - Battery 3SMF Reverse | [19 empty] | General Services | NO | Small Value Procurement |  | 2024-05-14 | [5 empty] | 2024-05-15 | 2024-05-15 |  |  |  |  | GAA | 30000 | 30000 |  | 26900 | 26900
| 88 | 2024-04-0034D | 2024-05-0017 | Gordiel Auto Parts | 4 Pieces - Spark Plug, 1 Piece - Oil Filter, 1 Piece - Fuel Fiter, 1 Gallon - Engine Oil, 1 Liter - Engine Oil | [19 empty] | RP-Cagayan de oro | NO | Small Value Procurement |  | 2024-04-29 | [5 empty] | 2024-05-23 | 2024-05-23 |  |  |  |  | GAA | 4020 | 4020 |  | 4020 | 4020
| 89 | 2024-04-0146 | 2024-05-0077 | MACJAB Industrial Chemical Products Wholesaling | 1 Lot - Various Cleaning Supplies | [19 empty] | General Services | NO | Shopping 52.1B |  | 2024-05-17 | [5 empty] | 2024-05-21 | 2024-05-21 |  |  |  |  | GAA | 73000 | 73000 |  | 46620 | 46620
| 90 | 2024-04-0034 | 2024-05-0015 | RGSA Carpets and Interior Products, Inc. | 1 Lot - Supply, Delivery and Installation of 6m x 6m Wall to Wall Broadloom Carpet w/ Foam Underlay for RP1-Studio Booth | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-05-13 | [5 empty] | 2024-05-21 | 2024-05-21 |  |  |  |  | GAA | 80000 | 80000 |  | 42888 | 42888
| 91 | 2024-04-0034C | 2024-05-0016 | 88 Traders & Contracting Services Corp. | 1 Lot - Repair of Vehicle Hyundai Starex MS-6843 | [19 empty] | General Services | NO | Small Value Procurement |  | 2024-05-20 | [5 empty] | 2024-05-23 | 2024-05-23 |  |  |  |  | GAA | 51500 | 51500 |  | 43000 | 43000
| 92 | 2024-05-0166 | 2024-05-0079 | Halden General Merchandise | 2 Units - High Back Executive Chair | [19 empty] | Proporty & Supply | NO | Small Value Procurement |  | 2024-05-22 | [5 empty] | 2024-05-24 | 2024-05-24 |  |  |  |  | GAA | 15000 | 15000 |  | 14600 | 14600
| 93 | 2024-05-0172 | 2024-05-0078 | Sagittarius Hardware Trading | 1 Roll - P.D. 5.5mm 2 Stranded Wire THHN/THWN – 2 Lead-Free, 11 Pieces - ½” EMT Conduit Pipe, 15 Pieces - ½” EMT Coupling, 4 Pieces - ½” EMT Elbow 90o, 2 Pieces - ½” EMT Connector with Locknut, 22 Pieces - ½” Metal C-Clamp | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-05-22 | [5 empty] | 2024-05-27 | 2024-05-27 |  |  |  |  | GAA | 14582 | 14582 |  | 14025 | 14025
| 94 | 2024-04-0163D | 2024-05-0080 | Adessa Corporation | 1 Unit - 2.0HP Airconditioner Window Type (Manual) Brand: Sharp Model# AFT2017CM | [19 empty] | RP-Dagupan | NO | Small Value Procurement |  | 2024-04-25 | [5 empty] | 2024-05-27 | 2024-05-27 |  |  |  |  | GAA | 27500 | 27500 |  | 27500 | 27500
| 95 | 2024-05-0040 | 2024-05-0018 | Composite Technology, Inc. | 1 Lot - One Time Diagnostic Check-up and Troubleshooting of Harris DX10 Transmitter of DZRK – Tabuk, Kalinga including Travel Expenses | [19 empty] | RP-Tabuk | NO | Direcr Contracting |  | 2024-05-22 | [5 empty] | 2024-05-27 | 2024-05-27 |  |  |  |  | GAA | 155680 | 155680 |  | 155680 | 155680
| 96 | 2024-05-0183 | 2024-05-0081 | GDP Trading | 1 Lot - Water Tank Installation Materials | [19 empty] | RP-Batanes | NO | Small Value Procurement |  | 2024-05-06 | [5 empty] | 2024-05-28 | 2024-05-28 |  |  |  |  | GAA | 38018 | 38018 |  | 38018 | 38018
| 97 | 2024-05-0201 | 2024-05-0084 | Dataview Computer Corporation | 1 Box - Belden Cat5e UTP Cable Gray, 305 Meters/Box | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-05-27 | [5 empty] | 2024-05-29 | 2024-05-29 |  |  |  |  | GAA | 8000 | 8000 |  | 7950 | 7950
| 99 | 2024-05-0202 |  | Luzon Sales, Co. Inc. | 3 Pieces - Marine Plywood ¾” x 4” x 8”, 10 Pieces - 2” x 3” x 8” S4S KD Lumber, 1 Kilo - 2” CW Nails, 1 Kilo - 3” CW Nails | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-05-27 | [5 empty] | 2024-05-29 | 2024-05-29 |  |  |  |  | GAA | 11900 | 11900 |  | 10632 | 10632
| 100 | 2024-05-0038 |  | 88 Trader's & Contracting Services, Corp. | 1 Unit - Repair of Vehicle, Hyundai Starex KOU-405 | [19 empty] | General Services | NO | Small Value Procurement |  | 2024-05-28 | [5 empty] | 2024-05-30 | 2024-05-30 |  |  |  |  | GAA | 48496 | 48496 |  | 48496 | 48496
| 101 | 2024-04-0144 | 2024-06-0085 | Halden General Merchandise | 2 Units - HD-SDI 3FCB LOW LOSS SDI Cable with BNC Connectors (20 Meters) | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-04-15 | [5 empty] | 2024-06-06 | 2024-06-06 |  |  |  |  | GAA | 29880 | 29880 |  | 27200 | 27200
| 102 | 2024-05-0037 | 2024-06-0020 | Frigid Zone Auto Aircon Sepcialist Co. | 1 Unit - Aircon Cleaning of Avanza SAB-6357 | [19 empty] | General Services | NO | Small Value Procurement |  | 2024-05-08 | [5 empty] | 2024-06-11 | 2024-06-11 |  |  |  |  | GAA | 6160 | 6160 |  | 6160 | 6160
| 103 | 2024-04-0163F | 2024-06-0086 | Sunray's Builder and Construction Supplies | 1 Lot - Materials for Perimieter Fencing and Water Connection with Hauling of Materials at the base of Mount Pokis | [19 empty] | RP-Bontoc | NO | Small Value Procurement |  | 2024-06-04 | [5 empty] | 2024-06-10 | 2024-06-10 |  |  |  |  | GAA | 85320 | 85320 |  | 85320 | 85320
| 104 | 2024-05-0205 | 2024-06-0084 | Octagon Computer Superstore | 1 Unit - Computer Printer Brother DCP-T420W with Continuous Ink | [19 empty] | RP-Zamboanga | NO | Small Value Procurement |  | 2024-05-21 | [5 empty] | 2024-06-04 | 2024-06-04 |  |  |  |  | GAA | 8750 | 8750 |  | 8350 | 8350
| 105 | 2024-05-0174 | 2024-06-0087 | Halden General Merchandise | 1 Unit - 2 Meters HD-SDI 3CFB LOW LOSS SDI Cable with BNC Connectors (20 Meters) PhP 14,940.00 PhP 29,880.00 Total PhP 29,880.00 | [19 empty] | FM1 | NO | Small Value Procurement | [7 empty] | 2024-06-13 | 2024-06-13 |  |  |  |  | GAA | 25000 | 25000 |  | 23000 | 23000
| 106 | 2024-06-0217 | 2024-06-0088 | Luzon Sales, Co. Inc. | 1 Lot - Materials for the Flood Control in Electrical Equipment Room at the Malolos Transmitter | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-06-05 | [5 empty] | 2024-06-20 | 2024-06-20 |  |  |  |  | GAA | 11220 | 11220 |  | 8834 | 8834
| 107 | 2024-06-0218 | 2024-06-0218 | Luzon Sales, Co. Inc. | 100 Pieces - 60cm x 60cm Floor Tiles, 2 Bags - Cement, 10 Bags - Fine Sand | [19 empty] | Engineering | NO | Small Value Procurement |  | 2024-06-05 | [5 empty] | 2024-06-20 | 2024-06-20 |  |  |  |  | GAA | 31600 | 31600 |  | 25140 | 25140
| 109 | 2024-06-0220 | 2024-06-0090 | CBCD Trading | 3 Pieces - Anchor Block Equalizer | [19 empty] | RP-Agoo | NO | Small Value Procurement |  | 2024-06-25 | [5 empty] | 2024-06-26 | 2024-06-26 |  |  |  |  | GAA | 24000 | 24000 |  | 24000 | 24000
| 110 | 2024-05-0207 | 2024-06-0091 | Caresystem Technology Solution Co., Inc. | 1 Unit - Airconditioner 3.0 TR Split Type Floor Mounted ACU Delivery and Installation included (1 Year Warranty) | [19 empty] | Network | NO | Small Value Procurement |  | 2024-06-24 | [5 empty] | 2024-06-27 | 2024-06-27 |  |  |  |  | GAA | 95700 | 95700 |  | 95000 | 95000
| 111 | 2024-06-0053 |  | Canva, Inc. | 1 Lot - Annual Online Graphic Design and Publishing Tool | [19 empty] | Research | NO | Section 53.14 Direct Retail |  | 2024-06-26 | [5 empty] | 2024-07-02 | 2024-07-02 |  |  |  |  | GAA | 6304 | 6304 |  | 6304 | 6304
Total Alloted Budget of Procurement Activities | [41 empty] | 5593981.72
Total Contract Price of Procurement Actitvites Conducted | [44 empty] | 4897292
Total Savings (Total Alloted Budget - Total Contract Price) | [41 empty] | 696689.72
0N-GOING PROCUREMENT ACTIVITIES
[5 empty] | One (1) Lot - Supply and Delivery of Fourteen (14) Units Brand-New 2024 Model Motor Vehicles | [19 empty] | Administrative | NO | Competitive Bidding | 2024-07-02 | 2024-07-08 | 2024-07-17 | 2024-07-31 | 2024-07-31 | [8 empty] | GAA | 16212000 |  | 16212000
[5 empty] | One (1) Lot - Supply and Delivery of Information System Strategic Plan (ISSP) Various Broadcast Studio Equipment, Broadcast Automation / Disaster Alerting System and Accessories | [19 empty] | Engineeering | NO | Competitve Bidding | [13 empty] | GAA | 9104000 | 2575000 | 6619000
0
0
Total Alloted Budget of On-going Procurement Activities | [41 empty] | 25316000
[25 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
[25 empty] | RODNEY O. VILLANUEVA | [10 empty] | ALAN L. ALLANIGUE | [10 empty] | RIZAL GIOVANNI P. APORTADERA, JR.
[25 empty] | BAC Secretariat Head | [10 empty] | BAC Chairperson | [10 empty] | Director IV / Head of the Procuring Entity

## Sheet2
49000 | 49000 | 49000 | 49000
8775 | 8775 | 8775 | 8775
10000 | 10000 | 9975 | 9975
6305 | 6305 | 6305 | 6305
20400 | 20400 | 19500 | 19500
9004 | 9004 | 8385 | 8385
5700 | 5700 | 5700 | 5700
9850 | 9850 | 9850 | 9850
15500 | 15500 | 15500 | 15500
5200 | 5200 | 5200 | 5200
6500 | 6500 | 6500 | 6500
34000 | 34000 | 33300 | 33300
79500 | 79500 | 79500 | 79500
15900 | 15900 | 13650 | 13650
8000 | 8000 | 7950 | 7950
310050 | 310050 | 230345 | 230345
5700 | 5700 | 5700 | 5700
14400 | 14400 | 12295 | 12295
11860 | 11860 | 9635 | 9635
65340 | 65340 | 64350 | 64350
23000 | 23000 | 23000 | 23000
84000 | 84000 | 82556 | 82556
26765 | 26765 | 26765 | 26765
36000 | 36000 | 34000 | 34000
50000 | 50000 | 37500 | 37500
188475 | 188475 | 188475 | 188475
60620 | 60620 | 60620 | 60620
13000 | 13000 | 13000 | 13000
6800 | 6800 | 6800 | 6800
37386 | 37386 | 36060 | 36060
55500 | 55500 | 39900 | 39900
75500 | 75500 | 73920 | 73920
16000 | 16000 | 15800 | 15800
36900 | 36900 | 36860 | 36860
97400 | 97400 | 97400 | 97400
29400 | 29400 | 29400 | 29400
17000 | 17000 | 16500 | 16500
60000 | 60000 | 38990 | 38990
9000 | 9000 | 8700 | 8700
49000 | 49000 | 45000 | 45000
11567.56 | 11567.56 | 9500 | 9500
5500 | 5500 | 5500 | 5500
23000 | 23000 | 23000 | 23000
30540 | 30540 | 30540 | 30540
432000 | 432000 | 432000 | 432000
8670 | 8670 | 8670 | 8670
48000 | 48000 | 48000 | 48000
9500 | 9500 | 9500 | 9500
13000 | 13000 | 13000 | 13000
36730 | 36730 | 36730 | 36730
77828 | 77828 | 77570.08 | 77570.08
6443 | 6443 | 6443 | 6443
3600 | 3600 | 3600 | 3600
11760 | 11760 | 11760 | 11760
9800 | 9800 | 9800 | 9800
18000 | 18000 | 17800 | 17800
7950 | 7950 | 7650 | 7650
112000 | 112000 | 112000 | 112000
5600 | 5600 | 5600 | 5600
7523.65 | 7523.65 | 7450 | 7450
10000 | 10000 | 7990 | 7990
13995 | 13995 | 13995 | 13995
10000 | 10000 | 9000 | 9000
6734 | 6734 | 6540 | 6540
59000 | 59000 | 56998 | 56998
38880 | 38880 | 32420 | 32420
7599 | 7599 | 7450 | 7450
24000 | 24000 | 21600 | 21600
45000 | 45000 | 43899 | 43899
10300 | 10300 | 10280 | 10280
8450 | 8450 | 6145 | 6145
16000 | 16000 | 15900 | 15900
10600 | 10600 | 9100 | 9100
10000 | 10000 | 10000 | 10000
23430 | 23430 | 22160 | 22160
19600 | 19600 | 19600 | 19600
12280 | 12280 | 12280 | 12280
6400 | 6400 | 6400 | 6400
49995 | 49995 | 41999 | 41999
137100 | 137100 | 105451 | 105451
9450 | 9450 | 9450 | 9450
28190 | 28190 | 28190 | 28190
8690 | 8690 | 8690 | 8690
17000 | 17000 | 16000 | 16000
12280 | 12280 | 12280 | 12280
22230 | 22230 | 22230 | 22230
26300 | 26300 | 26300 | 26300
42250 | 42250 | 42250 | 42250
7534 | 7534 | 7534 | 7534
39600 | 39600 | 39600 | 39600
13185 | 13185 | 13185 | 13185
15697 | 15697 | 15697 | 15697
8200 | 8200 | 8200 | 8200
9500 | 9500 | 9500 | 9500
17296.2 | 17296.2 | 17220 | 17220
11000 | 11000 | 11000 | 11000
20000 | 20000 | 19800 | 19800
36700 | 36700 | 36700 | 36700
12000 | 12000 | 9600 | 9600
194000 | 194000 | 193200 | 193200
150000 | 150000 | 99995 | 99995
73990 | 73990 | 73990 | 73990
3550 | 3550 | 3550 | 3550
17400 | 17400 | 17400 | 17400
29490 | 29490 | 27800 | 27800
26835 | 26835 | 26800 | 26800
9000 | 9000 | 8900 | 8900
118550 | 118550 | 89090 | 89090
15550 | 15550 | 15100 | 15100 | 450 | Savings | as of June 27, 2023
45500 | 45500 | 44500 | 44500
122000 | 122000 | 85000 | 85000
37800 | 37800 | 37035 | 37035
4261872.41 | 4261872.41 | 3923767.08 | 3923767.08

## Sheet3
1 | 9760 | 9760
11 | 365 | 4015
15 | 44 | 660
4 | 86 | 344
2 | 45 | 90
22 | 7 | 154
15023

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement