## PMR
[6 empty] | ANNEX A | [18 empty] | ANNEX B
[6 empty] | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | Bureau of Broadcast Services Procurement Monitoring Report as of December 31, 2024
Code (PAP) |  |  |  |  | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
[8 empty] | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| 112 | 2024-06-0219 | 2924-07-0092 | Varyline Corporation | 1 Lot - Various Office Supplies | [19 empty] | Property & Supply | NO | Shopping 52.1B |  | 2024-07-01 | [5 empty] | 2024-07-04 | 2024-07-04 |  |  |  |  | GoP | 648500 | 648500 |  | 540440 | 540440
| 113 | 2024-07-0233 | 2024-07-0093 | Dataview Computer Corporation | 3 Units - LED PC Monitor | [19 empty] | RP-Alert | NO | NP-53.9 - Small Value Procurement |  | 2024-07-11 | [5 empty] | 2024-07-16 | 2024-07-16 |  |  |  |  | GoP | 15000 | 15000 |  | 13500 | 13500
| 114 | 2024-07-0232 | 2024-07-0094 | Great Country Auto Supply | 1 Piece - Radiator Assembly, 1 Piece - Fan Motor, 1 Piece - Condenser, 1 Set - Shock Absorber | [19 empty] | General Services | NO | NP-53.9 - Small Value Procurement |  | 2024-07-11 | [5 empty] | 2024-07-16 | 2024-07-16 |  |  |  |  | GoP | 23000 | 23000 |  | 22500 | 22500
| 115 | 2024-06-0230C | 2024-07-0095 | Dataview Computer Corporation | 1 Lot - Various Materials for Video Streaming | [19 empty] | RP-Palawan | NO | NP-53.9 - Small Value Procurement |  | 2024-07-16 | [5 empty] | 2024-07-17 | 2024-07-17 |  |  |  |  | GoP | 27600 | 27600 |  | 25740 | 25740
| 116 | 2024-07-0240 | 2024-07-0096 | Timog Tirehaus Corporation | 10 Pieces - Tires 185/70 R 14 | [19 empty] | General Services | NO | NP-53.9 - Small Value Procurement |  | 2024-07-18 | [5 empty] | 2024-07-19 | 2024-07-19 |  |  |  |  | GoP | 45000 | 45000 |  | 43500 | 43500
| 117 | 2024-07-0249 | 2024-07-0097 | Benchmark Electrical and Cooling Solutions, Inc. | 1 Unit - Window Type Airconditioner 1HP AUX Brand | [19 empty] | RP-Laoag | NO | NP-53.9 - Small Value Procurement |  | 2024-07-10 | [5 empty] | 2024-07-22 | 2024-07-22 |  |  |  |  | GoP | 14449 | 14449 |  | 14449 | 14449
| 118 | 2024-02-0061 | 2024-07-0098 | CBCD Trading | 6 Units - Cable Mounr XLR Connector, 2 Units - Pole Adapter | [19 empty] | FM1 | NO | NP-53.9 - Small Value Procurement |  | 2024-07-19 | [5 empty] | 2024-07-23 | 2024-07-24 |  |  |  |  | GoP | 15300 | 15300 |  | 15240 | 15240
| 119 | 2024-05-0045B | 2024-07-0022 | Plom's Apartment | 1 Lot - Renewable Lease of Studio/Office Space for DXBN – Radyo Pilipinas – Butuan (6 months) | [19 empty] | RP-Butuan | NO | NP-53.9 - Small Value Procurement |  | 2024-07-18 | [5 empty] | 2024-07-22 | 2024-07-23 |  |  |  |  | GoP | 200000 | 200000 |  | 200000 | 200000
| 120 | 2024-02-0083D | 2024-07-0099 | F & E Enterprises, Inc. | 4 Pieces - Tire 186 x 14 Goodyear | [19 empty] | RP-Palawan | NO | NP-53.9 - Small Value Procurement |  | 2024-02-02 | [5 empty] | 2024-07-29 | 2024-07-29 |  |  |  |  | GoP | 18916 | 18916 |  | 18916 | 18916
| 121 | 2024-06-0048 | 2024-07-0023 | 88 Traders & Contracting Services Corp. | 1 Lot - Repair of Brakes System and Transmission Dialysis of Ford Wildtrak 8174 | [19 empty] | General Services | NO | NP-53.9 - Small Value Procurement |  | 2024-07-19 | [5 empty] | 2024-07-30 | 2024-07-30 |  |  |  |  | GoP | 98849.57 | 98849.57 |  | 78770 | 78770
| 122 | 2024-06-0052 | 2024-07-0024 | Broadtech Corporation | 1 Lot - Monthly Subscription of Satellite Internet Plan with Unlimited Data for Six (6) Months Kacific Marine Plan | [19 empty] | Engineering | NO | NP-53.9 - Small Value Procurement |  | 2024-07-29 | [5 empty] | 2024-07-30 | 2024-07-30 |  |  |  |  | GoP | 136320 | 136320 |  | 136320 | 136320
| 123 | 2024-07-0059 | 2024-07-0025 | R & J Printables Printing Services | 1 Lot - 60 Pieces Training Kit (Ballpen, Notebook & Non-woven Eco Bag) | [19 empty] | GAD | NO | NP-53.9 - Small Value Procurement |  | 2024-07-29 | [5 empty] | 2024-07-30 | 2024-07-30 |  |  |  |  | GoP | 13800 | 13800 |  | 11692 | 11692
| 124 | 2024-07-0239 | 2024-08-0100 | Sagittarius Hardware Trading | 1 Unit - Magnetic Contactor, SC-N2, 3 Pole, 220V, 40A, 60Hz | [19 empty] | Engineering | NO | NP-53.9 - Small Value Procurement |  | 2024-08-01 | [5 empty] | 2024-08-02 | 2024-08-02 |  |  |  |  | GoP | 7000 | 7000 |  | 6850 | 6850
| 125 | 2024-07-0255 | 2024-07-0101 | Silicon Valley Computer Groups Phils., Inc. | 1 Unit - Epson Printer 3210, All-in-One Print, Scan and Copy (Max A4) | [19 empty] | RP-Laoag | NO | NP-53.9 - Small Value Procurement |  | 2024-07-02 | [5 empty] | 2024-08-05 | 2024-08-05 |  |  |  |  | GoP | 8795 | 8795 |  | 8795 | 8795
| 126 | 2024-07-0247 | 2024-07-0102 | Halden General Merchandise | 1 Unit - 32” HDR LED Smart TV, 3 Uniys - Optical to RCA Converter Audio Coaxial | [19 empty] | Engineering | NO | NP-53.9 - Small Value Procurement |  | 2024-08-05 | [5 empty] | 2024-08-06 | 2024-08-06 |  |  |  |  | GoP | 34500 | 34500 |  | 20100 | 20100
| 127 | 2024-07-0257C | 2024-08-0103 | Laoag Auto Supply Corporation | 1 Piece - 2SM Motolite Gold Battery Maintenance Free | [19 empty] | RP-Laoag | NO | NP-53.9 - Small Value Procurement |  | 2024-07-10 | [5 empty] | 2024-08-12 | 2024-08-12 |  |  |  |  | GoP | 6268 | 6268 |  | 6268 | 6268
| 128 | 2024-07-0257D | 2024-08-0104 | Ong King Auto Supply | 1 Set - Whole Tire Hub for 2008 Isuzu Crosswind SJG 160 Left Driver Side | [19 empty] | RP-Bontoc | NO | NP-53.9 - Small Value Procurement |  | 2024-07-09 | [5 empty] | 2024-07-12 | 2024-07-12 |  |  |  |  | GoP | 18550 | 18550 |  | 18550 | 18550
| 129 | 2024-07-0061 | 2024-08-0026 | Composite Technology, Inc. | 1 Lot - Analog Input DX-10/15 Installation of Analog Input Board at BBS Tabuk including travel expenses (12 days onsite installation & 2 days travel) | [19 empty] | RP-Tabuk | NO | Direct Contracting |  | 2024-08-13 | [5 empty] | 2024-08-14 | 2024-08-14 |  |  |  |  | GoP | 779464 | 779464 |  | 779464 | 779464
| 130 | 2024-07-0251 | 2024-08-0105 | CBCD Trading | 2 Units - RF Connector 7/8 Flange with Inner Bullet, 1 Unit - 5/8 x 1 Meter Lighting Rod with Mounting, 2 Pieces - Rubber Tape Cotran 10 Pieces - Cable Holder for 7/8 RF Cable | [19 empty] | RP-Agoo | NO | NP-53.9 - Small Value Procurement |  | 2024-08-13 | [5 empty] | 2024-08-15 | 2024-08-15 |  |  |  |  | GoP | 37000 | 37000 |  | 36640 | 36640
| 130A | 2024-08-0071 |  | Zoom Video Communications, Inc. | 1 Lot - Zoom Account Subscription from August 19, 2024 to August 18, 2025 for video conferencing of Director’s Office, Training (Admin), PBS Network Stations, Engineering, and FM Stations | [19 empty] | Engineering | NO | Direct Contracting |  | 2024-08-15 | [5 empty] | 2024-08-15 | 2024-08-15 |  |  |  |  | GoP | 5570 | 5570 |  | 5570 | 5570
| 131 | 2024-07-0063 | 2024-08-0027 | Award Central Philippines, Inc. | 252 Pieces - Customized Acrylic Paper Weight | [19 empty] | GAD | NO | NP-53.9 - Small Value Procurement |  | 2024-08-15 | [5 empty] | 2024-08-21 | 2024-08-21 |  |  |  |  | GoP | 225330 | 225330 |  | 149940 | 149940
| 132 | 2024-06-0230E | 2024-08-0106 | Nationwide Sales, Corp. | 1 Lot - Materials for the Repair of Ceiling, Comfort Room for Male and Female (Additional) and Electrical Wirings including Fixtures for DXMR-Zamboanga (includes 12% VAT) | [19 empty] | RP-Zamboanga | NO | NP-53.9 - Small Value Procurement |  | 2024-08-15 | [5 empty] | 2024-08-21 | 2024-08-21 |  |  |  |  | GoP | 125833.12 | 125833.12 |  | 125833.12 | 125833.12
| 133 | 2024-07-0246 | 2024-08-0107 | Silvanus Non-Specialized Wholesale Trading | 7 Units - Android Tablet | [19 empty] | Research | NO | NP-53.9 - Small Value Procurement |  | 2024-08-15 | [5 empty] | 2024-08-22 | 2024-08-22 |  |  |  |  | GoP | 299600 | 299600 |  | 279930 | 279930
| 134 | 2024-07-0257 | 2024-08-0108 | AGB Refrigeration Center | 1 Set - Air conditioner, 2HP Inverter Daikin DSmart Series with Free Installation for the first 10ft. (400ft for excess of 10ft) | [19 empty] | RP-Agpp | NO | NP-53.9 - Small Value Procurement |  | 2024-08-15 | [5 empty] | 2024-08-22 | 2024-08-22 |  |  |  |  | GoP | 54500 | 54500 |  | 54500 | 54500
| 135 | 2024-07-0257F | 2024-08-0109 | Ethereum Technology Sales | 1 Unit - Computer Printer with Continuous Ink, Brother DCP-T420W 3-in-1 Print, Copy and Scan | [19 empty] | RP-Zamboanga | NO | Shopping 52.1B |  | 2024-08-15 | [5 empty] | 2024-08-22 | 2024-08-22 |  |  |  |  | GoP | 8855 | 8855 |  | 8855 | 8855
| 136 | 2024-08-0068 | 2024-08-0029 | John-Henry Car Care Center | 1 Lot - Overhaul abd Calibrate of the Injection Pump of Isuzu Crosswind and Pull Down Tank | [19 empty] | RP-Laoag | NO | NP-53.9 - Small Value Procurement |  | 2024-08-15 | [5 empty] | 2024-08-22 | 2024-08-22 |  |  |  |  | GoP | 16300 | 16300 |  | 16300 | 16300
| 137 | 2024-07-0064C | 2024-08-0028 | Geomer Airconditioning Works & Sales, Inc. | 1 Lot - Repair of One (1) Unit of 2.5HP Carrier Window Type Aircon at the Transmitter Site | [19 empty] | RP-Iloilo | NO | NP-53.9 - Small Value Procurement |  | 2024-07-23 | [5 empty] | 2024-08-22 | 2024-08-22 |  |  |  |  | GoP | 16240 | 16240 |  | 16240 | 16240
| 138 | 2024-07-0244, 2024-07-0245 |  | 90 Degrees North, Inc. | 1 Lot- Supply and Delivery of Information System Strategic Plan (ISSP) Various Broadcast Equipment, Broadcast Automation / Disaster Alert System and Components | [19 empty] | Engineering | NO | Competitve Bidding |  | 2024-07-16 | 2024-07-31 | 2024-08-14 | 2024-08-14 | 2024-08-27 | 2024-08-27 | 2024-09-09 | 2024-09-20 |  | 2024-10-17 |  |  | GoP | 9194000 |  | 9194000 | 9193899.98 |  | 9193899.98 | MR. Crisanto Frianeza, Secretary General of Philippine Chamber of Commerce and Industry, , Mr. Amador Astudillo, President of Procurement Watch and Ms. Estrellita M. Aguilar, Audit Team Leader in BBS of Commission on Audi | 2024-07-31 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-27
| 139 | 2024-08-0067 | 2024-09-0090 | Best Choice Gourmet & Catering Services | 1 Lot - Meals for PBS Management Conference cum GAD Strategic Plan and PBS 77th Anniversary | [19 empty] | GAD | NO | NP-53.9 - Small Value Procurement |  | 2024-08-12 | [5 empty] | 2024-09-04 | 2024-09-04 |  |  |  |  | GoP | 225000 | 225000 |  | 225000 | 225000
| 140 | 2024-08-0065 | 2024-00-0031 | Verjandel Hotel | 1 Lot - Function, Meals and Accommodation Package for PBS Management Conferecne cum GAD Strategic Planning | [19 empty] | GAD | NO | NP-53.9 - Small Value Procurement |  | 2024-08-12 | [5 empty] | 2024-09-04 | 2024-09-04 |  |  |  |  | GoP | 270000 | 270000 |  | 269100 | 269100
| 141 | 2024-08-0276 | 2024-09-0110 | Timog Tirehaus Corporation | 1 Unit - 6SM N100 Truck Master LM with Battery Solution, 8 Pieces - Distilled Water for Battery | [19 empty] | Engineering | NO | NP-53.9 - Small Value Procurement |  | 2024-08-29 | [5 empty] | 2024-09-05 | 2024-09-05 |  |  |  |  | GoP | 14100 | 14100 |  | 12300 | 12300
| 142 | 2024-08-0073 | 2024-09-0032 | Bolante Lights and Sound Services | 1 Set - P3 LED Wall Rental | [19 empty] | GAD | NO | NP-53.9 - Small Value Procurement |  | 2024-08-29 | [5 empty] | 2024-09-04 | 2024-09-04 |  |  |  |  | GoP | 14100 | 14100 |  | 14100 | 14100
| 143 | 2024-08-0262 | 2024-00-0112 | CBCD Trading | 6 Units - Muffin Series Axial Fan | [19 empty] | Engineering | NO | NP-53.9 - Small Value Procurement |  | 2024-08-07 | [5 empty] | 2024-09-05 | 2024-09-05 |  |  |  |  | GoP | 39000 | 39000 |  | 38100 | 38100
| 144 | 2024-08-0275 | 2024-09-0113 | Sonitram Merchandising Corp. | 1 CYL - Freon R 22 | [19 empty] | Engineering | NO | NP-53.9 - Small Value Procurement |  | 2024-08-12 | [5 empty] | 2024-09-05 | 2024-09-05 |  |  |  |  | GoP | 14000 | 14000 |  | 13500 | 13500
| 145 | 2024-07-0257H | 2024-09-0111 | Laoag Astronic Auto Supply | 4 Pieces - Tires 185 x 14 Goofyear | [19 empty] | RP-Laoag | NO | NP-53.9 - Small Value Procurement |  | 2024-08-12 | [5 empty] | 2024-09-05 | 2024-09-05 |  |  |  |  | GoP | 21000 | 21000 |  | 21000 | 21000
| 146 | 2024-08-0274 | 2024-08-0114 | MACJAB Industrial Chemical Products Wholesaling | 1 Lot - Various Cleaning Supplies | [19 empty] | General Services | NO | Shopping |  | 2024-08-28 | [5 empty] | 2024-09-05 | 2024-09-05 |  |  |  |  | GoP | 69500 | 69500 |  | 44220 | 44220
| 147 | 2024-09-0294 | 2024-09-0116 | Gordiel Auto Parts | 5 Pieces - Tires Yokohama | [19 empty] | RP-Cagayan de oro |  | NP-53.9 - Small Value Procurement |  | 2024-09-05 | [5 empty] | 2024-09-05 | 2024-09-09 |  |  |  |  | GoP | 34000 | 34000 |  | 34000 | 34000
| 148 | 2024-08-0291B | 2024-08-0115 | EER Auto Supply | 1 Unit - Battery, Motolite Gold | [19 empty] | RP-Lucena |  | NP-53.9 - Small Value Procurement |  | 2024-08-12 | [5 empty] | 2024-09-09 | 2024-09-09 |  |  |  |  | GoP | 6800 | 6800 |  | 6800 | 6800
| 149 | 2024-08-0266 | 2024-09-0117 | CBCD Trading | 1 Pair - Safety Shoes, 7”, 1 Pair - Safety Shoes 8”, 2 Pieces - Safety Ropes, 10 Meters, 2 Pieces - Safety Goggles, 2 Pieces - Catch Harness (Full Body with Padding), 2 Pieces - Full Body Harness with 2 Safety Lanyards | [19 empty] | Engineering | NO | NP-53.9 - Small Value Procurement |  | 2024-08-30 | [5 empty] | 2024-09-11 | 2024-09-11 |  |  |  |  | GoP | 20760 | 20760 |  | 20300 | 20300
| 150 | 2024-08-0290 | 2024-09-0119 | Halden General Merchandise | 5 Units - High Back Mesh Office Chair | [19 empty] | Engineering | NO | NP-53.9 - Small Value Procurement |  | 2024-09-12 | [5 empty] | 2024-09-13 | 2024-09-13 |  |  |  |  | GoP | 37500 | 37500 |  | 35000 | 35000
| 151 | 2024-08-0291 | 2024-09-0120 | Sagittarius Hardware Trading | 1 Unit - Refrigerator 2 Door 7.5cu.ft | [19 empty] | Administrative | NO | NP-53.9 - Small Value Procurement |  | 2024-09-12 | [5 empty] | 2024-09-13 | 2024-09-13 |  |  |  |  | GoP | 19000 | 19000 |  | 19000 | 19000
| 152 | 2024-08-0285 | 2024-09-0121 | Great Country Auto Supply | 1 Set - Transmission Clutch Set Assembly | [19 empty] | RP-Batanes | NO | NP-53.9 - Small Value Procurement |  | 2024-09-16 | [5 empty] | 2024-09-17 | 2024-09-17 |  |  |  |  | GoP | 8700 | 8700 |  | 8200 | 8200
| 153 | 2024-08-0288 | 2024-09-0122 | Sagittarius Hardware Trading | 2 Units - NS60 Maintenance Free Battery | [19 empty] | Engineering | NO | NP-53.9 - Small Value Procurement |  | 2024-09-17 | [5 empty] | 2024-09-18 | 2024-09-18 |  |  |  |  | GoP | 12000 | 12000 |  | 11600 | 11600
| 154 | 2024-07-0064D | 2024-09-0033 | R. Ibanez Construction | 1 Lot - Supply, Delivery and Labor for the Partitioning of RP1-Iloilo Booths and Offices | [19 empty] | RP-Iloilo | NO | NP-53.9 - Small Value Procurement |  | 2024-09-16 | [5 empty] | 2024-09-19 | 2024-09-19 |  |  |  |  | GoP | 434130.15 | 434130.15 |  | 424504 | 424504
| 155 | 2024-09-0076 |  | Zoom Video Communications, Inc. | 1 Lot - Subscription of Premium Zoom with Account Number 5057925491 for the period of September 24 to October 23, 2024 | [19 empty] | RP2-Sports | NO | Direct Contracting |  | 2024-09-17 | [5 empty] | 2024-09-23 | 2024-09-23 |  |  |  |  | GoP | 556.99 | 556.99 |  | 556.99 | 556.99
| 156 | 2024-07-0231 |  | Toyota Quezon Avenue, Inc, | 1 Lot - Supply and Delivery of Brand-New 2024 Model Motor Vehicle (fourteen (14) Units - Toyota Veloz 1.5 Gas CVT-Silver) | [19 empty] | Administrative | NO | Competitve Bidding | 2024-07-02 | 2024-07-08 | 2024-07-17 | 2024-07-31 | 2024-07-31 | 2024-08-08 | 2024-08-15 | 2024-09-30 | 2024-10-01 |  | 2024-10-16 |  |  | GoP | 16212000 |  | 16212000 | 15181950 |  | 15181950 | Mr. Crisanto Frianeza, Secretary General of Philippine Chamber of Commerce and Industry, , Mr. Amador Astudillo, President of Procurement Watch and Ms. Estrellita M. Aguilar, Audit Team Leader in BBS of Commission on Audit; | 2024-07-17 | 2024-07-31 | 2024-07-31 | 2024-08-08 | 2024-08-15
| 157 | 2024-09-0309 | 2024-09-0123 | CBCD Trading | 1 Unit - Dynamic Vocal Microphone (Cardiod Unidirectional) | [19 empty] | RP-Batanes | NO | NP-53.9 - Small Value Procurement |  | 2024-09-24 | [5 empty] | 2024-09-26 | 2024-09-26 |  |  |  |  | GoP | 8000 | 8000 |  | 7900 | 7900
| 158 | 2024-08-0070 | 2024-09-0034 | Versa Innovations Corporation | 1 Lot - 20 Units Push to Talk Over Cellular (PoC) Radio Services Monrhly Subscription (for the period of October to December 2024) | [19 empty] | Engineering | NO | NP-53.9 - Small Value Procurement |  | 2024-09-24 | [5 empty] | 2024-09-25 | 2024-09-25 |  |  |  |  | GoP | 40252.8 | 40252.8 |  | 35940 | 35940
| 159 | 2024-05-0190 | 2024-09-0124 | CBCD Trading | ! Lot - Pressire Tank with Installation | [19 empty] | Administrative | NO | NP-53.9 - Small Value Procurement |  | 2024-09-26 | [5 empty] | 2024-09-30 | 2024-09-30 |  |  |  |  | GoP | 70000 | 70000 |  | 70000 | 70000
| 160 | 2024-09-0299 | 2924-10-0126 | Sagittarius Hardware Trading | 1 Unit - Grass Cutter | [19 empty] | Marulas Transmitter | NO | NP-53.9 - Small Value Procurement |  | 2024-10-01 | [5 empty] | 2024-10-02 | 2024-10-02 |  |  |  |  | GoP | 8000 | 8000 |  | 7500 | 7500
| 161 | 2024-09-0313 | 2024-10-0125 | Dataview Computer Corporation | 1 Unit - All-in-One Ink Tank Printer | [19 empty] | RP3-Alert | NO | Shopping |  | 2024-10-01 | [5 empty] | 2024-10-02 | 2024-10-02 |  |  |  |  | GoP | 13500 | 13500 |  | 12995 | 12995
| 162 | 2024-07-0062 | 2024-10-0035 | CBCD Trading | 1 Lot - Repair of 400 Amp. ATS (Automatic Transfer Switch) at PBS Central Office. Supply of parts and labor included | [19 empty] | Engineering | NO | NP-53.9 - Small Value Procurement |  | 2024-10-01 | [5 empty] | 2024-10-02 | 2024-10-02 |  |  |  |  | GoP | 9000 | 9000 |  | 8900 | 8900
| 163 | 2024-09-0300 | 2024-10-0127 | Timog Tirehaus Corporation | 2 Pieces - Battery NS60ZR | [19 empty] | General Services | NO | NP-53.9 - Small Value Procurement |  | 2024-10-03 | [5 empty] | 2024-10-04 | 2024-10-04 |  |  |  |  | GoP | 17000 | 17000 |  | 16800 | 16800
| 164 | 2024-09-0310 | 2024-10-0129 | CBCD Trading | 200 Feet - 7/8 Foam Type Transmission RF Cable | [19 empty] | RP-Agoo | NO | NP-53.9 - Small Value Procurement |  | 2024-10-06 | [5 empty] | 2024-10-08 | 2024-10-08 |  |  |  |  | GoP | 64000 | 64000 |  | 61000 | 61000
| 165 | 2024-09-0295 | 2024-10-0131 | CBCD Trading | 100 Pieces - T8 LED Light 18W 4FT Industrial Daylight Double Ended | [19 empty] | Property & Supply | NO | Shopping |  | 2024-09-05 | [5 empty] | 2024-10-08 | 2024-10-08 |  |  |  |  | GoP | 32000 | 32000 |  | 30500 | 30500
| 166 | 2024-09-0309 | 2024-10-0130 | Sagittarius Hardware Trading | 1 Piece - Safety Switch, 100 Ampere, Double Pole / Double Throw, 250 Volts Fusible, 29 Pieces - XLR Male Plug, 20 Pieces - XLR Female Plug, 20 Pieces - Mono Audio Plug Jack | [19 empty] | RP-Batanes | NO | NP-53.9 - Small Value Procurement |  | 2024-10-01 | [5 empty] | 2024-10-08 | 2024-10-08 |  |  |  |  | GoP | 38535 | 38535 |  | 37600 | 37600
| 167 | 2024-10-0327 | 2024-10-0132 | Music World | 1 Unit - Audio Mixer 16 Channels | [19 empty] | RP-Baguio | NO | NP-53.9 - Small Value Procurement |  | 2024-10-03 | [5 empty] | 2024-10-09 | 2024-10-09 |  |  |  |  | GoP | 14744.73 | 14744.73 |  | 14744.73 | 14744.73
| 168 | 2024-09-0314C | 2024-10-0133 | Dataview Computer Corporation | 2 Units - NV2 PCIE 4.0 NVME 500GB SSD | [19 empty] | Research | NO | NP-53.9 - Small Value Procurement |  | 2024-10-15 | [5 empty] | 2024-10-16 | 2024-10-16 |  |  |  |  | GoP | 6000 | 6000 |  | 5990 | 5990
| 169 | 2024-10-0234 | 2024-10-0134 | Halden General Merchandise | 1 Unit - Executive Chair Black | [19 empty] | Public Affairs | NO | NP-53.9 - Small Value Procurement |  | 2024-10-01 | [5 empty] | 2024-10-17 | 2024-10-17 |  |  |  |  | GoP | 10000 | 10000 |  | 8200 | 8200
| 170 | 2024-10-0319 | 2024-10-0135 | Sagittarius Hardware Trading | 4 Pieces - Eye Terminal Lugs 30mm3, 30 Meters - Royal Cord 30mm3 2 Core (Phelps Dodge), 8 Pieces - Clamp 30 Meters | [19 empty] | RP-Batanes | NO | NP-53.9 - Small Value Procurement |  | 2024-10-22 | [5 empty] | 2024-10-23 | 2024-10-23 |  |  |  |  | GoP | 46200 | 46200 |  | 44144 | 44144
| 171 | 2024-10-0316 | 2024-10-0136 | Great Country Auto Supply | 1 Piece - Timing Belt Small, 1 Pieces - Timing Belt (Big), 1 Piece - Tensioner Bearing, 1 Piece - Idler Bearing, 1 Set - Oil Seal | [19 empty] | General Services | NO | NP-53.9 - Small Value Procurement |  | 2024-10-15 | [5 empty] | 2024-10-30 | 2024-10-30 |  |  |  |  | GoP | 7200 | 7200 |  | 7000 | 7000
| 172 | 2024-10-0336 | 2024-11-0137 | Relujac Enterprise | 591 Pieces | [19 empty] | GAD | NO | NP-53.9 - Small Value Procurement |  | 2024-10-28 | [5 empty] | 2024-11-05 | 2024-11-05 |  |  |  |  | GoP | 206850 | 206850 |  | 118170.45 | 118170.45
| 173 | 2024-10-0364 | 2024-11-0138 | Cove Traders Battery | 1 Piece - Generator Set Battery 12V 80Ah | [19 empty] | RP-Marawi | NO | NP-53.9 - Small Value Procurement |  | 2024-10-31 | [5 empty] | 2024-11-06 | 2024-11-06 |  |  |  |  | GoP | 10250 | 10250 |  | 10250 | 10250
| 175 | 2024-10-0353 | 2024-11-0141 | Dagupan Audio Electronics & Electrical Merchandising | 1 Unit - Console 6 Channel IMIX Brand | [19 empty] | RP-Dagupan | NO | NP-53.9 - Small Value Procurement |  | 2024-10-28 | [5 empty] | 2024-10-06 | 2024-10-06 |  |  |  |  | GoP | 14500 | 14500 |  | 14500 | 14500
| 176 | 2024-10-0354 | 2024-11-0142 | National Bazaar Electrical Appliance | 1 Unit - Audio Mixer Konzert MX-12 | [19 empty] | RP-Agoo | NO | NP-53.9 - Small Value Procurement |  | 2024-10-29 | [5 empty] | 2024-11-06 | 2024-11-06 |  |  |  |  | GoP | 11400 | 11400 |  | 11400 | 11400
| 177 | 2024-10-03440 | 2024-11-0145 | Great Country Auto Supply | 2 Sets - Clutch Assembly | [19 empty] | General Services | NO | NP-53.9 - Small Value Procurement |  | 2024-11-05 | [5 empty] | 2024-11-07 | 2024-11-07 |  |  |  |  | GoP | 16000 | 16000 |  | 14000 | 14000
| 178 | 2024-10-0326 | 2024-11-0144 | Sagittarius Hardware Trading | 1 Unit - Executive Chair Black | [19 empty] | Director's Office | NO | NP-53.9 - Small Value Procurement |  | 2024-11-05 | [5 empty] | 2024-11-07 | 2024-11-07 |  |  |  |  | GoP | 20000 | 20000 |  | 15500 | 15500
| 179 | 2924-10-0363 | 2024-11-0143 | Davao Electrical Sales | 2 Sets - LED Track Light with Track Light | [19 empty] | RP-Davao | NO | NP-53.9 - Small Value Procurement |  | 2024-10-29 | [5 empty] | 2024-11-06 | 2024-11-06 |  |  |  |  | GoP | 6004 | 6004 |  | 6004 | 6004
| 180 | 2024-10-0350 | 2024-11-0140 | F & E Enterprises, Inc. | 5 Pieces - 205/65/R15 Tire, 25 Pieces - Quick Stick 3/4 | [19 empty] | RP-Iloilo | NO | NP-53.9 - Small Value Procurement |  | 2024-10-29 | [5 empty] | 2024-11-06 | 2024-11-06 |  |  |  |  | GoP | 29250 | 29250 |  | 29250 | 29250
| 181 | 2024-07-0257G | 2024-11-0146 | Dataview Computer Corporation | 2 Units - Printer Laserjet | [19 empty] | BAC | NO | Shopping |  | 2024-11-05 | [5 empty] | 2024-11-07 | 2024-11-07 |  |  |  |  | GoP | 40000 | 40000 |  | 21000 | 21000
| 182 | 2024-10-0349 | 2024-11-0147 | Kellitech Import & Export, Corp. | 50 Pieces - Archfile Binder Color Green, 50 Pieces - Archfile Binder Color Black, 200 Pieces - Archfile Binder Color Blue | [19 empty] | Finance | NO | Shopping |  | 2024-11-06 | [5 empty] | 2024-11-11 | 2024-11-11 |  |  |  |  | GoP | 49500 | 49500 |  | 49500 | 49500
| 183 | 2024-10-0366D | 2024-11-0148 | Photoline | 1 Unit - Video Camera, Canon EOS 1500D | [19 empty] | RP-Naga | NO | NP-53.9 - Small Value Procurement |  | 2024-09-30 | [5 empty] | 2024-11-11 | 2024-11-11 |  |  |  |  | GoP | 33998 | 33998 |  | 33998 | 33998
| 184 | 2024-10-0366B | 2024-11-0149 | 3GX Solutions | 1 Unit- Audio Mixer Kevier | [19 empty] | RP-Naga | NO | NP-53.9 - Small Value Procurement |  | 2024-09-30 | [5 empty] | 2024-11-11 | 2024-11-11 |  |  |  |  | GoP | 14818 | 14818 |  | 14818 | 14818
| 185 | 2024-10-0366F | 2024-11-0150 | EJ'S General Merchandising | 1 Unit - DSLR Camera Kit 24.1 Mega Pixel 7.5cm / 3.0” LCD Full HD 1080/30p Video Recording, 1 Unit - Audio Mixer, 8-12 Channel with Multi Output / Input | [19 empty] | RP-Gingoog | NO | NP-53.9 - Small Value Procurement |  | 2024-10-23 | [5 empty] | 2024-11-11 | 2024-11-11 |  |  |  |  | GoP | 48000 | 48000 |  | 48000 | 48000
| 186 | 2024-10-0366G | 2024-11-0151 | Music World | 1 Unit - Audio Mixer 16 Channel | [19 empty] | RP-Bontoc | NO | NP-53.9 - Small Value Procurement |  | 2024-10-17 | [5 empty] | 2024-11-11 | 2024-11-11 |  |  |  |  | GoP | 14744.73 | 14744.73 |  | 14744.73 | 14744.73
| 187 | 2024-09-0337 | 2024-11-0153 | Halden General Merchandise | 2 Pieces - UV Light Lamp | [19 empty] | General Services | NO | NP-53.9 - Small Value Procurement |  | 2024-10-10 | [5 empty] | 2024-11-12 | 2024-11-12 |  |  |  |  | GoP | 7000 | 7000 |  | 5600 | 5600
| 188 | 2024-10-0355 | 2024-11-0154 | Silvanus Non-Specialized Wholesale Trading | 1 Unit - Smart TV 65" LED with WEB OS | [19 empty] | Director's Office | NO | NP-53.9 - Small Value Procurement |  | 2024-10-28 | [5 empty] | 2024-11-12 | 2024-11-12 |  |  |  |  | GoP | 45000 | 45000 |  | 42875 | 42875
| 189 | 2024-10-0338 | 2024-11-0152 | Halden General Merchandise | 1 Unit - 7 cubic feet Two-Door Inverter Refrigerator, 1 Unir - 1.8L Stainless Steel Electric Kettle | [19 empty] | GAD |  | NP-53.9 - Small Value Procurement |  | 2024-11-07 | [5 empty] | 2024-11-12 | 2024-11-12 |  |  |  |  | GoP | 21000 | 21000 |  | 20755 | 20755
| 190 | 2024-10-0331 | 2024-11-0155 | Dataview Computer Corporation | 2 Units - Computer Monitor with HDMI Port, 3 Units - UPS | [19 empty] | Finance | NO | NP-53.9 - Small Value Procurement |  | 2024-11-07 | [5 empty] | 2024-11-13 | 2024-11-13 |  |  |  |  | GoP | 34500 | 34500 |  | 20975 | 20975
| 191 | 2024-10-0359 | 2024-11-0157 | CBCD Trading | 12 Pieces - DB15 Connector (Male) 2 Row, 12 Pieces - DB15 Shell (2 Row), 20 Pieces - XLR Connector (Male), 20 Pieces - XLR Connector (Female) | [19 empty] | Engineering |  | NP-53.9 - Small Value Procurement |  | 2024-10-29 | [5 empty] | 2024-11-13 | 2024-11-13 |  |  |  |  | GoP | 6720 | 6720 |  | 6668 | 6668
| 192 | 2024-10-0358 | 2024-11-0156 | CBCD Trading | 12 Pieces - DB15 Connector (Male) 2 Row, 12 Pieces - DB15 Shell (2 Row), 20 Pieces - XLR Connector (Male), 20 Pieces - XLR Connector (Female) | [19 empty] | Engineering |  | NP-53.9 - Small Value Procurement |  | 2024-10-29 | [5 empty] | 2024-11-13 | 2024-11-13 |  |  |  |  | GoP | 6720 | 6720 |  | 6668 | 6668
| 193 | 2024-10-0366H | 2924-11-0169 | LCPC Enterprise, Inc. | 1 Unit - Computer Desktop Acer | [19 empty] | RP-Naga | NO | NP-53.9 - Small Value Procurement |  | 2024-10-21 | [5 empty] | 2024-11-19 | 2024-11-19 |  |  |  |  | GoP | 35415 | 35415 |  | 35415 | 35415
| 194 | 2024-10-0366K | 2024-11-0158 | Abenson Liberty Appliance, Inc. | 1 Unit - 2.0HP Airconditioner, Brand Condura Brand With free installation | [19 empty] | RP-Naga | NO | NP-53.9 - Small Value Procurement |  | 2024-10-21 | [5 empty] | 2024-11-19 | 2024-11-19 |  |  |  |  | GoP | 39998 | 39998 |  | 39998 | 39998
| 195 | 2024-10-0366L | 2024-11-0159 | TCL Merchandise Brokeragem Inc. | 4 Units- Clerical Table | [19 empty] | RP-Naga | NO | NP-53.9 - Small Value Procurement |  | 2024-10-28 | [5 empty] | 2024-11-19 | 2024-11-19 |  |  |  |  | GoP | 19580 | 19580 |  | 19580 | 19580
| 106 | 2020-10-0366J | 2024-11-0161 | Computer Bucket Computer Parts and Accessories | 1 Unit - Desktop Computer Ryzen 5700G | [19 empty] | RP-Dagupan | NO | NP-53.9 - Small Value Procurement |  | 2024-10-08 | [5 empty] | 2024-11-20 | 2024-11-20 |  |  |  |  | GoP | 39881 | 39881 |  | 39881 | 39881
| 197 | 2024-11-0377 | 2024-11-0162 | Virac Dotcom and General Merchandise | 1 Unit - Desktop Computer Ryzen 5 | [19 empty] | RP-Virac | NO | NP-53.9 - Small Value Procurement |  | 2024-10-18 | [5 empty] | 2024-11-20 | 2024-11-20 |  |  |  |  | GoP | 43554 | 43554 |  | 43554 | 43554
| 198 | 2024-10-0366M | 2024-11-0164 | Dataworld Computer Center | 1 Unit - Desktop Computer AMD Reyzen 5 with Complete Accessories | [19 empty] | RP-Cagayan de oro | NO | NP-53.9 - Small Value Procurement |  | 2024-10-18 | [5 empty] | 2024-10-20 | 2024-10-20 |  |  |  |  | GoP | 44000 | 44000 |  | 44000 | 44000
| 199 | 2024-11-0389 | 2024-11-0165 | Dwinar Computer Center | 1 Unit - 8 Channel Audio Mixer | [19 empty] | RP-Davao | NO | NP-53.9 - Small Value Procurement |  | 2024-11-12 | [5 empty] | 2024-11-20 | 2024-11-20 |  |  |  |  | GoP | 14950 | 14950 |  | 14950 | 14950
| 200 | 2024-10-0366I | 2024-11-0163 | ABANA Computer Services & General Merchandise | 1 Unit - Computer Desktop Set | [19 empty] | RP-Tuguegarao | NO | NP-53.9 - Small Value Procurement |  | 2024-10-18 | [5 empty] | 2024-11-20 | 2024-11-20 |  |  |  |  | GoP | 40980 | 40980 |  | 40980 | 40980
| 201 | 2024-10-0366O | 2024-11-0166 | 4RMTech Gadgets Shop | 1 Unit - DSLR Video Camera | [19 empty] | RP-Cebu | NO | NP-53.9 - Small Value Procurement |  | 2024-10-15 | [5 empty] | 2024-11-20 | 2024-11-20 |  |  |  |  | GoP | 31995 | 31995 |  | 31995 | 31995
| 202 | 2024-10-0366P | 2024-11-0167 | AC/DC Component Part Sale and Service Center, Inc. | 1 Unit - Console Mixer 12 Channel Trident | [19 empty] | RP-Cebu | NO | NP-53.9 - Small Value Procurement |  | 2024-10-04 | [5 empty] | 2024-11-21 | 2024-11-21 |  |  |  |  | GoP | 14500 | 14500 |  | 14500 | 14500
| 203 | 2024-10-0366Q | 2924-11-0168 | Nutech Marketing | 1 Unit - Desktop Computer Set ASUS Tower | [19 empty] | RP-Cebu | NO | NP-53.9 - Small Value Procurement |  | 2024-10-11 | [5 empty] | 2024-11-21 | 2024-11-21 |  |  |  |  | GoP | 41500 | 41500 |  | 41500 | 41500
| 204 | 2024-10-0081 | 2024-11-0036 | 88 Traders & Contracting Services Corp. | 1 Unit - Repair of Aircon of Toyota Avanza P5700 | [19 empty] | General Services | NO | NP-53.9 - Small Value Procurement |  | 2024-10-07 | [5 empty] | 2024-11-27 | 2024-11-27 |  |  |  |  | GoP | 39621.12 | 39621.12 |  | 39621.12 | 39621.12
| 205 | 2024-09-0314D | 2024-11-0169 | Mtech IT Solutions | 5 Units - PC Desktop Monitor, 24” Inches LED AOC 24B36H IPS, 1 Unit - All-in-One Printer /Scanner (A4 and Long Documents) Epson Ecotank 5290 | [19 empty] | RP-Butuan | NO | Shopping |  | 2024-11-21 | [5 empty] | 2024-11-26 | 2024-11-26 |  |  |  |  | GoP | 57000 | 57000 |  | 42700 | 42700
| 206 | 2024-11-0381 | 2024-11-0170 | Media Convergence Inc, | 1 Unit - LU2000 Rackmount HEVC/H.264 Server, 1 Unit - LiveU LU-Smart Plan for 1 Year | [19 empty] | Engineering | NO | NP-53.9 - Small Value Procurement |  | 2024-11-21 | [5 empty] | 2024-11-26 | 2024-11-26 |  |  |  |  | GoP | 979800 | 979800 |  | 979800 | 979800
| 207 | 2024-10-0364 | 2024-11-0171 | Regence Sales & Services | 1 Piece - Generator Battery 12V 80Ah | [19 empty] | RP-Marawi | NO | NP-53.9 - Small Value Procurement |  | 2024-11-21 | [5 empty] | 2024-11-26 | 2024-11-26 |  |  |  |  | GoP | 11000 | 11000 |  | 11000 | 11000
| 208 | 2024-10-0366R | 2024-11-0172 | Willy & Sons Corp. | 1 Unit - Water Dispenser with Hot and Cold, Bottom Load | [19 empty] | RP-Alert | NO | NP-53.9 - Small Value Procurement |  | 2024-10-30 | [5 empty] | 2024-11-27 | 2024-11-27 |  |  |  |  | GoP | 9998 | 9998 |  | 9998 | 9998
| 209 | 2024-10-0366S | 2024-11-0173 | Laoag Astronic Auto Supply | 1 Unit - 2SM Motolite Gold Maintenance Free | [19 empty] | RP-Laoag | NO | NP-53.9 - Small Value Procurement |  | 2024-10-14 | [5 empty] | 2024-11-27 | 2024-11-27 |  |  |  |  | GoP | 7325 | 7325 |  | 7325 | 7325
| 210 | 2024-10-0084 | 2024-11-0037 | Frigid Zone Auto Aircon Sepcialist Co. | 1 Lot - Pull-down Evaporator for General Cleaning and Leaktest | [19 empty] | General Services | NO | NP-53.9 - Small Value Procurement |  | 2024-10-10 | [5 empty] | 2024-11-28 | 2024-11-28 |  |  |  |  | GoP | 26880 | 26880 |  | 26880 | 26880
| 211 | 2024-11-0384 | 2024-12-0175 | Timog Tirehaus Corporation | 3 Sets - Battery, NS 60 ZR | [19 empty] | General Services | NO | NP-53.9 - Small Value Procurement |  | 2024-11-27 | [5 empty] | 2024-12-02 | 2024-12-02 |  |  |  |  | GoP | 25500 | 25500 |  | 25200 | 25200
` | 212 | 2024-11-0101 | 2024-12-0038 | PGP Travel & Tours | 1 Lot - Van Rental December 02-11, 2024, Metro Manila and Outside Metro Manila (Excluding Parking, Toll Fees, Meals, and Fuel) | [19 empty] | PAD | NO | NP-53.9 - Small Value Procurement |  | 2024-11-28 | [5 empty] | 2024-12-02 | 2024-12-02 |  |  |  |  | GoP | 105000 | 105000 |  | 83500 | 83500
| 213 | 2024-11-0370 | 2024-12-0176 | Halden General Merchandise | 1 Unit - Filing Cabinet Vertical (4 Drawers), 2 Unit - Stand Fan (Black) 3 Blades, 1 Unit - Oven Toaster | [19 empty] | COA | NO | NP-53.9 - Small Value Procurement |  | 2024-11-27 | [5 empty] | 2024-12-03 | 2024-12-03 |  |  |  |  | GoP | 16000 | 16000 |  | 15500 | 15500
| 214 | 2024-10-0340 | 2024-12-0177 | Halden General Merchandise | 3 Units - Modern Lifestyle 5-Shelf Bolted Steel Shelving Unit | [19 empty] | Finance | NO | NP-53.9 - Small Value Procurement |  | 2024-11-27 | [5 empty] | 2024-12-03 | 2024-12-03 |  |  |  |  | GoP | 12000 | 12000 |  | 10500 | 10500
| 215 | 2024-11-0371 | 2024-12-0178 | Halden General Merchandise | 2 Units - External Hard Drive, 1 Unit - Paper Tray 3 Layers | [19 empty] | CO0 | NO | Shopping |  | 2024-11-27 | [5 empty] | 2024-12-03 | 2024-12-03 |  |  |  |  | GoP | 6100 | 5100 |  | 5450 | 5450
| 216 | 2024-10-0366C | 2024-11-0179 | Double K Computer Retail & Services | 1 Unit - Desktop Computer, 1 Unit - Audio Mixer, 1 Unit - Video Camera | [19 empty] | RP-Laoag | NO | NP-53.9 - Small Value Procurement |  | 2024-10-30 | [5 empty] | 2024-11-28 | 2024-11-28 |  |  |  |  | GoP | 91765 | 91765 |  | 91765 | 91765
| 217 | 2024-11-0383 | 2024-0180 | Legazpi Grace Home Builders Supply, Inc. | 1 Lot - Water Piping Materials | [19 empty] | RP-Alert | NO | NP-53.9 - Small Value Procurement |  | 2024-11-11 | [5 empty] | 2024-11-28 | 2024-11-28 |  |  |  |  | GoP | 36117 | 36117 |  | 36114 | 36114
| 218 | 2024-11-0411 | 2024-12-0182 | Concept Computer Center | 1 Unit - Desktop Computer Set Intel Core i5-12th Gen Processor | [19 empty] | RP-Iloilo | NO | NP-53.9 - Small Value Procurement |  | 2024-11-22 | [5 empty] | 2024-12-05 | 2024-12-05 |  |  |  |  | GoP | 43147 | 43147 |  | 43147 | 43147
| 219 | 2024-11-0412 | 2024-12-0186 | Viracdotcom Enterprises | 1 Unit - IMIX 5 Channel Mixer Powered 250 Watts | [19 empty] | RP-Virac | NO | NP-53.9 - Small Value Procurement |  | 2024-11-21 | [5 empty] | 2024-12-05 | 2024-12-05 |  |  |  |  | GoP | 14490 | 14490 |  | 14490 | 14490
| 220 | 2024-11-0397 | 2024-12-0183 | Halden General Merchandise | 1 Lot - Various Office Supplies | [19 empty] | Network | NO | Shopping |  | 2024-11-22 | [5 empty] | 2024-12-05 | 2024-12-05 |  |  |  |  | GoP | 18540 | 18540 |  | 14312 | 14312
| 221 | 2024-11-0385 | 2024-12-0189 | Great Country Auto Supply | 2 Pieces - Electric Fan Motor | [19 empty] | General Services | NO | NP-53.9 - Small Value Procurement |  | 2024-12-02 | [5 empty] | 2024-12-06 | 2024-12-06 |  |  |  |  | GoP | 16000 | 16000 |  | 15200 | 15200
| 222 | 2024-11-0413C | 2024-12-0188 | Viracdotcom Enterprises | 1 Unit - Video Camera | [19 empty] | RP-Virac | NO | NP-53.9 - Small Value Procurement |  | 2024-11-21 | [5 empty] | 2024-12-05 | 2024-12-05 |  |  |  |  | GoP | 33600 | 33600 |  | 33600 | 33600
| 223 | 2024-11-0494 | 2024-12-0184 | MRM Electronic Center | 1 Unit - Mixer, Yamaha Model No. MG12XU | [19 empty] | RP-Iloilo | NO | NP-53.9 - Small Value Procurement |  | 2024-11-22 | [5 empty] | 2024-12-05 | 2024-12-05 |  |  |  |  | GoP | 14800 | 14800 |  | 14800 | 14800
| 224 | 2024-11-0406 | 2024-12-0185 | CITI Hardware | 1 Unit - Panel Door | [19 empty] | RP-Davao | NO | NP-53.9 - Small Value Procurement |  | 2024-11-25 | [5 empty] | 2024-12-05 | 2024-12-05 |  |  |  |  | GoP | 4500 | 4500 |  | 4500 | 4500
| 225 | 2024-11-0398 | 2024-12-0187 | Olivan Hardware | 5 Units - Ergonomic Office Chair | [19 empty] | RP-Naga | NO | NP-53.9 - Small Value Procurement |  | 2024-11-14 | [5 empty] | 2024-12-05 | 2024-12-05 |  |  |  |  | GoP | 21250 | 21250 |  | 21250 | 21250
| 226 | 2024-11-0101B | 2024-12-0039 | 88 Traders & Contracting Services Corp. | 2 Units - Replacement of Bypass and Bypass Hose, Hyundai Starex KOU-407 and KOU-405 | [19 empty] | General Services | NO | NP-53.9 - Small Value Procurement |  | 2024-11-29 | [5 empty] | 2024-12-06 | 2024-12-06 |  |  |  |  | GoP | 47712 | 47712 |  | 47712 | 47712
| 227 | 2024-11-0093 | 2024-12-0040 | Frigid Zone Auto Aircon Sepcialist Co. | 1 Lot - Repair of Aircon of Toyota Avanza P5V-554 | [19 empty] | General Services | NO | NP-53.9 - Small Value Procurement |  | 2024-11-13 | [5 empty] | 2024-12-06 | 2024-12-06 |  |  |  |  | GoP | 25760 | 25760 |  | 25760 | 25760
| 228 | 2024-11-0094 | 2024-12-041 | Frigid Zone Auto Aircon Sepcialist Co. | 1 Lot - Repair of Aircon of Toyota Avanza P5S-529 | [19 empty] | General Services | NO | NP-53.9 - Small Value Procurement |  | 2024-11-13 | [5 empty] | 2024-12-06 | 2024-12-06 |  |  |  |  | GoP | 56000 | 56000 |  | 56000 | 56000
| 229 | 2024-09-0314H | 2024-12-0190 | 8BTSI Corporation | 1 Lot - Spare Parts Elonos 20KW FM Transmitter, 3 Pieces - Elonos Acquisition Board, 3 Pieces - Elonos Power Supply 3Kw-5Kw, 50V-65A, 3 Pieces - Elonos RF Pallet Board with RF Devices, Engineering Services, Installation, Testing and Commissioning | [19 empty] | Engineering | NO | Direct Contracting | 2024-09-23 | [6 empty] | 2024-12-10 | 2024-12-10 |  |  |  |  | GoP | 1033300 | 1033300 |  | 1033300 | 1033300
| 230 | 202411-0413E | 2024-12-0192 | RYT Click Electronic Parts & Services | 1 Unit - Airconditioning Unit, Window Type, Inverter, Smart Cool Series | [19 empty] | RP-Naga | NO | NP-53.9 - Small Value Procurement | 2024-11-15 | [6 empty] | 2024-12-10 | 2024-12-10 |  |  |  |  | GoP | 45880 | 45880 |  | 45880 | 45880
| 231 | 2924-11-0374 | 2024-12-0191 | Silvanus Non-Specialized Wholesale Trading | 1 Unit - LED Smart TV 55” 4K Resolution HDR Google TV, 1 Unit - LED Smart TV 32” 4K Resolution HDR Google TV 1 Unit - TV Stand, removable floor mounted 360 degrees rotation for 32” to 75. 1 Unit - Vacuum Cleaner Heavy Duty 160W inverter motor, HEPA filtration, 4 step telescopic pipe, cyclone system, thumb touch control, LED indicator, Max running time 80 mins | [19 empty] | FM1 | NO | NP-53.9 - Small Value Procurement | 2024-11-27 | [6 empty] | 2024-12-10 | 2024-12-10 |  |  |  |  | GoP | 117000 | 117000 |  | 96250 | 96250
| 232 | 2024-10-0092 | 2024-11-0037B | Jay L. Po Real Estate Lessor | 1 Lot - One Year Renewable Office/Studio Space DXBN-Butuan | [19 empty] | RP-Butuan | NO | NP-53.9 - Small Value Procurement | 2024-10-28 | [6 empty] | 2024-11-29 | 2024-11-29 |  |  |  |  | GoP | 68000 | 68000 |  | 68000 | 68000
| 233 | 2024-12-0422 | 2024-12-0193 | Martin Tires and Battery | 2 Pieces - 12V Battery for 14V Generator Set | [19 empty] | RP-Tabuk | NO | NP-53.9 - Small Value Procurement | 2024-12-03 | [6 empty] | 2024-12-17 | 2024-12-17 |  |  |  |  | GoP | 13144 | 13144 |  | 13144 | 13144
| 234 | 2024-12-0103 | 2024-12-0042 | Best Choice Gourmet & Catering Services | 1 Lot - Meals for PBS GAD Year-End Assessment 2024 December 18, 2024 | [19 empty] | GAD | NO | NP-53.9 - Small Value Procurement | 2024-12-11 | [6 empty] | 2024-12-17 | 2024-12-17 |  |  |  |  | GoP | 180000 | 180000 |  | 179000 | 179000
| 235 | 2024-11-0396 |  | 168 Security, Inc. | 1 Lot - Contract for the Provision of Security Agency Services for twelve (12) months | [19 empty] | Administrative | YES | Competitive Bidding | 2024-11-12 | 2024-11-15 | 2024-11-25 | 2024-12-09 | 2024-12-09 | 2024-12-17 | 2024-12-17 | 2024-12-18 | 2025-01-06 |  |  |  |  | GoP | 29620000 | 29620000 |  | 29367693.96 | 29367693.96 |  | Philippine Chamber of Commerce and Industry, , MR. AMADOR ASTUDILLO, President of Procurement Watch and MS. CLARICE E. PALITIC, Audit Team Leader/Resident Auditor in BBS of the Commission on Audit | 2024-11-25 | 2024-12-09 | 2024-12-09 | 2024-12-17 | 2024-12-17
| 236 | 2024-12-0420 | 2024-12-0194 | Dataview Computer Corporation | 1 Unit - Ink Tank Printer with WIFI (print, scan and copy) | [19 empty] | RP-Alert | NO | Shopping |  | 2024-12-16 | [5 empty] | 2024-12-28 | 2024-12-28 |  |  |  |  | GoP | 13495 | 13495 |  | 13495 | 13495
| 237 | 2024-12-0102 |  | Verjandel Hotel | 1 Lot - Live-In Workshop with Accommodation and Venue | [19 empty] | Network | NO | NP-53.9 - Small Value Procurement |  | 2024-12-02 | [5 empty] | 2024-12-28 | 2024-12-28 |  |  |  |  | GoP | 142400 | 142400 |  | 138500 | 138500
| 238 | 2024-11-0403 |  | Silvanus Non-Specialized Wholesale Trading | 10 Units - Portable Power Station | [19 empty] | Engineering | NO | NP-53.9 - Small Value Procurement |  | 2024-11-25 | [6 empty] | 2024-12-28 |  |  |  |  | GoP | 420000 | 420000 |  | 389137.5 | 389137.5
Total Alloted Budget of Procurement Activities | [41 empty] | 64306851.21
Total Contract Price of Procurement Actitvites Conducted | [44 empty] | 62488800.58
Total Savings (Total Alloted Budget - Total Contract Price) | [41 empty] | 1818050.63
0N-GOING PROCUREMENT ACTIVITIES
0
Total Alloted Budget of On-going Procurement Activities | [41 empty] | 0
[25 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
[25 empty] | RODNEY O. VILLANUEVA | [10 empty] | ALAN L. ALLANIGUE | [10 empty] | FERNANDO A. SANGA
[25 empty] | BAC Secretariat Head | [10 empty] | BAC Chairperson | [10 empty] | Director IV
Head of the Procuring Entity

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement