## PMR
Bureau of Broadcast Services | [11 empty] | Procurement Monitoring Report as of 30 June 2025
[5 empty] | Actual Procurement Activities | [20 empty] | ABC (PhP) |  |  | Contract Cost (PhP) |  |  |  |  | Date of Receipt of Invitation
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/ Open of Bids6 | Bid Eval 7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP)
COMPLETED PROCUREMENT ACTIVITIES | [31 empty] | -
| 90 Pieces - Floor Tiles (60 x 60), 5 Sacks - Cement, 50 Sacks - Binistay (Sand) | COA | NO | NP-53.9 - Small Value Procurement |  | 2025-01-07 | [7 empty] | 2025-01-09 |  |  |  | 2025-01-09 | [6 empty] | GoP | 33950 | 33950 |  | 33950 | 33950 |  | -
NO | 1 Lot - Transmitter Lot Rental of DZRA-Bontoc (Renwal) Lease of 1000sqm. Tax Declaration Land and Improvements found therein located at Mt. Pokis, Bontoc Mountain Province (January to December 2025) | RP-Bontoc | NO | GPPB Resolution No, 06-2022 Renewal of Recurring Regular Services |  | 2025-01-02 | [7 empty] | 2025-01-06 |  |  |  | 2025-01-06 | [6 empty] | GoP | 240000 | 240000 |  | 240000 | 240000
| 1 Lot - One (1) Year Renewal of Lease of Studio/Office Space for DXBN-Butuan and Additional two (2) months security deposit |  | NO | GPPB Resolution No, 06-2022 Renewal of Recurring Regular Services |  | 2025-01-06 | [7 empty] | 2025-01-07 |  |  |  | 2025-01-07 | [6 empty] | GoP | 511484 | 511484 |  | 511484 | 511484
| 1 Lot - One (1) Year Renewal of Rental Office of DXIM Radyo Pilipinas Cagayan de Oro |  | NO | GPPB Resolution No, 06-2022 Renewal of Recurring Regular Services |  | 2025-01-06 | [7 empty] | 2025-01-07 |  |  |  | 2025-01-07 | [6 empty] | GoP | 540920.52 | 540920.52 |  | 540920.52 | 540920.52
| 1 Unit - 1500D Kit (EF S18-55 IS II) Cameraloor Tile (60x60) | RP-Batanes | NO | NP-53.9 - Small Value Procurement |  | 2025-01-07 | [7 empty] | 2025-01-09 |  |  |  | 2025-01-09 | [6 empty] | GoP | 34000 | 34000 |  | 34000 | 34000
| 3 Pieces - Office Chair, 2 Units - PC Monitor Wire 5 Pieces - Cover Cable Holder, 1 Units - Computer Speaker | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-01-07 | [7 empty] | 2025-01-09 |  |  |  | 2025-01-09 | [6 empty] | GoP | 25085 | 25085 |  | 23885 | 23885
| 1 Unit - Television 32" Skyworth Google TV, 1 Unit - Office Chair | RP-Borongan | NO | NP-53.9 - Small Value Procurement |  | 2025-01-09 | [7 empty] | 2025-01-13 |  |  |  | 2025-01-13 | [6 empty] | GoP | 16500 | 16500 |  | 16500 | 16500
| 1 Set - Air Filter, 1 Piece - Fuel Filter, 1 Piece - Ball Joint Left Upper, 1 Piece - Ball Joint Right Lower | RP-Marawi | NO | NP-53.9 - Small Value Procurement |  | 2025-01-09 | [7 empty] | 2025-01-13 |  |  |  | 2025-01-13 | [6 empty] | GoP | 5980 | 5980 |  | 5980 | 5980
| 1 Unit - Executive Chair | PAD | NO | NP-53.9 - Small Value Procurement |  | 2025-01-07 | [7 empty] | 2025-01-16 |  |  |  | 2025-01-16 | [6 empty] | GoP | 7000 | 7000 |  | 7000 | 7000
| 1 Unit - Multi-Purpose Audio Mixer | RP-Batanes | NO | NP-53.9 - Small Value Procurement |  | 2025-01-07 | [7 empty] | 2025-01-16 |  |  |  | 2025-01-16 | [6 empty] | GoP | 15000 | 15000 |  | 15000 | 15000
| 1 Lot - Lease of Nine (9) Units Multi-Functional Photocopying Machine (Digital Copier, Network Peinter/Scanner) 9 Units | Finance | NO | NP-53.9 - Small Value Procurement |  | 2025-01-07 | [7 empty] | 2025-01-16 |  |  |  | 2025-01-16 | [6 empty] | GoP | 388800 | 388800 |  | 388800 | 388800
| 1 Lot - Various Office Supplies | Property & Supply | NO | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS |  | 2025-01-09 | [7 empty] | 2025-01-22 |  |  |  | 2025-01-22 | [6 empty] | GoP | 394000 | 394000 |  | 283947.5 | 283947.5
| 1 Set - Battery NS60 | General Services | NO | NP-53.9 - Small Value Procurement |  | 2025-01-09 | [7 empty] | 2025-01-24 |  |  |  | 2025-01-24 | [6 empty] | GoP | 8500 | 8500 |  | 8400 | 8400
| 1 Lot - Various Cleaning Supplies | Property & Supply | NO | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS |  | 2025-01-09 | [7 empty] | 2025-01-23 |  |  |  | 2025-01-23 | [6 empty] | GoP | 70250 | 70250 |  | 39990 | 39990
| 6 Pieces - ZC100/300 Series Card Printer Ribbon | Personnel Section | NO | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS |  | 2025-01-09 | [7 empty] | 2025-01-27 |  |  |  | 2025-01-27 | [6 empty] | GoP | 48000 | 48000 |  | 43800 | 43800
| 13 Units - Smart Phone, Iphone 16 128GB Warranty: 1 Year Warranty, 13 Units - 2.4GHz Wireless Microphone for IOS Boya BY-V20 One Trigger-Two Warranty: 1 Year, 13 Units - Smart Phone Triood, BAVIN DS5208 Professional Tripod Stand Portable Adjustable Height, Phone Holder for SLR, DSLR Digital Camera, Warranty: 6 Months, 13 Units - 3-Axis GIMBAL Stabilizer Hohem iStrady Mobile Plus Kit 3-Axis, Smartphone Gimbal Stabilizer with Magnetic Warranty: 6 Months | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-01-09 | [7 empty] | 2025-01-27 |  |  |  | 2025-01-27 | [6 empty] | GoP | 979800 | 979800 |  | 875784 | 875784
| 45 Pieces - 0.30 x 0.30m Glossy Floor Tiles , 3 Pieces - PVC Fluted Wall Panel 8” x 2.90m, 1 Box - 1” Metal Black Screw (100pcs/box) | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-01-15 | [7 empty] | 2025-01-28 |  |  |  | 2025-01-28 | [6 empty] | GoP | 7600 | 7600 |  | 6735 | 6735
| 3 Units - 2.0 hP Split Type Wall Mounted Super Inverter ACU, 4 Units - 3.0 HP Split Type Wall Mounted Super Inverter ACU | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-01-16 | [7 empty] | 2025-01-30 |  |  |  | 2025-01-30 | [6 empty] | GoP | 653000 | 653000 |  | 526000 | 526000
| 6 Units - Office Chair for Announcer’s Booth, 4 Units - Office Chair for Guest, 7 Units - Spotlight for Announcer’s Booth | RP-Albay | NO | NP-53.9 - Small Value Procurement |  | 2025-01-09 | [7 empty] | 2025-01-30 |  |  |  | 2025-01-30 | [6 empty] | GoP | 50480 | 50480 |  | 43500 | 43500
| 1 Lot - 80 Packs (12 Pieces per Pack) Acoustic Panels Sound Proof Padded Beveled Edge Polyester Fiber Panels, High Density Accoutic Treatment Wall Decoration for Home Office Studio 12” x 12” x 0.35” inch | RP-Palawan | NO | NP-53.9 - Small Value Procurement |  | 2025-01-09 | [7 empty] | 2025-01-30 |  |  |  | 2025-01-30 | [6 empty] | GoP | 92000 | 92000 |  | 90000 | 90000
| 1 Unit - Soldering Gun Kit, 100W/230V, 1 Unit - Analog Multi-Tester, 1 Unit - Soldering Pump (Desoldering Tool), 1 Unit - Portable AM/FM Digital Radio | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-01-15 | [7 empty] | 2025-02-04 |  |  |  | 2025-02-04 | [6 empty] | GoP | 8200 | 8200 |  | 7260 | 7260
| 1 Lot - Supply of Labor and Parts for the repair of 225KVA Cummins Generator Set @ Site: PBS, Visayas Avenue, Quezon City | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-01-15 | [7 empty] | 2025-02-05 |  |  |  | 2025-02-05 | [6 empty] | GoP | 59000 | 59000 |  | 54378 | 54378
| 1 Lot - Repair of ACU of Toyota Avanza P5-V610 (Repair and Replace Defective Parts of ACU) | General Services | NO | NP-53.9 - Small Value Procurement |  | 2025-01-15 | [7 empty] | 2025-02-05 |  |  |  | 2025-02-05 | [6 empty] | GoP | 57120 | 57120 |  | 48000 | 48000
| 1 Lot - Monthly Subscription of Satellite Internet Plan with Unlimited Data for twelve (12) months | Engineeeing | NO | GPPB Resolution No. 41-2017 |  | 2025-02-17 | [7 empty] | 2025-01-15 |  |  |  | 2025-01-15 | [6 empty] | GoP | 432000 | 432000 |  | 432000 | 432000 |  |  | GPPB Resolution No. 41-2017
| 20 Units - Push to Talk Over Cellular (PoC) Radio Service Monthly Subscription (January to February) | Engineeeing | NO | GPPB Resolution No. 41-2017 |  | 2025-01-03 | [11 empty] | 2025-01-03 | [6 empty] | GoP | 26835.2 | 26835.2 |  | 26835.2 | 26835.2
| 2 Units - High-End Branded Desktop Computer for Streaming, Dell XPS 8960 Desktop Computer, 2 Units - Uninterruptible Power Supply, APC UPS BV10001, MS, 1000VA, 2 Units - HDMI Cable 5 Meters, Offer: Vention HDMI Cable 5 Meters, 3 Units - BNC HD-SDI 3CFB Low Loss SDI Cable with BNC Connectors, 3 Meters, 2 Units - Mini Converter HDMI to SDI 6G, Blackmagic Design CONVMHHS24K 6G Mini Converter, 4 Pieces - XLR Audio Connector Male Plug 3 Way Hosa XLM-025, 3-Pin, XLR Male Cable, 4 Units - XLR Audio Connector Female Plug 3 Way, NC3FXX | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-01-22 | [7 empty] | 2025-02-06 |  |  |  | 2025-02-06 | [6 empty] | GoP | 380400 | 380400 |  | 377860 | 377860
| 2 Units - Portable Power Station,Eco Flow DELTA Portable Power Station | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-01-22 | [7 empty] | 2025-02-06 |  |  |  | 2025-02-06 | [6 empty] | GoP | 242000 | 242000 |  | 239970 | 239970
| 1 Unit - AIO Desktop PC | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-01-22 | [7 empty] | 2025-02-06 |  |  |  | 2025-02-06 | [6 empty] | GoP | 77000 | 77000 |  | 74280 | 74280
| 1 Unit - 15 PS Heavy Duty Vacuum Cleaner | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-02-24 | [7 empty] | 2025-02-07 |  |  |  | 2025-02-07 | [6 empty] | GoP | 12000 | 12000 |  | 12000 | 12000
| 1 Set - Clutch Cover with Lining 11”, 1 Piece - Release Bearing, 1 Piece - Pilot Bearing | RP-Marawi | NO | NP-53.9 - Small Value Procurement |  | 2025-01-09 | [7 empty] | 2025-02-10 |  |  |  | 2025-02-10 | [6 empty] | GoP | 29980 | 29980 |  | 29980 | 29980
| 1 Unit - Multi-Function All-In-One Tank Printer | RP2-Sports | NO | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS |  | 2025-02-03 | [7 empty] | 2025-02-11 |  |  |  | 2025-02-11 | [6 empty] | GoP | 13000 | 13000 |  | 12995 | 12995
| 1 Unit - Deskfan 16" Banana Blade, 1 Unit - Standfan 18" Banana Blade, 5 Units- Travel Extension Cord 3 Gang with USB Port | FM1 | NO | NP-53.9 - Small Value Procurement |  | 2025-02-12 | [7 empty] | 2025-02-20 |  |  |  | 2025-02-20 | [6 empty] | GoP | 15000 | 15000 |  | 11300 | 11300
| 1 Unit - 8GB GDDR6 Video Card, 1 Unit - 16GB DDR4 Desktop Memory | RP-Tabuk | NO | NP-53.9 - Small Value Procurement |  | 2025-02-12 | [7 empty] | 2025-02-19 |  |  |  | 2025-02-19 | [6 empty] | GoP | 16700 | 16700 |  | 16195 | 16195
| 6 Pieces - 45mm2 Solderless Connector, 6 Pieces - 8.0mm2 Solderless Connector, 1 Box - P.D. 5.5 mm2 Stranded Wire THHN/THWN 2-Lead-Free | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-02-12 | [7 empty] | 2025-02-19 |  |  |  | 2025-02-19 | [6 empty] | GoP | 10550 | 10550 |  | 10302 | 10302
| 1 Lot - Materials for Studio Airconditioning Units Feeder Lines | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-02-13 | [7 empty] | 2025-02-20 |  |  |  | 2025-02-20 | [6 empty] | GoP | 76751 | 76751 |  | 68952 | 68952
| 1 Unit - Dry Type Induction 25KVA Transformer, 2 Unit - Dry Type Induction 25KVA Transformer | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-02-14 | [7 empty] | 2025-02-20 |  |  |  | 2025-02-20 | [6 empty] | GoP | 183400 | 183400 |  | 169000 | 169000
| 4 Pieces - Tire 185 / R 14 | General Services | NO | NP-53.9 - Small Value Procurement |  | 2025-02-17 | [7 empty] | 2025-02-24 |  |  |  | 2025-02-24 | [6 empty] | GoP | 22000 | 22000 |  | 22000 | 22000
| 1 Unit - Professional Main Camera, Tenveo LC600 4K UHD TOF Live Streaming Camera with Auto Focus 12x Optical Zoom, Sony, 1 Unit - PTZ Professional Camera, Tenveo TEVO-VL 12U 4K UHD USB/HDMI Video Conference, 1 Unit - PTZ Camera Controller with 4D Joystick Multi-Interfaced, 1 Piece - POE Switch, Gigabit 5-port, TPLink TL-SG1005P V5, 1 Unit - 55” Smart TV Sony KD55X75K 55in 4K Ultra HD Google TV, 1 Box - 16 Port Gigabit Switch, TL-SG1016D 16 Port Gigabit Desktop/Rackmount Switch, 1 Box - UTP Cable CAT6 Indoor, Belden Brand, 1 Box - AV Wirings and Connectors Roxtone XLR 3-Pole Female to XLR 3-Pole Male 5 Meters, Roxtone XLR 3-Pole Female to 6.3mm Mono Jack Plug 5 Meters, 1 Piece - HDMI Vention AACBO 20 Meters, 2 Units - Dynamic Broadcast Microphone, Professional XLR Connection, No Power required, Sensitivity: 53db Internal Foam Pop Filter, Weighted Desktop Stand, Singel Axis Suspension Suppresses Vibration, RODE PobMic USB, 3 Units - Desktop Computer for Announcer’s Booth and Admin, i5 Processor, 90VT006UPH Ideacentre 3 071RB8, 1 Unit - Video Mixer Switcher 4 HDMI Input Ports, 1 HDMI Output Port, Downstreams Keyers, Cut and Mix Functions, ATEM Mino Pro | RP-Albay | NO | NP-53.9 - Small Value Procurement |  | 2025-02-24 | [7 empty] | 2025-02-27 |  |  |  | 2025-02-27 | [6 empty] | GoP | 589200 | 589200 |  | 465730 | 465730
| 1 Unit - STXe 500 Regulator, 1 Unit - RF Pallet Model No. 959-4500, 6 Units - Resistor PFS12-301CPK | Engineeeing | NO | Direct Contracting |  | 2025-02-26 | [7 empty] | 2025-03-03 |  |  |  | 2025-03-03 | [6 empty] | GoP | 567968.65 | 567968.65 |  | 567968.65 | 567968.65
| 5 Units - Ergonomic Office Chair | RP-Naga | NO | NP-53.9 - Small Value Procurement |  | 2025-02-20 | [7 empty] | 2025-03-04 |  |  |  | 2025-03-04 | [6 empty] | GoP | 24995 | 24995 |  | 24995 | 24995
| 1 Unit - 3-in-1 Printer | News Division | NO | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS |  | 2025-02-12 | [7 empty] | 2025-03-21 |  |  |  | 2025-03-21 | [6 empty] | GoP | 10554 | 10554 |  | 10100 | 10100
| 3 Units - 1TB Portable SSD | Public Affairs | NO | NP-53.9 - Small Value Procurement |  | 2025-02-12 | [7 empty] | 2025-03-21 |  |  |  | 2025-03-21 | [6 empty] | GoP | 15000 | 15000 |  | 14310 | 14310
| 2 Units - 2TB External Hard Drive | FM1 | NO | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS |  | 2025-02-17 | [7 empty] | 2025-03-21 |  |  |  | 2025-03-21 | [6 empty] | GoP | 9100 | 9100 |  | 8600 | 8600
| 1 Set - Clutch Assembly, 1 Piece - Brake Pad, 1 Piece - Secondary Assembly, 1 Set - Wiper Blade | General Services | NO | NP-53.9 - Small Value Procurement |  | 2025-02-20 | [7 empty] | 2025-03-06 |  |  |  | 2025-03-06 | [6 empty] | GoP | 13250 | 13250 |  | 12480 | 12480
| 1 Lot - Marulas Transmitter Blocks and Posts Materials | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-02-25 | [7 empty] | 2025-03-05 |  |  |  | 2025-03-05 | [6 empty] | GoP | 385359 | 385359 |  | 315637 | 315637
| 2 Units - Office Chair with Headrest | News Division | NO | NP-53.9 - Small Value Procurement |  | 2025-02-25 | [7 empty] | 2025-03-06 |  |  |  | 2025-03-06 | [6 empty] | GoP | 7920 | 7920 |  | 6600 | 6600
| 492 Pieces - GAD Women's Month Advocacy Polo Shirt | GAD | NO | NP-53.9 - Small Value Procurement |  | 2025-02-26 | [7 empty] | 2025-03-10 |  |  |  | 2025-03-10 | [6 empty] | GoP | 295200 | 295200 |  | 171634.2 | 171634.2
| 1 CYL - R410A Refrigerant | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-02-14 | [7 empty] | 2025-03-13 |  |  |  | 2025-03-13 | [6 empty] | GoP | 12500 | 12500 |  | 8500 | 8500
| 4 Units - Leather Office Chair | RP-Alert | NO | NP-53.9 - Small Value Procurement |  | 2025-02-17 | [7 empty] | 2025-03-19 |  |  |  | 2025-03-19 | [6 empty] | GoP | 20000 | 20000 |  | 19400 | 19400
| 1 Unit - Desktop Computer | RP-Worldwide | NO | NP-53.9 - Small Value Procurement |  | 2025-03-03 | [7 empty] | 2025-03-21 |  |  |  | 2025-03-21 | [6 empty] | GoP | 49000 | 49000 |  | 47900 | 47900
| 2 Units - Webcam 1080P, 1 Piece - Gooseneck Table Top Microphone Stand with Weighted Based, 2 Pieces - USB 3.0 2.0 Extension Cable Male to Female | RP-Worldwide | NO | NP-53.9 - Small Value Procurement |  | 2025-02-26 | [7 empty] | 2025-03-21 |  |  |  | 2025-03-21 | [6 empty] | GoP | 11700 | 11700 |  | 10770 | 10770
| 1 Unit - 2HP Split Type Aircon with Installation | RP-Naga | NO | NP-53.9 - Small Value Procurement |  | 2025-02-20 | [7 empty] | 2025-03-24 |  |  |  | 2025-03-24 | [6 empty] | GoP | 54995 | 54995 |  | 51500 | 51500
| 4 Units - Cellphone, Smart Phone, IT Equipment | RP-Albay | NO | NP-53.9 - Small Value Procurement |  | 2025-03-17 | [7 empty] | 2025-03-24 |  |  |  | 2025-03-24 | [6 empty] | GoP | 196000 | 196000 |  | 160637.08 | 160637.08
| 16 Pieces - PVC Pipe ½”, 8ft, 10 Pieces - Tee Connector, 1 ½”, 10 Pieces - Reducer ½”, 10 Pieces - Coupling 1 ½” , 30 Peces - C-Clamp. 1 ½”, 50 Pieces - Tox with Screw, ½”, 1 Pieces - PVC Pipe Cement, Neltex 200cc, 3 Pieces - Masonry Drill Bit, 3mm, 3 Pieces - Hack Saw Blade, 24 TPI | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-03-11 | [7 empty] | 2025-03-28 |  |  |  | 2025-03-18 | [6 empty] | GoP | 7980 | 7980 |  | 7774 | 7774
| 2 Units - Industrial Fan 18” 115 m3/ Min Air Volume 1600rpm speed 55db Noise Level with Solid Base | General Services | NO | NP-53.9 - Small Value Procurement |  | 2025-03-11 | [7 empty] | 2025-03-28 |  |  |  | 2025-03-28 | [6 empty] | GoP | 14000 | 14000 |  | 13880 | 13880
| 2 Units - 5 Shelves Heavy Duty Utily Rack | Network | NO | NP-53.9 - Small Value Procurement |  | 2025-02-10 | [7 empty] | 2025-04-03 |  |  |  | 2025-04-03 | [6 empty] | GoP | 8000 | 8000 |  | 7900 | 7900
| 1 Piece - Hydrovac, 1 Piece - Brakd Master | General Services | NO | NP-53.9 - Small Value Procurement |  | 2025-02-26 | [7 empty] | 2025-04-03 |  |  |  | 2025-04-03 | [6 empty] | GoP | 47000 | 47000 |  | 45000 | 45000
| 2 Pieces - Tire 205/65 R16 | General Services | NO | NP-53.9 - Small Value Procurement |  | 2025-03-04 | [7 empty] | 2025-04-04 |  |  |  | 2025-04-04 | [6 empty] | GoP | 17000 | 17000 |  | 16800 | 16800
| 1 Lot - Materials for Console Table and Elevated Floor (Announcer’s Booth-New Studio) | RP-Tuguegarao | NO | NP-53.9 - Small Value Procurement |  | 2025-04-04 | [7 empty] | 2025-04-15 |  |  |  | 2025-04-15 | [6 empty] | GoP | 33273 | 33273 |  | 33273 | 33273
| 100 Pads - Printing Service of Certificate of Performance Forms | Finance | NO | NP-53.5 Agency-to-Agency |  | 2025-04-08 | [7 empty] | 2025-04-15 |  |  |  | 2025-04-15 | [6 empty] | GoP | 78000 | 78000 |  | 78000 | 78000
| 2 Units - Rewinding of 25KVA Transformer | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-04-08 | [7 empty] | 2025-04-15 |  |  |  | 2025-04-15 | [6 empty] | GoP | 100000 | 100000 |  | 100000 | 100000
| 13 Pieces - Rocket SIM Smart Bro 84GB | News Division | NO | NP-53.9 - Small Value Procurement |  | 2025-03-24 | [7 empty] | 2025-04-15 |  |  |  | 2025-04-15 | [6 empty] | GoP | 14300 | 14300 |  | 14300 | 14300
| 1 Unit - 24” Full HD Monitor, 2 Unit - 1TB SATA Solid State Drive | Property & Supply | NO | NP-53.9 - Small Value Procurement |  | 2025-03-17 | [7 empty] | 2025-04-15 |  |  |  | 2025-04-15 | [6 empty] | GoP | 20000 | 20000 |  | 17630 | 17630
| 1 Unit - 32" Inch HD TV | RP-Alert | NO | NP-53.9 - Small Value Procurement |  | 2025-04-08 | [7 empty] | 2025-04-15 |  |  |  | 2025-04-15 | [6 empty] | GoP | 14000 | 14000 |  | 12500 | 12500
| 2 Units – Brand-New Clone Desktop Computer Set | Personnel Section | NO | NP-53.9 - Small Value Procurement |  | 2025-03-11 | [7 empty] | 2025-04-15 |  |  |  | 2025-04-15 | [6 empty] | GoP | 120000 | 120000 |  | 117598 | 117598
| 1 Lot - Janitorial Cleaning Supplies | General Services | NO | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS |  | 2025-03-04 | [7 empty] | 2025-04-21 |  |  |  | 2025-04-21 | [6 empty] | GoP | 88250 | 88250 |  | 58167 | 58167
| 1 Unit - 1TB 2,5 SATA Solid State Drive | Personnel Section | NO | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS |  | 2025-03-17 | [7 empty] | 2025-04-22 |  |  |  | 2025-04-22 | [6 empty] | GoP | 6000 | 6000 |  | 5600 | 5600
| 4 Units - UPS | Finance Division | NO | NP-53.9 - Small Value Procurement |  | 2025-03-11 | [7 empty] | 2025-04-22 |  |  |  | 2025-04-22 | [6 empty] | GoP | 14000 | 14000 |  | 13200 | 13200
| 1 Lot - Livestreaming Software (1 Year Subscription) (1 Unit - Wirecast Pro for MAC, 2 Units - Wirecast Pro for Windows, 10 Units - Wirecast Studio for Windows) | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-04-14 | [7 empty] | 2025-04-22 |  |  |  | 2025-04-22 | [6 empty] | GoP | 500000 | 500000 |  | 340500 | 340500
| 4 Units - Muffin Series Axial Fan | RP-Zamboanga | NO | NP-53.9 - Small Value Procurement |  | 2025-04-11 | [7 empty] | 2025-04-24 |  |  |  | 2025-04-24 | [6 empty] | GoP | 26000 | 26000 |  | 26000 | 26000
| 500 Pieces - Zebra Premier Card | Personnel Section | NO | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS |  | 2025-03-11 | [7 empty] | 2025-04-24 |  |  |  | 2025-03-24 | [6 empty] | GoP | 9000 | 9000 |  | 9000 | 9000
| 1 Unit - Computer Desktop Rayzen 24” Monitor | RP-Cagayan de Oro | NO | NP-53.9 - Small Value Procurement |  | 2025-03-17 | [7 empty] | 2025-04-28 |  |  |  | 2025-04-28 | [6 empty] | GoP | 43837 | 43837 |  | 43837 | 43837
| 1 Unit - Airconditioner Window Type 2HP Condura | RP-Naga | NO | NP-53.9 - Small Value Procurement |  | 2025-03-12 | [7 empty] | 2025-04-29 |  |  |  | 2025-04-29 | [6 empty] | GoP | 36995 | 36995 |  | 36995 | 36995
| 1 Piece - Network Attached Storage (NAS), 4 Pieces - NAS Internal Hard Drive (12TB) | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-04-21 | [7 empty] | 2025-04-29 |  |  |  | 2025-04-29 | [6 empty] | GoP | 107124.12 | 107124.12 |  | 100400 | 100400
| 4 Units - RV (Roam Satellite Internet with 1 Year Subscriptin, 4 Units - Standard Kit | RP-Albay & Engineering | NO | NP-53.9 - Small Value Procurement |  | 2025-04-29 | [7 empty] | 2025-05-07 |  |  |  | 2025-05-07 | [6 empty] | GoP | 504000 | 504000 |  | 503040 | 503040
| 2 Units - Production Division Air conditioners 5.0 TR Split Type Floor Mounted ACU, Koppel (Vertical Air Discharge) | Production & Engineering | NO | NP-53.9 - Small Value Procurement |  | 2025-04-29 | [7 empty] | 2025-05-08 |  |  |  | 2025-05-08 | [6 empty] | GoP | 290000 | 290000 |  | 264000 | 264000
| 2 Units - Airconditioners, Sharp Window Type Manual 2HP, MOD AFT2017CM, 2 Units - Airconditioners, Sharp Window Type Manual, 1HP MDO AFT1022CM | RP-Dagupan | NO | NP-53.9 - Small Value Procurement |  | 2025-04-29 | [7 empty] | 2025-05-08 |  |  |  | 2025-05-08 | [6 empty] | GoP | 67288 | 67288 |  | 67288 | 67288
| 1 CYL - Freon R 22, 2 Sets - Wire Compressor for Carrier (5TR -7-5TR) 22.7kgs, 1 Set - Aircon Access Valve (5 Pieces) | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-05-05 | [7 empty] | 2025-05-09 |  |  |  | 2025-05-09 | [6 empty] | GoP | 14550 | 14550 |  | 14465 | 14465
| 1 Unit - GRS 18V-65 Cordless Brushless Drill/Driver 13MM Kit | General Services | NO | NP-53.9 - Small Value Procurement |  | 2025-05-02 | [7 empty] | 2025-05-07 |  |  |  | 2025-05-07 | [6 empty] | GoP | 15000 | 15000 |  | 14750 | 14750
| 4 Units - Microchip Technology APT6025BVRG, Mosfet FG Mosfet, 600V, TO -247 RoHS, VAT Inclusive | RP-Tayug | NO | NP-53.9 - Small Value Procurement |  | 2025-05-02 | [7 empty] | 2025-05-07 |  |  |  | 2025-05-07 | [6 empty] | GoP | 6272 | 6272 |  | 6272 | 6272
| 1 Lot - Production Video Editing Computer System Brand-New Cloned Desktop Computer Set | RP-Alert | NO | NP-53.9 - Small Value Procurement |  | 2025-05-06 | [7 empty] | 2025-05-13 |  |  |  | 2025-05-13 | [6 empty] | GoP | 70000 | 70000 |  | 67946 | 67946
| 1 Lot - Repair of Clutch Mechanism of Isuzu Crosswind | RP-Laoag | NO | NP-53.9 - Small Value Procurement |  | 2025-05-07 | [7 empty] | 2025-05-13 |  |  |  | 2025-05-13 | [6 empty] | GoP | 14488 | 14488 |  | 14488 | 14488
| 9 Pieces - 10 Meters Male HDMI to Male Mini HDMI 4K Ugreen HD108, 3 Pieces - Tripod (3-Way Head) Benro T8oo EX Aluminum, 6 Pieces - Video Capture Card, Ugreen CM489 | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-05-07 | [7 empty] | 2025-05-13 |  |  |  | 2025-05-13 | [6 empty] | GoP | 55500 | 55500 |  | 51010 | 51010
| 1 Lot - 180 Feet Trilon Galvanized AM Tower | RP-Batanes | NO | NP-53.9 - Small Value Procurement |  | 2025-05-07 | [7 empty] | 2025-05-13 |  |  |  | 2025-05-13 | [6 empty] | GoP | 992000 | 992000 |  | 990000 | 990000
| 4 Units - PC Deskrop Monitor 24” Inches LED Monitor | RP-Gingoog | NO | NP-53.9 - Small Value Procurement |  | 2025-05-07 | [7 empty] | 2025-05-14 |  |  |  | 2025-05-14 | [6 empty] | GoP | 20000 | 20000 |  | 20000 | 20000
| 4 Units - Office Compuiter Chair with Wheels (No Armrests) | RP-Sports | NO | NP-53.9 - Small Value Procurement |  | 2025-05-09 | [7 empty] | 2025-05-16 |  |  |  | 2025-05-15 | [6 empty] | GoP | 14000 | 14000 |  | 11200 | 11200
| 1 Unit - Window Type Airconditioner !HP HK Type | RP-Laoag | NO | NP-53.9 - Small Value Procurement |  | 2025-04-07 | [7 empty] | 2025-05-15 |  |  |  | 2025-05-15 | [6 empty] | GoP | 14449 | 14449 |  | 14449 | 14449
| 1 Unit - All-in-One Printer/Scanner (A4 and Long Documents) | RP-Gingoog | NO | NP-53.9 - Small Value Procurement |  | 2025-03-19 | [7 empty] | 2025-05-15 |  |  |  | 2025-05-15 | [6 empty] | GoP | 16000 | 16000 |  | 15990 | 15990
| 8 Pieces - 1 ¼” EMT Conduit Pipe, 8 Pieces - 1 ¼” EMT Coupling (Compression Type), 1 Piece - 1 ¼” EMT Elbow 90O, 1 Piece - 1 ¼” EMT Connector with Locknut (Compression Type), 20 Pieces - ¾” EMTConduit Pipe, 12 Pieces - ¾” EMT Coupling (Compression Type), 6 Pieces - ¾” EMT Elbow 90O, 4 Pieces - ¾” EMT Connector with Locknut (Compression Type), 8 Pieces - 1 ½” EMT Coupling (Compression Type), 1 Piece - 1 ½” EMT Elbow 90O, 1 Piece - 1 ½” EMT Connector with Locknut (Compression Type) | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-05-14 | [7 empty] | 2025-05-22 |  |  |  | 2025-05-22 | [6 empty] | GoP | 17760 | 17760 |  | 15702 | 15702
| 2 Pieces - Pull-Box with Cover, 3 Pieces - PG Strut Channel Half Slot 1-5/8 x 13/16, 20 Pieces - Galvanized Unistrut Clamp Bracket for Channel Bar 3/4”, 10 Pieces - Galvanized Unistrut Strut Clamp Bracket for Channel Bar 1”, 6 Pieces - Galvanized Unistrut Strut Clamp Bracket for Channel Bar 1-1/4”, 5 Pieces - Galvanized Unistrut Strut Clamp Bracket for Channel Bar 1-1/2”, 20 Pieces - 3/4" EMT Conduit Pipe, 12 Pieces - 3/4” EMT Elbow 90” 10 Pieces - EMT Coupling (Compression) 3/4", 10 Pieces - Liquid Tile Flexible Conduit 3/4" Soft Type, 12 Pieces - Liquid Tight Connector (Straight) 3/4" with Locknut, 12 Pieces - Liquid Tight Transition Coupling 3/4" | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-05-20 | [7 empty] | 2025-05-27 |  |  |  | 2025-05-27 | [6 empty] | GoP | 16785 | 16785 |  | 16149 | 16149
| 1 Piece - P.D. 3.5mm2 Stranded Wire THHN/THWN – 2 Lead Free, 3 Pieces - 3M Electrical Tape (Color Blue), 3 Pieces - 3M Electrical Tape (Color Red), 3 Pieces - 3M Electrical Tape (Color Yellow), 10 Pieces - 3M Electrical Tape (Tartan), 4 Pieces - 3M Comfort Grip Gloves Multi-Purpose (Large) | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-03-13 | [7 empty] | 2025-05-25 |  |  |  | 2025-05-25 | [6 empty] | GoP | 8905 | 8905 |  | 8305 | 8305
| 1 Unit - Charging Hub for Drone, 1 Piece - Drone Bag, 3 Units - Drone Battery, 1 Piece - ND Filters for Drone, 1 Piece - Lanyard for Drone, 1 Piece - Sunhood for Drone Controller. 1 {oece - Landing Pad for Drone | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-05-20 | [7 empty] | 2025-05-29 |  |  |  | 2025-05-29 | [6 empty] | GoP | 44044 | 44044 |  | 43853 | 43853
| 1 Lot - Mica Capacitor Type 293 0056 MFD 10000 PW 33 Amps at 1000kc Model 293100B562100 | RP-Iloilo | NO | NP-53.9 - Small Value Procurement |  | 2025-03-05 | [7 empty] | 2025-06-04 |  |  |  | 2025-06-04 | [6 empty] | GoP | 115000 | 115000 |  | 114780 | 114780
| 16 Liters - ATF SP4 Transmission Fluid | General Services | NO | NP-53.9 - Small Value Procurement |  | 2025-04-21 | [7 empty] | 2025-06-10 |  |  |  | 2025-06-10 | [6 empty] | GoP | 9920 | 9920 |  | 9600 | 9600
| 4 Pieces - Tire 205/65 R 16, 1 Piece - Battery 3SMF Reverse (Gold) | General Services | NO | NP-53.9 - Small Value Procurement |  | 2025-05-14 | [7 empty] | 2025-06-10 |  |  |  | 2025-06-10 | [6 empty] | GoP | 44000 | 44000 |  | 43550 | 43550
| 1 Piece - Battery for Isuzu Crosswind | RP-Bontoc | NO | NP-53.9 - Small Value Procurement |  | 2025-06-03 | [7 empty] | 2025-06-09 |  |  |  | 2025-06-09 | [6 empty] | GoP | 7500 | 7500 |  | 7500 | 7500
| 1 Lot - Materials for the Installation of Broadcast Technician's Desk at RP-Worldwide | RP-Worldwide | NO | NP-53.9 - Small Value Procurement |  | 2025-06-03 | [7 empty] | 2025-06-11 |  |  |  | 2025-06-11 | [6 empty] | GoP | 39030 | 39030 |  | 34458 | 34458
| 1 Unit - 27” Desktop PC Monitor, 1 Piec - HDMI Cable 2 Meters, 1 Unit - Wireless Keyboard and Mouse Combo | RP-Worldwide | NO | NP-53.9 - Small Value Procurement |  | 2025-06-03 | [7 empty] | 2025-06-11 |  |  |  | 2025-06-11 | [6 empty] | GoP | 10200 | 10200 |  | 10150 | 10150
| 1 Lot - Hauling of Broadcast Equipment, Office Furniture & Fixtures, Aircons and other Assorted Stuff of Radyo Pilipinas – Iloilo (from TTW Bulidng corner J.M. Basa, Mapa Street, Iloilo from Iloilo Science and Technology, La Paz, Iloilo City) | RP-Iloilo | NO | NP-53.9 - Small Value Procurement |  | 2025-06-03 | [7 empty] | 2025-06-11 |  |  |  | 2025-06-11 | [6 empty] | GoP | 8000 | 8000
| 1 Unit - Water Condensate Drain Pump for 5TR Floor Mounted Aircon | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-05-19 | [7 empty] | 2025-06-13 |  |  |  | 2025-06-13 | [6 empty] | GoP | 11500 | 11500 |  | 11500 | 11500
| 2 Units -Powered Bluetooth Bookshelf Speakers Multiple Inputs – Wireless Studio Monitors | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-05-15 | [7 empty] | 2025-06-13 |  |  |  | 2025-06-13 | [6 empty] | GoP | 9800 | 9800 |  | 9800 | 9800
| 2 Units - 1TB NV3 NVME PCIE 4.0 Internal SSD | Property & Supply | NO | NP-53.9 - Small Value Procurement |  | 2025-05-16 | [7 empty] | 2025-06-13 |  |  |  | 2025-06-13 | [7 empty] | 8000 | 8000 |  | 7990 | 7990
| 1 Unit - 43” Inch UHD 1A UT80 45 Smart TV 2024 | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-05-15 | [7 empty] | 2025-06-17 |  |  |  | 2025-06-17 | [6 empty] | GoP | 25000 | 25000 |  | 25000 | 25000
| 1 Unit - Wired Mouse, 1 Unit - Mouse Pad, 1 Unit - Printer, 1 Unit - Office Chair | Personnel Section | NO | NP-53.9 - Small Value Procurement |  | 2025-05-19 | [7 empty] | 2025-06-17 |  |  |  | 2025-06-17 | [6 empty] | GoP | 17500 | 17500 |  | 15350 | 15350
| 1 Unit - Computer Monitor 24 Inches | Finance Division | NO | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS |  | 2025-06-03 | [7 empty] | 2025-06-17 |  |  |  | 2025-06-17 | [6 empty] | GoP | 7000 | 7000 |  | 6000 | 6000
| 2 Units - Webcam 1080p HD, 1 Unit - External Storage SSD 1TB | Property & Supply | NO | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS |  | 2025-06-03 | [7 empty] | 2025-06-18 |  |  |  | 2025-06-18 | [6 empty] | GoP | 23000 | 23000 |  | 22686 | 22686
| 1 Unit - 550W 80+ Bronze Non-Modular True Power Supply, 1 Unit - 1TB SATA Solid State Drive | Property & Supply | NO | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS |  | 2025-06-03 | [7 empty] | 2025-06-19 |  |  |  | 2025-06-19 | [6 empty] | GoP | 10000 | 10000 |  | 8995 | 8995
| 1 Unit - Mobile TV Stand 55" | Administrative Division | NO | NP-53.9 - Small Value Procurement |  | 2025-05-27 | [7 empty] | 2025-06-23 |  |  |  | 2025-06-23 | [6 empty] | GoP | 16500 | 16500 |  | 16300 | 16300
| 6 Units - Tower Obstruction Light | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-04-29 | [7 empty] | 2025-06-25 |  |  |  | 2025-06-25 | [6 empty] | GoP | 159000 | 159000 |  | 154800 | 154800
| 4 Pieces - SDI Cable Assembly 1 Meter (DeEmbedder Out, Switcher In), 4 Pieces - SDI Cable Assembly 5 Meters (Server Out, DeEmbedder In), 8 Pieces - PL to XLR (M) Audio Cables (DeEmbedder Out, Mixer In), 4 Pieces - Mini Converter – SDI to Audio DeEmbedder, 1 Piece - USB Audio Interface for Remote Audio, 2 Pieces - Monittoring, 1 Piece - 27” 1920 x 1080 HDMI Monitor for Switcher Multiviewer Vertical Stand Mount Bracket for Dual Monitor, 1 Lot - Installation and System Integration | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-06-16 | [7 empty] | 2025-06-25 |  |  |  | 2025-06-25 | [6 empty] | GoP | 182360 | 182360 |  | 177500 | 177500
| 1 Lot - One (1) Month Subscription of Satellite Internet with Unlimited Data | Engineeeing | NO | NP-53.9 - Small Value Procurement |  | 2025-05-14 | [7 empty] | 2025-06-25 |  |  |  | 2025-06-25 | [6 empty] | GoP | 28000 | 28000 |  | 27160 | 27160
| 1 Unit - 1.5HP Split Type Wall Mounted Airconditioner Delivery and Installation Included (1 Year Warranty) | FM1 | NO | NP-53.9 - Small Value Procurement |  | 2025-05-14 | [7 empty] | 2025-06-26 |  |  |  | 2025-06-26 | [6 empty] | GoP | 60000 | 60000 |  | 51000 | 51000
[26 empty] | 12324137.49 | 12324137.49 | 0 | 11237125.15 | 11237125.15 | 0 | -
-
-
[18 empty] | Total Allotted Budget of Procurement Activities | [7 empty] | 12324137.49 | 12324137.49 | 0 |  |  |  | 0%
[25 empty] | Total Contract Price of Procurement Activities Conducted |  |  |  | 11237125.15 | 11237125.15 | 0
[25 empty] | Total Savings (Total Allotted Budget - Total Contract Price) | 1087012.34
ONGOING PROCUREMENT ACTIVITIES | [31 empty] | -
-
-
-
-
-
-
[7 empty] | #DIV/0! | [17 empty] | Total Allotted Budget of On-going Procurement Activities | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
|  | Prepared by: | [9 empty] | Recommended for Approval by: | [16 empty] | APPROVED:
|  | RODNEY O. VILLANUEVA | [9 empty] | ALAN L. ALLANIGUE | [16 empty] | FERNANDO A. SANGA
|  | BAC Secretariat | [9 empty] | BAC Chairperson | [16 empty] | Director IV
Head of the Procuring Entity